## Summary
Business Case - Gate 1
Taxiway K West Rehabiltation/ Reconstruction (w/o M&I btwn Rwy 3-21 and NRWY) | : Project Title
701219 | : Project Number
G. Tupper | : Originator
C. Edwards | : Project Manager (If Assigned)
G. Evenhus | : Reviewer/Approver
2023-07-28 | : Date (Last Revised)
0 | : Revision#
Level 3: Project scope is a "vision" with limited detail | : Scope Accuracy
Level B: Conceptual engineering performed | : Engineering Effort
Business Case - Gate 1 | : Project Stage
SCOPE DESCRIPTION:
Rehabiliate Taxiway K West (Left and Right) mainline and adjacent Taxiway K apron adjacent to the Terminal Buidling (approx. Gates D3-D13, E2.5-E6) with a full depth AC pavement section; this area is east of Taxiway T. Rehabilitate the western section of Taxiway K with a mill and inlay. Rehabilitate Taxiway K (west of Taxiway E and extending from Taxiway K/E hold line to between Taxiways E and T) with 3" mill and inlay; north limits at Taxiway E/Runway 10L-28R hold line and south limits at intersection of Taxiways E/K transition to concrete pavement. Install new electrical centerline lighting infrastructure in full depth pavement areas. Includes thermoplastic markers for hold lines to Rwy 3-21. Excludes pavement at hold bars to Rwy 10L-28R (North Rwy). See sketches on Work Plan tab of this spreadsheet.
SCOPE ASSUMPTIONS AND CLARIFICATIONS:
General Assumptions: • This project will be completed as a stand along project. See supporting Work Plan sketch for project area. • Construction of project is planned for May 2026 to September 2026. • Maintain existing alignment and striping.
Operational Assumptions: • Concourse D gates adjacent to the Taxiway K reconstruction area will be closed during construction. A maximum of 2 gates can be closed at one time.
Environmental Assumptions: • No upgrades to stormwater treatment are required. • No contaminated soils are in the areas of full depth excavation. • Low level petroleum contamination in ground water may occur. Dewatering will be captured and tested.
Earthwork Assumptions: • Earthwork will only occur in areas of full depth reconstruction in Taxiway K. Paving activities will otherwise not impact existing subgrade. • Excess Common Excavation will be taken off-site and not stockpiled.
Paving Assumptions: • This estimate was prepared with preliminary geotechnical information. The full report may provide adjustments to the estimated pavement sections. • Existing pavement sections are based upon cores performed for the geotechnical report. • Taxiway K mainline adjacent to the Terminal Building will be rehabilitated with a full depth AC pavement section. Project will use pavement section provided by preliminary geotechnical information (4” AC surface course, 14” AC base course, 6” agg base, and 29” of sand subbase). • Taxiway K apron adjacent to the Terminal Building will be rehabilitated with a full depth AC pavement section. Project will use pavement section provided by preliminary geotechnical information (4” AC surface course, 11” AC base course, 6” agg base, and 13” of sand subbase). • No shoulder work will be required. • The western section of Taxiway K will be rehabilitated with a 3” AC mill and inlay. • New full depth AC areas will assume a 15’ wide AC tie in to adjacent taxiways and aprons to account for shifts in grading. Tie in areas will be a 3” ACP mill and inlay. |  | Suggest using same pavement sections for K - not worth changing for BC | 1
Utility Assumptions: • Stormwater work shown in this estimate corresponds to an identified need in the stormwater master planning Solution 7C documents in the vicinity of this project. The work was included in this estimate because completing it now will minimize future impacts to the new pavements, and the cost is the most economical now because a contractor is already mobilized in the area. • Underdrains will be placed in areas of full depth reconstruction. • Trench drains will not be required along the edge of the existing PCCP terminal apron. |  | what is identified in SWMP?- pipe size - not worth changing for BC
Electrical Assumptions • Existing centerline lights are LED and will be reused. Install new conduit and conductors for Taxiway K mainline and apron. Protect existing edge lights. • Protect existing edge lights, centerline lights, and threshold in the western section of Taxiway K. • No work will be required on existing supporting electrical infrastructure. • No new lighting will be required.
REVISION NOTES:
HARD COST SUBTOTAL | 15778427.8667
SOFT COST SUBTOTAL | 3984053.0363
HARD COST CONTINGENCY | 4733528.36
(Enter % of Hard Cost): | 30%
SOFT COST CONTINGENCY | 597607.9554
(Enter % of Soft Cost): | 15%
ESCALATION | 3886073.187
Based on Calculations Below Under "Escalation Calculator" : | 15.49%
TOTAL PROJECT ESTIMATE | 28979690.4055
Hard Cost Summary
HARD COST DESCRIPTION | TOTAL
01 General Requirements | 2359402.5333
02 Existing Conditions | 0
03 Concrete | 0
04 Masonry | 0
05 Metals | 0
06 Wood Plastics And Composites | 0
07 Thermaland Moisture Protection | 0
08 Openings | 0
09 Finishes | 0
10 Specialties | 0
11 Equipment | 0
12 Furnishings | 0
13 Special Construction | 0
14 Conveying Equipment | 0
21 Fire Suppression | 0
22 Plumbing | 0
23 Heating Ventilating And Air Conditioning | 0
26 Electrical | 570000
27 Communications | 0
28 Electronic Safety And Security | 0
31 Earthwork | 0
32 Exterior Improvements | 0
33 Utilities | 0
34 Transportation | 1377500
35 Waterway And Marine | 0
41 Material Proc And Handling Eq. | 0
51 Earthwork FAA | 4427285.3333
52 Flexible Base Courses FAA | 510750
53 Rigid Base Courses FAA | 0
54 Flexible Surface Courses FAA | 5509390
55 Rigid Pavement FAA | 0
56 Miscellaneous FAA | 177900
57 Fencing FAA | 0
58 Drainage FAA | 750000
59 Turfing FAA | 28000
60 Lighting Installation FAA | 68200
Misc - Not Listed | 0
1 | 1
Soft Cost Summary
101000 - Project Admin & Mgmt-General | 9467.0567
101400 - Project Admin & Mgmt-Design | 126227.4229
101500 - Project Admin & Mgmt-Construction | 94670.5672
141010 - Design-Outside Design Services | 899370.3884
141100 - Design-Specification Development | 15778.4279
141600 - Design-Environmental | 31556.8557
141700 - Design-PE Design | 331346.9852
141800 - Design-Survey | 205119.5623
141900 - Design-Drawing and Development | 205119.5623
142100 - Design-Construction/Inspection Suppor | 0
142600 - Design-IT Design Support | 0
171500 - Development-Conceptual Design | 0
191100 - Construction-Equipment Contracts | 0
191200 - Construction-Management | 205119.5623
191300 - Construction-Inspection | 315568.5573
191400 - Construction-Testing | 110448.9951
191500 - Construction-Survey | 220897.9901
191600 - Construction-Environmental | 15778.4279
191800 - Construction-Engineering Support | 110448.9951
191810 - Construction-Outside Construction Services | 157784.2787
191900 - Construction-Maintenance | 15778.4279
192000 - Construction-IT | 0
201400 - Permitting-City | 0
781100 - Project Close Out-As Builts | 11044.8995
781200 - Project Close Out-Survey | 11044.8995
781300 - Project Close Out-Technical Reference Center | 7889.2139
781400 - Project Close Out-Geographic Information System | 15778.4279
908550 - Capitalized Alloc Sup Svs-Annual Engineering Adjustment | 0
909000 - Capitalized Alloc Sup Svs-Capitalized Allocated Supp Svs | 867813.5327
Misc - Not Listed | 0
Escalation Calculator
Base Escalation Rate (Yearly): | 5%
Date of Estimate: | 2023-05-31
Construction Start: | 2026-04-01
Construction Finish: | 2026-10-07
Construction Midpoint: | 2026-07-04 12:00
Est. Date to Const. Start: | 1036
34.0602
2.8384
Const. Start to Midpoint: | 94.5
3.1068
0.2589
Estimate Date to Midpoint: | 1130.5
37.1671
3.0973
Escalation: | 15.49%
Instructions:
STEP 1: Fill in User Defined fields in white and green cells. Blue fields are auto-populated.
STEP 2: Fill out Hard/ Soft Cost Estimate forms (Optional Soft Cost Form Available)
STEP 3: Click on the Dashboard form and manually update dashboard.
Scope Accuracy:
Level 1: Project scope well understood and well defined.
Level 2: Project scope conceptual. Scope lacks detail due to potential permit requirements; Unknown project conditions; limited knowledge of external impacts.
Level 3: Project scope is a "vision" with limited detail.
Engineering Effort:
Level A: Preliminary engineering performed. Technical is information available, engineering calculations have been performed; clear understanding of the materials size and quantities needed to execute job. Schedule understood; staff and permitting is fairly clear, (however this element may still need refining.) Project Development & Construction Contingencies ranges between 15%-20%.
Level B: Conceptual engineering performed. Technical information is available, rough engineering calculations may have been performed, or similar information from previous similar work is compared and used. Project Development Contingencies ranges between 15% to 25% and Construction Contingencies ranges between 20% to 30%.
Level C: No engineering performed. Educated guesstimating. Limited technical information available and/or analysis performed. Project Development and Construction Contingencies should be selected appropriately by Project Manager. Contingency may range up to 50%.

## Hard Cost Estimate Form
Hard costs estimated by removing area 1 from 4-19-2023 estimates showing "Areas 1+2+3" and adding mill & inlay portion from 8-25-22 estimate
Hard Cost Estimating Form (Details)
Project Title: | Taxiway K West Rehabiltation/ Reconstruction (w/o M&I btwn Rwy 3-21 and NRWY) |  | Instructions:
Project #: | 701219 |  | Step 1: Select Division from Dropdown in Column A to Populate Options in Column B
Rev #: | 0 |  | Step 2: Select Associated Cost Code Description from Dropdown in Column B [Optional]
Rev # Date: | 2023-07-28 |  | Step 3: Fill in Estimating Table in Columns (D to G) |  |  | Hard Cost Total: | 15778427.8667
Division | Cost Code Description | Cost Code | Item Description | QTY | Unit | Unit Rate | Total
01 General Requirements | MobilizationandDemobilization | 15000 | Mobilization | 0.1 | % | 14344025.3333 | 1434402.5333
01 General Requirements | Sweeping | 15002 | Sweeping | 1 |  | 250000 | 250000
01 General Requirements | SecurityControl | 13500 | Security Control Monitoring | 1 |  | 175000 | 175000
01 General Requirements | Escort | 13501 | Escorting | 1 |  | 250000 | 250000
01 General Requirements | TrafficControl | 15001 | Traffic Control | 1 |  | 250000 | 250000
51 Earthwork FAA | Surface Preparation (P-101) | 510000 | Asphalt Concrete Pavement Removal | 40833 | SY | 15 | 612495
51 Earthwork FAA | Surface Preparation (P-101) | 510000 | Asphalt Concrete Pavement Milling 0-3 Inches | 17038.8889 | SY | 6 | 102233.3333 | 7-25-2023 Revised to reflect planned 3" M&I for Taxiway K West (Taxiway K/E hold line to between Taxiways E and T) plus tie-ins on Taxiway K West (East of Taxiway E)
51 Earthwork FAA | Surface Preparation (P-101) | 510000 | Asphalt Concrete Pavement Milling 3-6 Inches | 0 | SY | 12
51 Earthwork FAA | Surface Preparation (P-101) | 510000 | Subgrade Preparation | 40835 | SY | 10 | 408350
51 Earthwork FAA | Excavation and Embankment (P-152) | 510000 | Unclassified Excavation (includes agg base and subbase) | 35370 | CY | 42 | 1485540
51 Earthwork FAA | Excavation and Embankment (P-152) | 510000 | Unsuitable Excavation | 1150 | CY | 93 | 106950
51 Earthwork FAA | Geotextile (P-161) | 510000 | Geotextile | 1839 | SY | 3 | 5517
51 Earthwork FAA | Subbase Course (P-154) | 510000 | Sand Subbase | 21340 | CY | 55 | 1173700
51 Earthwork FAA | Surface Preparation (P-101) |  | Surface Grading | 0 | SY | 10
51 Earthwork FAA | Temporary Air & Water Pollution, Soil Erosion, & Siltation Control (P-156) | 510000 | Inlet Protection | 50 | Ea | 150 | 7500
51 Earthwork FAA | Temporary Air & Water Pollution, Soil Erosion, & Siltation Control (P-156) | 510000 | Misc. Erosion Control | 1 | LS | 250000 | 250000
51 Earthwork FAA | Temporary Air & Water Pollution, Soil Erosion, & Siltation Control (P-156) | 510000 | Dewatering | 1 | LS | 275000 | 275000
52 Flexible Base Courses FAA | Crushed Aggregate Base Course (P-209) | 520000 | Crushed Aggregate Base Course | 6810 | CY | 75 | 510750
54 Flexible Surface Courses FAA | (Superpave™) Plant Mix Bituminous Pavements (P-401sp) | 540000 | Surface Course | 12840 | Ton | 137 | 1759080 | 7/28/2023 Revised to reflect removal of Twy K West M&I (K1/10L to K/E)
54 Flexible Surface Courses FAA | (Superpave™) Plant Mix Bituminous Bases (P-403sp) | 540000 | Base Course | 29530 | Ton | 127 | 3750310 | 7/28/2023 Revised to reflect removal of Twy K West M&I (K1/10L to K/E)
56 Miscellaneous FAA | Runway and Taxiway Painting (P-620) | 560000 | Permanant Pavement Marking | 11000 | SF | 2.5 | 27500
56 Miscellaneous FAA | Runway and Taxiway Painting (P-620) | 560000 | Blackout Pavement Marking | 4000 | SF | 1.25 | 5000
56 Miscellaneous FAA | Runway and Taxiway Painting (P-620) | 560000 | Temporary Pavement Marking | 4000 | SF | 1.5 | 6000
56 Miscellaneous FAA | Runway and Taxiway Painting (P-620) | 560000 | Preformed Roadway Marking | 5000 | SF | 25 | 125000
56 Miscellaneous FAA | Runway and Taxiway Painting (P-620) | 560000 | Thermoplastic marking for hold bar striping at Rwy 3-21 | 3200 | SF | 4.5 | 14400
58 Drainage FAA | Pipe for Storm Drains and Culverts (D-701) | 580000 | Misc. Storm Sewer Work | 1 | LS | 450000 | 450000
58 Drainage FAA | Slotted Drains (D-702) | 580000 | Underdrain System | 4000 | LF | 50 | 200000
58 Drainage FAA | Manholes, Catch Basins, Inlets, and Inspection Holes (D-751) | 580000 | Manholes | 5 | Ea | 20000 | 100000
26 Electrical | Lighting | 265000 | General Electrical Removal | 1 | LS | 300000 | 300000
26 Electrical | Lighting | 265000 | Misc Electrical Work | 1 | LS | 250000 | 250000
26 Electrical | Lighting | 265000 | Temporary Circuit Connection | 1 | LS | 20000 | 20000
34 Transportation | AirfieldLighting | 344300 | Install New Taxiway Centerline Light on CF Base Can, CF Extension, CF Flange Ring, and CF Transformer | 95 | Ea | 4500 | 427500
34 Transportation | AirfieldLighting | 344300 | Install New Taxiway Centerline Light on Existing Base Can with existing Transformer (Includes stop taxiway stop bars) | 125 | Ea | 1300 | 162500 | 7-25-2023 Reduced by 50 lights (between but not including lights in hold bars at K1 and Twy E; includes lights at hold bar at K/K1)
34 Transportation | AirfieldLighting | 344300 | Install New Taxiway Edge Light on CF Base Can, CF Extension, CF Flange Ring, and CF Transformer | 175 | Ea | 4500 | 787500
60 Lighting Installation FAA | Airport Underground Electrical Duct (L-110) | 600000 | 2-Inch PVC in P-610 | 1500 | LF | 40 | 60000
60 Lighting Installation FAA | Airport Underground Cable (L-108) | 600000 | No. 8 AWG, 5kV, L-824, Type C Cable Installed in Trench, Duct Bank or Conduit | 2000 | LF | 2 | 4000
60 Lighting Installation FAA | Airport Underground Cable (L-108) | 600000 | No. 6 AWG, Solid, Bare Counterpoise Wire | 1500 | LF | 2 | 3000
60 Lighting Installation FAA | Airport Underground Cable (L-108) | 600000 | Ground Rod for Counterpoise | 4 | Ea | 300 | 1200
59 Turfing FAA | Seeding (T-901) |  | Seeding, Topsoiling, and Jet Blast Control | 0.8 | Acre | 35000 | 28000

## Soft Cost Estimating Form
Soft Cost Estimating Form (Details) | [11 empty] | 16.45
| Project Title: |  | Taxiway K West Rehabiltation/ Reconstruction (w/o M&I btwn Rwy 3-21 and NRWY)
| Project #: |  | 701219 | [6 empty] | Estimating Method | Percentage Based
| Rev #: |  | 0 | [6 empty] | Soft Cost %
| Rev # Date: |  | 2023-07-28 | [6 empty] | Soft Cost Total: | 3984053.0363
15778427.8667
Chart Type | Chart Name | Description | Cost Code | Description | Container | Container Description | Interdepartmental Labor | Total Unit Rate | Qty | Unit | Total
M01 | Engineering Standard | Engineering Standard - Project Admin & Mgmt | 101000 | Project Admin & Mgmt-General | M02 | General Administration | LBR | 15778427.8667 | 0.06 | % | 9467.0567
M01 | Engineering Standard | Engineering Standard - Project Admin & Mgmt | 101400 | Project Admin & Mgmt-Design | M02 | General Administration | LBR | 15778427.8667 | 0.8 | % | 126227.4229
M01 | Engineering Standard | Engineering Standard - Project Admin & Mgmt | 101500 | Project Admin & Mgmt-Construction | M02 | General Administration | LBR | 15778427.8667 | 0.6 | % | 94670.5672
M01 | Engineering Standard | Engineering Standard - Design | 141010 | Design-Outside Design Services | M03 | Design |  | 15778427.8667 | 5.7 | % | 899370.3884
M01 | Engineering Standard | Engineering Standard - Design | 141100 | Design-Specification Development | M03 | Design | LBR | 15778427.8667 | 0.1 | % | 15778.4279
M01 | Engineering Standard | Engineering Standard - Design | 141600 | Design-Environmental | M03 | Design | LBR | 15778427.8667 | 0.2 | % | 31556.8557
M01 | Engineering Standard | Engineering Standard - Design | 141700 | Design-PE Design | M03 | Design | LBR | 15778427.8667 | 2.1 | % | 331346.9852
M01 | Engineering Standard | Engineering Standard - Design | 141800 | Design-Survey | M03 | Design | LBR | 15778427.8667 | 1.3 | % | 205119.5623
M01 | Engineering Standard | Engineering Standard - Design | 141900 | Design-Drawing and Development | M03 | Design | LBR | 15778427.8667 | 1.3 | % | 205119.5623
M01 | Engineering Standard | Engineering Standard - Design | 142100 | Design-Construction/Inspection Suppor | M03 | Design | LBR | 15778427.8667 |  | % | 0
M01 | Engineering Standard | Engineering Standard - Design | 142600 | Design-IT Design Support | M03 | Design | LBR | 15778427.8667 |  | % | 0
M01 | Engineering Standard | Engineering Standard - Development | 171500 | Development-Conceptual Design | M03 | Design | LBR | 15778427.8667 |  | % | 0
M01 | Engineering Standard | Engineering Standard - Construction | 191100 | Construction-Equipment Contracts | M04 | Execute/Build | LBR | 15778427.8667 |  | % | 0
M01 | Engineering Standard | Engineering Standard - Construction | 191200 | Construction-Management | M04 | Execute/Build | LBR | 15778427.8667 | 1.3 | % | 205119.5623
M01 | Engineering Standard | Engineering Standard - Construction | 191300 | Construction-Inspection | M04 | Execute/Build | LBR | 15778427.8667 | 2 | % | 315568.5573
M01 | Engineering Standard | Engineering Standard - Construction | 191400 | Construction-Testing | M04 | Execute/Build | LBR | 15778427.8667 | 0.7 | % | 110448.9951
M01 | Engineering Standard | Engineering Standard - Construction | 191500 | Construction-Survey | M04 | Execute/Build | LBR | 15778427.8667 | 1.4 | % | 220897.9901
M01 | Engineering Standard | Engineering Standard - Construction | 191600 | Construction-Environmental | M04 | Execute/Build | LBR | 15778427.8667 | 0.1 | % | 15778.4279
M01 | Engineering Standard | Engineering Standard - Construction | 191800 | Construction-Engineering Support | M04 | Execute/Build | LBR | 15778427.8667 | 0.7 | % | 110448.9951
M01 | Engineering Standard | Engineering Standard - Construction | 191810 | Construction-Outside Construction Services | M04 | Execute/Build |  | 15778427.8667 | 1 | % | 157784.2787
M01 | Engineering Standard | Engineering Standard - Construction | 191900 | Construction-Maintenance | M04 | Execute/Build | LBR | 15778427.8667 | 0.1 | % | 15778.4279
M01 | Engineering Standard | Engineering Standard - Construction | 192000 | Construction-IT | M04 | Execute/Build | LBR | 15778427.8667 |  | % | 0
M01 | Engineering Standard | Engineering Standard - Permitting | 201400 | Permitting-City | M02 | General Administration | LBR | 15778427.8667 | 0 | % | 0
M01 | Engineering Standard | Engineering Standard - Project Close Out | 781100 | Project Close Out-As Builts | M05 | Close-out | LBR | 15778427.8667 | 0.07 | % | 11044.8995
M01 | Engineering Standard | Engineering Standard - Project Close Out | 781200 | Project Close Out-Survey | M05 | Close-out | LBR | 15778427.8667 | 0.07 | % | 11044.8995
M01 | Engineering Standard | Engineering Standard - Project Close Out | 781300 | Project Close Out-Technical Reference Center | M05 | Close-out | LBR | 15778427.8667 | 0.05 | % | 7889.2139
M01 | Engineering Standard | Engineering Standard - Project Close Out | 781400 | Project Close Out-Geographic Information System | M05 | Close-out | LBR | 15778427.8667 | 0.1 | % | 15778.4279
M01 | Engineering Standard | Engineering Standard - Capitalized Alloc Sup Svs | 908550 | Capitalized Alloc Sup Svs-Annual Engineering Adjustment | M02 | General Administration |  | 15778427.8667 |  | % | 0
M01 | Engineering Standard | Engineering Standard - Capitalized Alloc Sup Svs | 909000 | Capitalized Alloc Sup Svs-Capitalized Allocated Supp Svs | M02 | General Administration |  | 15778427.8667 | 5.5 | % | 867813.5327
M02 | IT Standard | IT Standard - Project Admin & Mgmt | 101000 | Project Admin & Mgmt-General | M02 | General Administration | LBR | 162 |  | Hr | 0
M02 | IT Standard | IT Standard - Project Admin & Mgmt | 101200 | Project Admin & Mgmt-Project Mgmt | M02 | General Administration | LBR | 162 |  | Hr | 0
M02 | IT Standard | IT Standard - Analysis & Requirements Defin. | 121000 | Analysis & Requirements Defin.-General | M01 | Project Planning | LBR | 149 |  | Hr | 0
M02 | IT Standard | IT Standard - Analysis & Requirements Defin. | 121200 | Analysis & Requirements Defin.-Select Vendor | M01 | Project Planning | LBR | 149 |  | Hr | 0
M02 | IT Standard | IT Standard - Security | 131000 | Security-General | M02 | General Administration | LBR | 149 |  | Hr | 0
M02 | IT Standard | IT Standard - Design | 141000 | Design-General | M03 | Design | LBR | 149 |  | Hr | 0
M02 | IT Standard | IT Standard - Design | 141010 | Design-Outside Design Services | M03 | Design |  |  |  |  | 0
M02 | IT Standard | IT Standard - Design | 142600 | Design-IT Design Support | M03 | Design | LBR | 149 |  | Hr | 0
M02 | IT Standard | IT Standard - Acquisition | 162300 | Acquisition-Contract | M04 | Execute/Build | LBR | 149 |  | Hr | 0
M02 | IT Standard | IT Standard - Acquisition | 162400 | Acquisition-Procurement | M04 | Execute/Build | LBR | 149 |  | Hr | 0
M02 | IT Standard | IT Standard - Development | 171000 | Development-Database Administration | M04 | Execute/Build | LBR | 149 |  | Hr | 0
M02 | IT Standard | IT Standard - Development | 171100 | Development-Software Develop. & Config. | M04 | Execute/Build | LBR | 149 |  | Hr | 0
M02 | IT Standard | IT Standard - Development | 171510 | Development-Outside Design Services | M04 | Execute/Build |  |  |  |  | 0
M02 | IT Standard | IT Standard - Implementation | 181400 | Implementation-Hardware Installation | M04 | Execute/Build | LBR | 149 |  | Hr | 0
M02 | IT Standard | IT Standard - Implementation | 181600 | Implementation-Software Installation | M04 | Execute/Build | LBR | 149 |  | Hr | 0
M02 | IT Standard | IT Standard - Implementation | 181700 | Implementation-IT Conversion | M04 | Execute/Build | LBR | 149 |  | Hr | 0
M02 | IT Standard | IT Standard - Construction | 191810 | Construction-Outside Construction Services | M04 | Execute/Build |  |  |  |  | 0
M02 | IT Standard | IT Standard - Documentation | 261000 | Documentation-Technical Documentation | M04 | Execute/Build | LBR | 149 |  | Hr | 0
M02 | IT Standard | IT Standard - Documentation | 261400 | Documentation-Training Materials | M04 | Execute/Build | LBR | 149 |  | Hr | 0
M02 | IT Standard | IT Standard - Testing | 281000 | Testing-General | M04 | Execute/Build | LBR | 149 |  | Hr | 0
M02 | IT Standard | IT Standard - Training | 291000 | Training-Core User Training | M04 | Execute/Build | LBR | 149 |  | Hr | 0
M02 | IT Standard | IT Standard - Training | 291200 | Training-Support Team Training | M04 | Execute/Build | LBR | 149 |  | Hr | 0
M02 | IT Standard | IT Standard - Project Close Out | 781000 | Project Close Out-General | M05 | Close-out | LBR |  |  |  | 0
M02 | IT Standard | IT Standard - Capitalized Alloc Sup Svs | 908550 | Capitalized Alloc Sup Svs-Annual Engineering Adjustment | M02 | General Administration |  | 63 |  |  | 0
M02 | IT Standard | IT Standard - Capitalized Alloc Sup Svs | 909000 | Capitalized Alloc Sup Svs-Capitalized Allocated Supp Svs | M02 | General Administration |  | 63 |  |  | 0
M03 | Upland Control Sites | Upland Control Sites - Project Admin & Mgmt | 101000 | Project Admin & Mgmt-General | M02 | General Administration | LBR |  |  |  | 0
M03 | Upland Control Sites | Upland Control Sites - Design | 141010 | Design-Outside Design Services | M03 | Design |  |  |  |  | 0
M03 | Upland Control Sites | Upland Control Sites - Design | 141400 | Design-Remedial Design | M03 | Design | LBR |  |  |  | 0
M03 | Upland Control Sites | Upland Control Sites - Design | 141600 | Design-Environmental | M03 | Design | LBR |  |  |  | 0
M03 | Upland Control Sites | Upland Control Sites - Design | 141700 | Design-PE Design | M03 | Design | LBR |  |  |  | 0
M03 | Upland Control Sites | Upland Control Sites - Design | 142600 | Design-IT Design Support | M03 | Design | LBR |  |  |  | 0
M03 | Upland Control Sites | Upland Control Sites - Design | 142700 | Design-Maintenance Design Support | M03 | Design | LBR |  |  |  | 0
M03 | Upland Control Sites | Upland Control Sites - Planning | 151100 | Planning-Assessment/Planning | M03 | Design | LBR |  |  |  | 0
M03 | Upland Control Sites | Upland Control Sites - Planning | 151110 | Planning-Preliminary Assessment | M03 | Design | LBR |  |  |  | 0
M03 | Upland Control Sites | Upland Control Sites - Planning | 151200 | Planning-Site Investigation | M03 | Design | LBR |  |  |  | 0
M03 | Upland Control Sites | Upland Control Sites - Planning | 151300 | Planning-Remedial Investigation | M03 | Design | LBR |  |  |  | 0
M03 | Upland Control Sites | Upland Control Sites - Planning | 151310 | Planning-Cargill OU1 | M03 | Design | LBR |  |  |  | 0
M03 | Upland Control Sites | Upland Control Sites - Planning | 151320 | Planning-OU2 | M03 | Design | LBR |  |  |  | 0
M03 | Upland Control Sites | Upland Control Sites - Planning | 151600 | Planning-Feasibility Study | M03 | Design | LBR |  |  |  | 0
M03 | Upland Control Sites | Upland Control Sites - Development | 171510 | Development-Outside Design Services | M04 | Execute/Build |  |  |  |  | 0
M03 | Upland Control Sites | Upland Control Sites - Implementation | 181000 | Implementation-Remedial Action | M04 | Execute/Build | LBR |  |  |  | 0
M03 | Upland Control Sites | Upland Control Sites - Implementation | 181100 | Implementation-O&M-Systems | M04 | Execute/Build | LBR |  |  |  | 0
M03 | Upland Control Sites | Upland Control Sites - Implementation | 181200 | Implementation-O&M-Monitoring | M04 | Execute/Build | LBR |  |  |  | 0
M03 | Upland Control Sites | Upland Control Sites - Construction | 191810 | Construction-Outside Construction Services | M04 | Execute/Build |  |  |  |  | 0
M03 | Upland Control Sites | Upland Control Sites - Legal/Regulatory | 231300 | Legal/Regulatory-Pre-Litigation Preparation | M04 | Execute/Build | LBR |  |  |  | 0
M03 | Upland Control Sites | Upland Control Sites - Legal/Regulatory | 231400 | Legal/Regulatory-Litigation Defense | M04 | Execute/Build | LBR |  |  |  | 0
M03 | Upland Control Sites | Upland Control Sites - Legal/Regulatory | 231600 | Legal/Regulatory-Closure Report/NFA | M04 | Execute/Build | LBR |  |  |  | 0
M03 | Upland Control Sites | Upland Control Sites - Legal/Regulatory | 231900 | Legal/Regulatory-Action Memo | M04 | Execute/Build | LBR |  |  |  | 0
M03 | Upland Control Sites | Upland Control Sites - Public Records Request | 241000 | Public Records Request-General | M02 | General Administration | LBR |  |  |  | 0
M03 | Upland Control Sites | Upland Control Sites - Outreach | 251000 | Outreach-General | M02 | General Administration | LBR |  |  |  | 0
M03 | Upland Control Sites | Upland Control Sites - Outreach | 251010 | Outreach-Community Relations | M02 | General Administration | LBR |  |  |  | 0
M03 | Upland Control Sites | Upland Control Sites - Cost Recovery | 301000 | Cost Recovery-PRP Pursuit | M04 | Execute/Build | LBR |  |  |  | 0
M03 | Upland Control Sites | Upland Control Sites - Payments | 321000 | Payments-Group Payments | M04 | Execute/Build | LBR |  |  |  | 0
M03 | Upland Control Sites | Upland Control Sites - Payments | 321300 | Payments-Oversight Costs | M04 | Execute/Build | LBR |  |  |  | 0
M03 | Upland Control Sites | Upland Control Sites - Payments | 321310 | Payments-Oversight Costs-EPA | M04 | Execute/Build | LBR |  |  |  | 0
M03 | Upland Control Sites | Upland Control Sites - Payments | 321320 | Payments-Oversight Costs-DEQ | M04 | Execute/Build | LBR |  |  |  | 0
M03 | Upland Control Sites | Upland Control Sites - Payments | 321330 | Payments-Oversight Costs-Tribes | M04 | Execute/Build | LBR |  |  |  | 0
M03 | Upland Control Sites | Upland Control Sites - Payments | 321340 | Payments-Oversight Costs-Trustees | M04 | Execute/Build | LBR |  |  |  | 0
M03 | Upland Control Sites | Upland Control Sites - Contingency | 790000 | Contingency-Contingency | M02 | General Administration |  |  |  |  | 0
M03 | Upland Control Sites | Upland Control Sites - Capitalized Alloc Sup Svs | 909000 | Capitalized Alloc Sup Svs-Capitalized Allocated Supp Svs | M02 | General Administration |  |  |  |  | 0
M04 | Natural Resource Damages | Natural Resource Damages - Project Admin & Mgmt | 101000 | Project Admin & Mgmt-General | M02 | General Administration | LBR |  |  |  | 0
M04 | Natural Resource Damages | Natural Resource Damages - Design | 141500 | Design-Restoration | M03 | Design | LBR |  |  |  | 0
M04 | Natural Resource Damages | Natural Resource Damages - Design | 141510 | Design-Restore. Plan & Dev, incl. Des | M03 | Design | LBR |  |  |  | 0
M04 | Natural Resource Damages | Natural Resource Damages - Planning | 151100 | Planning-Assessment/Planning | M03 | Design | LBR |  |  |  | 0
M04 | Natural Resource Damages | Natural Resource Damages - Planning | 151120 | Planning-Strategy/Planning | M03 | Design | LBR |  |  |  | 0
M04 | Natural Resource Damages | Natural Resource Damages - Planning | 151130 | Planning-Injury Assessment | M03 | Design | LBR |  |  |  | 0
M04 | Natural Resource Damages | Natural Resource Damages - Implementation | 181200 | Implementation-O&M-Monitoring | M04 | Execute/Build | LBR |  |  |  | 0
M04 | Natural Resource Damages | Natural Resource Damages - Implementation | 181300 | Implementation-Restoration | M04 | Execute/Build | LBR |  |  |  | 0
M04 | Natural Resource Damages | Natural Resource Damages - Implementation | 181320 | Implementation-Restoration Implementation | M04 | Execute/Build | LBR |  |  |  | 0
M04 | Natural Resource Damages | Natural Resource Damages - Legal/Regulatory | 231000 | Legal/Regulatory-Design | M04 | Execute/Build | LBR |  |  |  | 0
M04 | Natural Resource Damages | Natural Resource Damages - Legal/Regulatory | 231300 | Legal/Regulatory-Pre-Litigation Preparation | M04 | Execute/Build | LBR |  |  |  | 0
M04 | Natural Resource Damages | Natural Resource Damages - Legal/Regulatory | 231400 | Legal/Regulatory-Litigation Defense | M04 | Execute/Build | LBR |  |  |  | 0
M04 | Natural Resource Damages | Natural Resource Damages - Legal/Regulatory | 231600 | Legal/Regulatory-Closure Report/NFA | M04 | Execute/Build | LBR |  |  |  | 0
M04 | Natural Resource Damages | Natural Resource Damages - Legal/Regulatory | 232100 | Legal/Regulatory-Negotiations | M04 | Execute/Build | LBR |  |  |  | 0
M04 | Natural Resource Damages | Natural Resource Damages - Legal/Regulatory | 232140 | Legal/Regulatory-Trustee Negotiations | M04 | Execute/Build | LBR |  |  |  | 0
M04 | Natural Resource Damages | Natural Resource Damages - Public Records Request | 241000 | Public Records Request-General | M02 | General Administration | LBR |  |  |  | 0
M04 | Natural Resource Damages | Natural Resource Damages - Outreach | 251000 | Outreach-General | M02 | General Administration | LBR |  |  |  | 0
M04 | Natural Resource Damages | Natural Resource Damages - Outreach | 251010 | Outreach-Community Relations | M02 | General Administration | LBR |  |  |  | 0
M04 | Natural Resource Damages | Natural Resource Damages - Cost Recovery | 301000 | Cost Recovery-PRP Pursuit | M04 | Execute/Build | LBR |  |  |  | 0
M04 | Natural Resource Damages | Natural Resource Damages - Payments | 321000 | Payments-Group Payments | M04 | Execute/Build | LBR |  |  |  | 0
M04 | Natural Resource Damages | Natural Resource Damages - Payments | 321300 | Payments-Oversight Costs | M04 | Execute/Build | LBR |  |  |  | 0
M04 | Natural Resource Damages | Natural Resource Damages - Payments | 321310 | Payments-Oversight Costs-EPA | M04 | Execute/Build | LBR |  |  |  | 0
M04 | Natural Resource Damages | Natural Resource Damages - Payments | 321320 | Payments-Oversight Costs-DEQ | M04 | Execute/Build | LBR |  |  |  | 0
M04 | Natural Resource Damages | Natural Resource Damages - Payments | 321330 | Payments-Oversight Costs-Tribes | M04 | Execute/Build | LBR |  |  |  | 0
M04 | Natural Resource Damages | Natural Resource Damages - Payments | 321340 | Payments-Oversight Costs-Trustees | M04 | Execute/Build | LBR |  |  |  | 0
M04 | Natural Resource Damages | Natural Resource Damages - Contingency | 790000 | Contingency-Contingency | M02 | General Administration |  |  |  |  | 0
M04 | Natural Resource Damages | Natural Resource Damages - Capitalized Alloc Sup Svs | 909000 | Capitalized Alloc Sup Svs-Capitalized Allocated Supp Svs | M02 | General Administration |  |  |  |  | 0
M05 | LW Programmatic | LW Programmatic - Project Admin & Mgmt | 101000 | Project Admin & Mgmt-General | M02 | General Administration | LBR |  |  |  | 0
M05 | LW Programmatic | LW Programmatic - Project Admin & Mgmt | 101010 | Project Admin & Mgmt-Upland Source Cont. Program Co | M02 | General Administration | LBR |  |  |  | 0
M05 | LW Programmatic | LW Programmatic - Project Admin & Mgmt | 101020 | Project Admin & Mgmt-Program Management | M02 | General Administration | LBR |  |  |  | 0
M05 | LW Programmatic | LW Programmatic - Planning | 151200 | Planning-Site Investigation | M03 | Design | LBR |  |  |  | 0
M05 | LW Programmatic | LW Programmatic - Planning | 151240 | Planning-General Storm Water Pipes | M03 | Design | LBR |  |  |  | 0
M05 | LW Programmatic | LW Programmatic - Planning | 151900 | Planning-Technical Support | M03 | Design | LBR |  |  |  | 0
M05 | LW Programmatic | LW Programmatic - Public Records Request | 241000 | Public Records Request-General | M02 | General Administration | LBR |  |  |  | 0
M05 | LW Programmatic | LW Programmatic - Outreach | 251000 | Outreach-General | M02 | General Administration | LBR |  |  |  | 0
M05 | LW Programmatic | LW Programmatic - Records Management | 271000 | Records Management-General | M04 | Execute/Build | LBR |  |  |  | 0
M05 | LW Programmatic | LW Programmatic - Records Management | 271100 | Records Management-Coding/Scanning | M04 | Execute/Build | LBR |  |  |  | 0
M05 | LW Programmatic | LW Programmatic - Records Management | 271300 | Records Management-Hardware/Software | M04 | Execute/Build | LBR |  |  |  | 0
M05 | LW Programmatic | LW Programmatic - Cost Recovery | 301000 | Cost Recovery-PRP Pursuit | M04 | Execute/Build | LBR |  |  |  | 0
M05 | LW Programmatic | LW Programmatic - Cost Recovery | 301100 | Cost Recovery-Insurance Cost Recovery | M04 | Execute/Build | LBR |  |  |  | 0
M05 | LW Programmatic | LW Programmatic - Contingency | 790000 | Contingency-Contingency | M02 | General Administration |  |  |  |  | 0
M05 | LW Programmatic | LW Programmatic - Capitalized Alloc Sup Svs | 909000 | Capitalized Alloc Sup Svs-Capitalized Allocated Supp Svs | M02 | General Administration |  |  |  |  | 0
M06 | LW Project | LW Project - Project Admin & Mgmt | 101000 | Project Admin & Mgmt-General | M02 | General Administration | LBR |  |  |  | 0
M06 | LW Project | LW Project - Design | 141400 | Design-Remedial Design | M03 | Design | LBR |  |  |  | 0
M06 | LW Project | LW Project - Planning | 151100 | Planning-Assessment/Planning | M03 | Design | LBR |  |  |  | 0
M06 | LW Project | LW Project - Planning | 151120 | Planning-Strategy/Planning | M03 | Design | LBR |  |  |  | 0
M06 | LW Project | LW Project - Planning | 151300 | Planning-Remedial Investigation | M03 | Design | LBR |  |  |  | 0
M06 | LW Project | LW Project - Planning | 151600 | Planning-Feasibility Study | M03 | Design | LBR |  |  |  | 0
M06 | LW Project | LW Project - Implementation | 181000 | Implementation-Remedial Action | M04 | Execute/Build | LBR |  |  |  | 0
M06 | LW Project | LW Project - Permitting | 201000 | Permitting-General | M04 | Execute/Build | LBR |  |  |  | 0
M06 | LW Project | LW Project - Legal/Regulatory | 232000 | Legal/Regulatory-Compliance | M04 | Execute/Build | LBR |  |  |  | 0
M06 | LW Project | LW Project - Legal/Regulatory | 232010 | Legal/Regulatory-WRDA | M04 | Execute/Build | LBR |  |  |  | 0
M06 | LW Project | LW Project - Legal/Regulatory | 232100 | Legal/Regulatory-Negotiations | M04 | Execute/Build | LBR |  |  |  | 0
M06 | LW Project | LW Project - Legal/Regulatory | 232110 | Legal/Regulatory-AOC Negotiations | M04 | Execute/Build | LBR |  |  |  | 0
M06 | LW Project | LW Project - Public Records Request | 241000 | Public Records Request-General | M02 | General Administration | LBR |  |  |  | 0
M06 | LW Project | LW Project - Outreach | 251000 | Outreach-General | M02 | General Administration | LBR |  |  |  | 0
M06 | LW Project | LW Project - Cost Recovery | 301000 | Cost Recovery-PRP Pursuit | M04 | Execute/Build | LBR |  |  |  | 0
M06 | LW Project | LW Project - Payments | 321200 | Payments-LWG Group Payments | M04 | Execute/Build | LBR |  |  |  | 0
M06 | LW Project | LW Project - Payments | 321300 | Payments-Oversight Costs | M04 | Execute/Build | LBR |  |  |  | 0
M06 | LW Project | LW Project - Payments | 321310 | Payments-Oversight Costs-EPA | M04 | Execute/Build | LBR |  |  |  | 0
M06 | LW Project | LW Project - Payments | 321320 | Payments-Oversight Costs-DEQ | M04 | Execute/Build | LBR |  |  |  | 0
M06 | LW Project | LW Project - Payments | 321330 | Payments-Oversight Costs-Tribes | M04 | Execute/Build | LBR |  |  |  | 0
M06 | LW Project | LW Project - Payments | 321340 | Payments-Oversight Costs-Trustees | M04 | Execute/Build | LBR |  |  |  | 0
M06 | LW Project | LW Project - Contingency | 790000 | Contingency-Contingency | M02 | General Administration |  |  |  |  | 0
M06 | LW Project | LW Project - Capitalized Alloc Sup Svs | 909000 | Capitalized Alloc Sup Svs-Capitalized Allocated Supp Svs | M02 | General Administration |  |  |  |  | 0
M07 | Early Action Sites | Early Action Sites - Design | 142700 | Design-Maintenance Design Support | M03 | Design | LBR |  |  |  | 0
M07 | Early Action Sites | Early Action Sites - Planning | 151200 | Planning-Site Investigation | M03 | Design | LBR |  |  |  | 0
M07 | Early Action Sites | Early Action Sites - Planning | 151210 | Planning-EE(Site Characterization) | M03 | Design | LBR |  |  |  | 0
M07 | Early Action Sites | Early Action Sites - Development | 171510 | Development-Outside Design Services | M04 | Execute/Build |  |  |  |  | 0
M07 | Early Action Sites | Early Action Sites - Implementation | 181000 | Implementation-Remedial Action | M04 | Execute/Build | LBR |  |  |  | 0
M07 | Early Action Sites | Early Action Sites - Implementation | 181200 | Implementation-O&M-Monitoring | M04 | Execute/Build | LBR |  |  |  | 0
M07 | Early Action Sites | Early Action Sites - Implementation | 181300 | Implementation-Restoration | M04 | Execute/Build | LBR |  |  |  | 0
M07 | Early Action Sites | Early Action Sites - Implementation | 181310 | Implementation-NRD Restoration/Settlement | M04 | Execute/Build | LBR |  |  |  | 0
M07 | Early Action Sites | Early Action Sites - Construction | 191810 | Construction-Outside Construction Services | M04 | Execute/Build |  |  |  |  | 0
M07 | Early Action Sites | Early Action Sites - Legal/Regulatory | 231900 | Legal/Regulatory-Action Memo | M04 | Execute/Build | LBR |  |  |  | 0
M07 | Early Action Sites | Early Action Sites - Legal/Regulatory | 232100 | Legal/Regulatory-Negotiations | M04 | Execute/Build | LBR |  |  |  | 0
M07 | Early Action Sites | Early Action Sites - Legal/Regulatory | 232110 | Legal/Regulatory-AOC Negotiations | M04 | Execute/Build | LBR |  |  |  | 0
M07 | Early Action Sites | Early Action Sites - Legal/Regulatory | 232120 | Legal/Regulatory-CD/AO/UO Negotiations | M04 | Execute/Build | LBR |  |  |  | 0
M07 | Early Action Sites | Early Action Sites - Legal/Regulatory | 232130 | Legal/Regulatory-NRD Negotiations | M04 | Execute/Build | LBR |  |  |  | 0
M07 | Early Action Sites | Early Action Sites - Public Records Request | 241000 | Public Records Request-General | M02 | General Administration | LBR |  |  |  | 0
M07 | Early Action Sites | Early Action Sites - Outreach | 251000 | Outreach-General | M02 | General Administration | LBR |  |  |  | 0
M07 | Early Action Sites | Early Action Sites - Outreach | 251010 | Outreach-Community Relations | M02 | General Administration | LBR |  |  |  | 0
M07 | Early Action Sites | Early Action Sites - Cost Recovery | 301000 | Cost Recovery-PRP Pursuit | M04 | Execute/Build | LBR |  |  |  | 0
M07 | Early Action Sites | Early Action Sites - Payments | 321000 | Payments-Group Payments | M04 | Execute/Build | LBR |  |  |  | 0
M07 | Early Action Sites | Early Action Sites - Payments | 321200 | Payments-LWG Group Payments | M04 | Execute/Build | LBR |  |  |  | 0
M07 | Early Action Sites | Early Action Sites - Payments | 321300 | Payments-Oversight Costs | M04 | Execute/Build | LBR |  |  |  | 0
M07 | Early Action Sites | Early Action Sites - Payments | 321310 | Payments-Oversight Costs-EPA | M04 | Execute/Build | LBR |  |  |  | 0
M07 | Early Action Sites | Early Action Sites - Payments | 321320 | Payments-Oversight Costs-DEQ | M04 | Execute/Build | LBR |  |  |  | 0
M07 | Early Action Sites | Early Action Sites - Payments | 321330 | Payments-Oversight Costs-Tribes | M04 | Execute/Build | LBR |  |  |  | 0
M07 | Early Action Sites | Early Action Sites - Payments | 321340 | Payments-Oversight Costs-Trustees | M04 | Execute/Build | LBR |  |  |  | 0
M07 | Early Action Sites | Early Action Sites - Contingency | 790000 | Contingency-Contingency | M02 | General Administration |  |  |  |  | 0
M07 | Early Action Sites | Early Action Sites - Capitalized Alloc Sup Svs | 909000 | Capitalized Alloc Sup Svs-Capitalized Allocated Supp Svs | M02 | General Administration |  |  |  |  | 0
M08 | Navigation | Navigation - Dredge Production | 800010 | Dredge Production-Dredge Labor | M04 | Execute/Build | LBR |  |  |  | 0
M08 | Navigation | Navigation - Dredge Production | 800020 | Dredge Production-Dredge Survey | M04 | Execute/Build | LBR |  |  |  | 0
M08 | Navigation | Navigation - Dredge Production | 800030 | Dredge Production-Shore Labor | M04 | Execute/Build | LBR |  |  |  | 0
M08 | Navigation | Navigation - Dredge Production | 800040 | Dredge Production-Services | M04 | Execute/Build |  |  |  |  | 0
M08 | Navigation | Navigation - Dredge Production | 800050 | Dredge Production-Materials & Supplies | M04 | Execute/Build |  |  |  |  | 0
M08 | Navigation | Navigation - Dredge Production | 800060 | Dredge Production-Fuel, Lube, Oil | M04 | Execute/Build |  |  |  |  | 0
M08 | Navigation | Navigation - Dredge Production | 800070 | Dredge Production-Port Equipment Rented to Corps | M04 | Execute/Build |  |  |  |  | 0
M08 | Navigation | Navigation - Dredge Production | 800080 | Dredge Production-Out of Town | M04 | Execute/Build |  |  |  |  | 0
M08 | Navigation | Navigation - Major Maintenance | 810010 | Major Maintenance-Dredge Labor | M04 | Execute/Build | LBR |  |  |  | 0
M08 | Navigation | Navigation - Major Maintenance | 810020 | Major Maintenance-Dredge Survey | M04 | Execute/Build | LBR |  |  |  | 0
M08 | Navigation | Navigation - Major Maintenance | 810030 | Major Maintenance-Shore Labor | M04 | Execute/Build | LBR |  |  |  | 0
M08 | Navigation | Navigation - Major Maintenance | 810040 | Major Maintenance-Services | M04 | Execute/Build |  |  |  |  | 0
M08 | Navigation | Navigation - Major Maintenance | 810050 | Major Maintenance-Materials & Supplies | M04 | Execute/Build |  |  |  |  | 0
M08 | Navigation | Navigation - Major Maintenance | 810060 | Major Maintenance-Fuel, Lube, Oil | M04 | Execute/Build |  |  |  |  | 0
M08 | Navigation | Navigation - Major Maintenance | 810070 | Major Maintenance-Out of Town | M04 | Execute/Build |  |  |  |  | 0
M08 | Navigation | Navigation - Major Maintenance | 810080 | Major Maintenance-Port Equipment Rented to Corps | M04 | Execute/Build |  |  |  |  | 0
M08 | Navigation | Navigation - Mob/Demob | 820010 | Mob/Demob-Dredge Labor | M04 | Execute/Build | LBR |  |  |  | 0
M08 | Navigation | Navigation - Mob/Demob | 820020 | Mob/Demob-Dredge Survey | M04 | Execute/Build | LBR |  |  |  | 0
M08 | Navigation | Navigation - Mob/Demob | 820030 | Mob/Demob-Shore Labor | M04 | Execute/Build | LBR |  |  |  | 0
M08 | Navigation | Navigation - Mob/Demob | 820040 | Mob/Demob-Services | M04 | Execute/Build | LBR |  |  |  | 0
M08 | Navigation | Navigation - Mob/Demob | 820050 | Mob/Demob-Materials & Supplies | M04 | Execute/Build |  |  |  |  | 0
M08 | Navigation | Navigation - Mob/Demob | 820060 | Mob/Demob-Fuel, Lube, Oil | M04 | Execute/Build |  |  |  |  | 0
M08 | Navigation | Navigation - Mob/Demob | 820070 | Mob/Demob-Out of Town | M04 | Execute/Build |  |  |  |  | 0
M08 | Navigation | Navigation - Mob/Demob | 820080 | Mob/Demob-Port Equipment Rented to Corps | M04 | Execute/Build |  |  |  |  | 0
M08 | Navigation | Navigation - Standby | 830010 | Standby-Dredge Labor | M04 | Execute/Build | LBR |  |  |  | 0
M08 | Navigation | Navigation - Standby | 830020 | Standby-Dredge Survey | M04 | Execute/Build | LBR |  |  |  | 0
M08 | Navigation | Navigation - Standby | 830030 | Standby-Shore Labor | M04 | Execute/Build | LBR |  |  |  | 0
M08 | Navigation | Navigation - Standby | 830040 | Standby-Services | M04 | Execute/Build | LBR |  |  |  | 0
M08 | Navigation | Navigation - Standby | 830050 | Standby-Materials & Supplies | M04 | Execute/Build |  |  |  |  | 0
M08 | Navigation | Navigation - Standby | 830060 | Standby-Fuel, Lube, Oil | M04 | Execute/Build |  |  |  |  | 0
M08 | Navigation | Navigation - Standby | 830070 | Standby-Out of Town | M04 | Execute/Build |  |  |  |  | 0
M08 | Navigation | Navigation - Standby | 830080 | Standby-Port Equipment Rented to Corps | M04 | Execute/Build |  |  |  |  | 0
M08 | Navigation | Navigation - Standby Full Crew | 840010 | Standby Full Crew-Dredge Labor | M04 | Execute/Build | LBR |  |  |  | 0
M08 | Navigation | Navigation - Standby Full Crew | 840020 | Standby Full Crew-Dredge Survey | M04 | Execute/Build | LBR |  |  |  | 0
M08 | Navigation | Navigation - Standby Full Crew | 840030 | Standby Full Crew-Shore Labor | M04 | Execute/Build | LBR |  |  |  | 0
M08 | Navigation | Navigation - Standby Full Crew | 840040 | Standby Full Crew-Services | M04 | Execute/Build |  |  |  |  | 0
M08 | Navigation | Navigation - Standby Full Crew | 840050 | Standby Full Crew-Materials & Supplies | M04 | Execute/Build |  |  |  |  | 0
M08 | Navigation | Navigation - Standby Full Crew | 840060 | Standby Full Crew-Fuel, Lube, Oil | M04 | Execute/Build |  |  |  |  | 0
M08 | Navigation | Navigation - Standby Full Crew | 840070 | Standby Full Crew-Out of Town | M04 | Execute/Build |  |  |  |  | 0
M08 | Navigation | Navigation - Standby Full Crew | 840080 | Standby Full Crew-Port Equipment Rented to Corps | M04 | Execute/Build |  |  |  |  | 0
M08 | Navigation | Navigation - Nav Office Operations | 850010 | Nav Office Operations-Staff Labor | M04 | Execute/Build | LBR |  |  |  | 0
M08 | Navigation | Navigation - Nav Office Operations | 850020 | Nav Office Operations-Materials & Supplies | M04 | Execute/Build |  |  |  |  | 0
M08 | Navigation | Navigation - Nav Office Operations | 850030 | Nav Office Operations-Services | M04 | Execute/Build |  |  |  |  | 0
M08 | Navigation | Navigation - Nav Office Operations | 850040 | Nav Office Operations-Utilities | M04 | Execute/Build |  |  |  |  | 0
M08 | Navigation | Navigation - Nav Office Operations | 850050 | Nav Office Operations-Cost Offsets | M04 | Execute/Build |  |  |  |  | 0
M08 | Navigation | Navigation - Nav Office Operations | 850070 | Nav Office Operations-Out of Town | M04 | Execute/Build |  |  |  |  | 0
M08 | Navigation | Navigation - Nav Div Overhead | 860010 | Nav Div Overhead-Depreciation | M04 | Execute/Build |  |  |  |  | 0
M08 | Navigation | Navigation - Nav Div Overhead | 860020 | Nav Div Overhead-Property/Liability Claims | M04 | Execute/Build |  |  |  |  | 0
M08 | Navigation | Navigation - Nav Div Overhead | 860030 | Nav Div Overhead-Operating Engr Trust 701 Local | M04 | Execute/Build |  |  |  |  | 0
M08 | Navigation | Navigation - Nav Div Overhead | 860040 | Nav Div Overhead-Unemployment | M04 | Execute/Build |  |  |  |  | 0
M08 | Navigation | Navigation - Nav Div Overhead | 860050 | Nav Div Overhead-Workers Comp Fees/Claims | M04 | Execute/Build |  |  |  |  | 0
M08 | Navigation | Navigation - Nav Div Overhead | 860060 | Nav Div Overhead-Pensions | M04 | Execute/Build |  |  |  |  | 0
M08 | Navigation | Navigation - Nav Div Overhead | 860090 | Nav Div Overhead-Safety Incentive Program | M04 | Execute/Build | LBR |  |  |  | 0
M08 | Navigation | Navigation - Interdepartment Support | 870010 | Interdepartment Support-Engineering Support | M04 | Execute/Build | LBR |  |  |  | 0
M08 | Navigation | Navigation - Interdepartment Support | 870020 | Interdepartment Support-Projects Support | M04 | Execute/Build | LBR |  |  |  | 0
M08 | Navigation | Navigation - Interdepartment Support | 870030 | Interdepartment Support-Financial Support | M04 | Execute/Build | LBR |  |  |  | 0
M08 | Navigation | Navigation - Interdepartment Support | 870040 | Interdepartment Support-Marine Support | M04 | Execute/Build | LBR |  |  |  | 0
M08 | Navigation | Navigation - General & Admin (G&A) 15% | 880010 | General & Admin (G&A) 15%-Allocated Support Services | M04 | Execute/Build |  |  |  |  | 0
M08 | Navigation | Navigation - General & Admin (G&A) 15% | 880020 | General & Admin (G&A) 15%-Cost of Money Rate | M04 | Execute/Build |  |  |  |  | 0
M08 | Navigation | Navigation - Other Reimbursements | 901400 | Other Reimbursements-COE Dredge Operations | M04 | Execute/Build |  |  |  |  | 0
M09 | Equipment Standard | Equipment Standard - Project Admin & Mgmt | 101000 | Project Admin & Mgmt-General | M02 | General Administration | LBR |  |  |  | 0
M09 | Equipment Standard | Equipment Standard - Design | 141000 | Design-General | M03 | Design | LBR |  |  |  | 0
M09 | Equipment Standard | Equipment Standard - Design | 141010 | Design-Outside Design Services | M03 | Design |  |  |  |  | 0
M09 | Equipment Standard | Equipment Standard - Design | 141100 | Design-Specification Development | M03 | Design | LBR |  |  |  | 0
M09 | Equipment Standard | Equipment Standard - Acquisition | 162300 | Acquisition-Contract | M04 | Execute/Build | LBR |  |  |  | 0
M09 | Equipment Standard | Equipment Standard - Acquisition | 162400 | Acquisition-Procurement | M04 | Execute/Build | LBR |  |  |  | 0
M09 | Equipment Standard | Equipment Standard - Acquisition | 162500 | Acquisition-Delivery | M04 | Execute/Build | LBR |  |  |  | 0
M09 | Equipment Standard | Equipment Standard - Implementation | 181800 | Implementation-Equipment Installation | M04 | Execute/Build | LBR |  |  |  | 0
M09 | Equipment Standard | Equipment Standard - Construction | 191300 | Construction-Inspection | M04 | Execute/Build | LBR |  |  |  | 0
M09 | Equipment Standard | Equipment Standard - Contingency | 790000 | Contingency-Contingency | M02 | General Administration |  |  |  |  | 0
M09 | Equipment Standard | Equipment Standard - Capitalized Alloc Sup Svs | 908550 | Capitalized Alloc Sup Svs-Annual Engineering Adjustment | M02 | General Administration |  |  |  |  | 0
M09 | Equipment Standard | Equipment Standard - Capitalized Alloc Sup Svs | 909000 | Capitalized Alloc Sup Svs-Capitalized Allocated Supp Svs | M02 | General Administration |  |  |  |  | 0
M10 | Emergency | Emergency - Insurance/FEMA Tracking | 391000 | Insurance/FEMA Tracking-Preservation/Prevention | M04 | Execute/Build | LBR |  |  |  | 0
M10 | Emergency | Emergency - Insurance/FEMA Tracking | 391100 | Insurance/FEMA Tracking-Clean-Up (Removal of Debris) | M04 | Execute/Build | LBR |  |  |  | 0
M10 | Emergency | Emergency - Insurance/FEMA Tracking | 391200 | Insurance/FEMA Tracking-Damages (Cost To Repair Dam | M04 | Execute/Build | LBR |  |  |  | 0
M10 | Emergency | Emergency - Insurance/FEMA Tracking | 391300 | Insurance/FEMA Tracking-EOC 1. Extra Expense to Supp | M04 | Execute/Build | LBR |  |  |  | 0
M10 | Emergency | Emergency - Contingency | 790000 | Contingency-Contingency | M04 | Execute/Build |  |  |  |  | 0
M11 | Reimbursements | Reimbursements - Other Reimbursements | 901000 | Other Reimbursements-Environ. Remediation - PRP | M02 | General Administration |  |  |  |  | 0
M11 | Reimbursements | Reimbursements - Other Reimbursements | 901100 | Other Reimbursements-Insurance Reimbursements | M02 | General Administration |  |  |  |  | 0
M11 | Reimbursements | Reimbursements - Other Reimbursements | 901200 | Other Reimbursements-Third Party Shared Costs | M02 | General Administration |  |  |  |  | 0
M11 | Reimbursements | Reimbursements - Other Reimbursements | 901300 | Other Reimbursements-Business Development | M02 | General Administration |  |  |  |  | 0
M11 | Reimbursements | Reimbursements - Other Reimbursements | 901400 | Other Reimbursements-COE Dredge Operations | M02 | General Administration |  |  |  |  | 0
M11 | Reimbursements | Reimbursements - Other Reimbursements | 901500 | Other Reimbursements-TSA Agreements | M02 | General Administration |  |  |  |  | 0
M11 | Reimbursements | Reimbursements - Other Reimbursements | 901600 | Other Reimbursements-Business Energy Tax Credit | M02 | General Administration |  |  |  |  | 0
M11 | Reimbursements | Reimbursements - Other Reimbursements | 901700 | Other Reimbursements-SEP Program | M02 | General Administration |  |  |  |  | 0
M11 | Reimbursements | Reimbursements - Other Reimbursements | 901800 | Other Reimbursements-Intergovernmental Agreemen | M02 | General Administration |  |  |  |  | 0
M11 | Reimbursements | Reimbursements - Other Reimbursements | 901910 | Other Reimbursements-Port of Kalama Reimbursement | M02 | General Administration |  |  |  |  | 0
M11 | Reimbursements | Reimbursements - Other Reimbursements | 901920 | Other Reimbursements-Port of Longview Reimbursement | M02 | General Administration |  |  |  |  | 0
M11 | Reimbursements | Reimbursements - Other Reimbursements | 901930 | Other Reimbursements-Port of Vancouver Reimbursemen | M02 | General Administration |  |  |  |  | 0
M11 | Reimbursements | Reimbursements - Other Reimbursements | 901940 | Other Reimbursements-Port of Woodland Reimbursement | M02 | General Administration |  |  |  |  | 0
M11 | Reimbursements | Reimbursements - Other Reimbursements | 902000 | Other Reimbursements-Port of St. Helens Reimburseme | M02 | General Administration |  |  |  |  | 0
M11 | Reimbursements | Reimbursements - Other Reimbursements | 902100 | Other Reimbursements-State of Oregon Reimbursement | M02 | General Administration |  |  |  |  | 0
M11 | Reimbursements | Reimbursements - Other Reimbursements | 902200 | Other Reimbursements-OECDD - $27.7M | M02 | General Administration |  |  |  |  | 0
M11 | Reimbursements | Reimbursements - Other Reimbursements | 902300 | Other Reimbursements-ICTSI Estimated Reimbursement | M02 | General Administration |  |  |  |  | 0
M11 | Reimbursements | Reimbursements - Other Reimbursements | 902310 | Other Reimbursements-ICTSI Lease Reimbursements | M02 | General Administration |  |  |  |  | 0
M11 | Reimbursements | Reimbursements - Other Reimbursements | 902400 | Other Reimbursements-Equitable Sharing-Treasury Dep | M02 | General Administration |  |  |  |  | 0
M11 | Reimbursements | Reimbursements - Other Reimbursements | 902450 | Other Reimbursements-Equitable Sharing-Justice Dept | M02 | General Administration |  |  |  |  | 0
M12 | Channel Deepening | Channel Deepening - Project Admin & Mgmt | 101000 | Project Admin & Mgmt-General | M02 | General Administration | LBR |  |  |  | 0
M12 | Channel Deepening | Channel Deepening - Design | 141600 | Design-Environmental | M03 | Design | LBR |  |  |  | 0
M12 | Channel Deepening | Channel Deepening - Design | 141800 | Design-Survey | M03 | Design | LBR |  |  |  | 0
M12 | Channel Deepening | Channel Deepening - Design | 141900 | Design-Drawing and Development | M03 | Design | LBR |  |  |  | 0
M12 | Channel Deepening | Channel Deepening - Construction | 191000 | Construction-Contract | M04 | Execute/Build | LBR |  |  |  | 0
M12 | Channel Deepening | Channel Deepening - Construction | 191100 | Construction-Equipment Contracts | M04 | Execute/Build | LBR |  |  |  | 0
M12 | Channel Deepening | Channel Deepening - Construction | 191200 | Construction-Management | M04 | Execute/Build | LBR |  |  |  | 0
M12 | Channel Deepening | Channel Deepening - Construction | 191300 | Construction-Inspection | M04 | Execute/Build | LBR |  |  |  | 0
M12 | Channel Deepening | Channel Deepening - Construction | 191400 | Construction-Testing | M04 | Execute/Build | LBR |  |  |  | 0
M12 | Channel Deepening | Channel Deepening - Construction | 191600 | Construction-Environmental | M04 | Execute/Build | LBR |  |  |  | 0
M12 | Channel Deepening | Channel Deepening - Construction | 191800 | Construction-Engineering Support | M04 | Execute/Build | LBR |  |  |  | 0
M12 | Channel Deepening | Channel Deepening - Construction | 192200 | Construction-Tenant Access | M04 | Execute/Build | LBR |  |  |  | 0
M12 | Channel Deepening | Channel Deepening - Construction | 192300 | Construction-Operating Dept Support | M04 | Execute/Build | LBR |  |  |  | 0
M12 | Channel Deepening | Channel Deepening - Permitting | 201000 | Permitting-General | M04 | Execute/Build | LBR |  |  |  | 0
M12 | Channel Deepening | Channel Deepening - Survey | 211500 | Survey-Engineering Support | M04 | Execute/Build | LBR |  |  |  | 0
M12 | Channel Deepening | Channel Deepening - Maintenance | 221000 | Maintenance-Environmental | M04 | Execute/Build | LBR |  |  |  | 0
M12 | Channel Deepening | Channel Deepening - Maintenance | 221400 | Maintenance-Monitoring | M04 | Execute/Build | LBR |  |  |  | 0
M12 | Channel Deepening | Channel Deepening - Project Close Out | 781000 | Project Close Out-General | M05 | Close-out | LBR |  |  |  | 0
M12 | Channel Deepening | Channel Deepening - Contingency | 790000 | Contingency-Contingency | M02 | General Administration |  |  |  |  | 0
M12 | Channel Deepening | Channel Deepening - Dredge Production | 800010 | Dredge Production-Dredge Labor | M04 | Execute/Build | LBR |  |  |  | 0
M12 | Channel Deepening | Channel Deepening - Dredge Production | 800020 | Dredge Production-Dredge Survey | M04 | Execute/Build | LBR |  |  |  | 0
M12 | Channel Deepening | Channel Deepening - Dredge Production | 800030 | Dredge Production-Shore Labor | M04 | Execute/Build | LBR |  |  |  | 0
M12 | Channel Deepening | Channel Deepening - Dredge Production | 800040 | Dredge Production-Services | M04 | Execute/Build |  |  |  |  | 0
M12 | Channel Deepening | Channel Deepening - Dredge Production | 800050 | Dredge Production-Materials & Supplies | M04 | Execute/Build |  |  |  |  | 0
M12 | Channel Deepening | Channel Deepening - Dredge Production | 800060 | Dredge Production-Fuel, Lube, Oil | M04 | Execute/Build |  |  |  |  | 0
M12 | Channel Deepening | Channel Deepening - Dredge Production | 800070 | Dredge Production-Port Equipment Rented to Corps | M04 | Execute/Build |  |  |  |  | 0
M12 | Channel Deepening | Channel Deepening - Dredge Production | 800080 | Dredge Production-Out of Town | M04 | Execute/Build |  |  |  |  | 0
M12 | Channel Deepening | Channel Deepening - Major Maintenance | 810010 | Major Maintenance-Dredge Labor | M04 | Execute/Build | LBR |  |  |  | 0
M12 | Channel Deepening | Channel Deepening - Major Maintenance | 810020 | Major Maintenance-Dredge Survey | M04 | Execute/Build | LBR |  |  |  | 0
M12 | Channel Deepening | Channel Deepening - Major Maintenance | 810030 | Major Maintenance-Shore Labor | M04 | Execute/Build | LBR |  |  |  | 0
M12 | Channel Deepening | Channel Deepening - Major Maintenance | 810040 | Major Maintenance-Services | M04 | Execute/Build |  |  |  |  | 0
M12 | Channel Deepening | Channel Deepening - Major Maintenance | 810050 | Major Maintenance-Materials & Supplies | M04 | Execute/Build |  |  |  |  | 0
M12 | Channel Deepening | Channel Deepening - Major Maintenance | 810060 | Major Maintenance-Fuel, Lube, Oil | M04 | Execute/Build |  |  |  |  | 0
M12 | Channel Deepening | Channel Deepening - Major Maintenance | 810070 | Major Maintenance-Out of Town | M04 | Execute/Build |  |  |  |  | 0
M12 | Channel Deepening | Channel Deepening - Major Maintenance | 810080 | Major Maintenance-Port Equipment Rented to Corps | M04 | Execute/Build |  |  |  |  | 0
M12 | Channel Deepening | Channel Deepening - Mob/Demob | 820010 | Mob/Demob-Dredge Labor | M04 | Execute/Build | LBR |  |  |  | 0
M12 | Channel Deepening | Channel Deepening - Mob/Demob | 820020 | Mob/Demob-Dredge Survey | M04 | Execute/Build | LBR |  |  |  | 0
M12 | Channel Deepening | Channel Deepening - Mob/Demob | 820030 | Mob/Demob-Shore Labor | M04 | Execute/Build | LBR |  |  |  | 0
M12 | Channel Deepening | Channel Deepening - Mob/Demob | 820040 | Mob/Demob-Services | M04 | Execute/Build | LBR |  |  |  | 0
M12 | Channel Deepening | Channel Deepening - Mob/Demob | 820050 | Mob/Demob-Materials & Supplies | M04 | Execute/Build |  |  |  |  | 0
M12 | Channel Deepening | Channel Deepening - Mob/Demob | 820060 | Mob/Demob-Fuel, Lube, Oil | M04 | Execute/Build |  |  |  |  | 0
M12 | Channel Deepening | Channel Deepening - Mob/Demob | 820070 | Mob/Demob-Out of Town | M04 | Execute/Build |  |  |  |  | 0
M12 | Channel Deepening | Channel Deepening - Mob/Demob | 820080 | Mob/Demob-Port Equipment Rented to Corps | M04 | Execute/Build |  |  |  |  | 0
M12 | Channel Deepening | Channel Deepening - Standby | 830010 | Standby-Dredge Labor | M04 | Execute/Build | LBR |  |  |  | 0
M12 | Channel Deepening | Channel Deepening - Standby | 830020 | Standby-Dredge Survey | M04 | Execute/Build | LBR |  |  |  | 0
M12 | Channel Deepening | Channel Deepening - Standby | 830030 | Standby-Shore Labor | M04 | Execute/Build | LBR |  |  |  | 0
M12 | Channel Deepening | Channel Deepening - Standby | 830040 | Standby-Services | M04 | Execute/Build | LBR |  |  |  | 0
M12 | Channel Deepening | Channel Deepening - Standby | 830050 | Standby-Materials & Supplies | M04 | Execute/Build |  |  |  |  | 0
M12 | Channel Deepening | Channel Deepening - Standby | 830060 | Standby-Fuel, Lube, Oil | M04 | Execute/Build |  |  |  |  | 0
M12 | Channel Deepening | Channel Deepening - Standby | 830070 | Standby-Out of Town | M04 | Execute/Build |  |  |  |  | 0
M12 | Channel Deepening | Channel Deepening - Standby | 830080 | Standby-Port Equipment Rented to Corps | M04 | Execute/Build |  |  |  |  | 0
M12 | Channel Deepening | Channel Deepening - Standby Full Crew | 840010 | Standby Full Crew-Dredge Labor | M04 | Execute/Build | LBR |  |  |  | 0
M12 | Channel Deepening | Channel Deepening - Standby Full Crew | 840020 | Standby Full Crew-Dredge Survey | M04 | Execute/Build | LBR |  |  |  | 0
M12 | Channel Deepening | Channel Deepening - Standby Full Crew | 840030 | Standby Full Crew-Shore Labor | M04 | Execute/Build | LBR |  |  |  | 0
M12 | Channel Deepening | Channel Deepening - Standby Full Crew | 840040 | Standby Full Crew-Services | M04 | Execute/Build |  |  |  |  | 0
M12 | Channel Deepening | Channel Deepening - Standby Full Crew | 840050 | Standby Full Crew-Materials & Supplies | M04 | Execute/Build |  |  |  |  | 0
M12 | Channel Deepening | Channel Deepening - Standby Full Crew | 840060 | Standby Full Crew-Fuel, Lube, Oil | M04 | Execute/Build |  |  |  |  | 0
M12 | Channel Deepening | Channel Deepening - Standby Full Crew | 840070 | Standby Full Crew-Out of Town | M04 | Execute/Build |  |  |  |  | 0
M12 | Channel Deepening | Channel Deepening - Standby Full Crew | 840080 | Standby Full Crew-Port Equipment Rented to Corps | M04 | Execute/Build |  |  |  |  | 0
M12 | Channel Deepening | Channel Deepening - Nav Office Operations | 850010 | Nav Office Operations-Staff Labor | M04 | Execute/Build | LBR |  |  |  | 0
M12 | Channel Deepening | Channel Deepening - Nav Office Operations | 850020 | Nav Office Operations-Materials & Supplies | M04 | Execute/Build |  |  |  |  | 0
M12 | Channel Deepening | Channel Deepening - Nav Office Operations | 850030 | Nav Office Operations-Services | M04 | Execute/Build |  |  |  |  | 0
M12 | Channel Deepening | Channel Deepening - Nav Office Operations | 850040 | Nav Office Operations-Utilities | M04 | Execute/Build |  |  |  |  | 0
M12 | Channel Deepening | Channel Deepening - Nav Office Operations | 850050 | Nav Office Operations-Cost Offsets | M04 | Execute/Build |  |  |  |  | 0
M12 | Channel Deepening | Channel Deepening - Nav Office Operations | 850070 | Nav Office Operations-Out of Town | M04 | Execute/Build |  |  |  |  | 0
M12 | Channel Deepening | Channel Deepening - Nav Div Overhead | 860010 | Nav Div Overhead-Depreciation | M04 | Execute/Build |  |  |  |  | 0
M12 | Channel Deepening | Channel Deepening - Nav Div Overhead | 860020 | Nav Div Overhead-Property/Liability Claims | M04 | Execute/Build |  |  |  |  | 0
M12 | Channel Deepening | Channel Deepening - Nav Div Overhead | 860030 | Nav Div Overhead-Operating Engr Trust 701 Local | M04 | Execute/Build |  |  |  |  | 0
M12 | Channel Deepening | Channel Deepening - Nav Div Overhead | 860040 | Nav Div Overhead-Unemployment | M04 | Execute/Build |  |  |  |  | 0
M12 | Channel Deepening | Channel Deepening - Nav Div Overhead | 860050 | Nav Div Overhead-Workers Comp Fees/Claims | M04 | Execute/Build |  |  |  |  | 0
M12 | Channel Deepening | Channel Deepening - Nav Div Overhead | 860060 | Nav Div Overhead-Pensions | M04 | Execute/Build |  |  |  |  | 0
M12 | Channel Deepening | Channel Deepening - Nav Div Overhead | 860090 | Nav Div Overhead-Safety Incentive Program | M04 | Execute/Build | LBR |  |  |  | 0
M12 | Channel Deepening | Channel Deepening - Interdepartment Support | 870010 | Interdepartment Support-Engineering Support | M04 | Execute/Build | LBR |  |  |  | 0
M12 | Channel Deepening | Channel Deepening - Interdepartment Support | 870020 | Interdepartment Support-Projects Support | M04 | Execute/Build | LBR |  |  |  | 0
M12 | Channel Deepening | Channel Deepening - Interdepartment Support | 870030 | Interdepartment Support-Financial Support | M04 | Execute/Build | LBR |  |  |  | 0
M12 | Channel Deepening | Channel Deepening - Interdepartment Support | 870040 | Interdepartment Support-Marine Support | M04 | Execute/Build | LBR |  |  |  | 0
M12 | Channel Deepening | Channel Deepening - General & Admin (G&A) 15% | 880010 | General & Admin (G&A) 15%-Allocated Support Services | M04 | Execute/Build |  |  |  |  | 0
M12 | Channel Deepening | Channel Deepening - General & Admin (G&A) 15% | 880020 | General & Admin (G&A) 15%-Cost of Money Rate | M04 | Execute/Build |  |  |  |  | 0
M12 | Channel Deepening | Channel Deepening - Other Reimbursements | 901910 | Other Reimbursements-Port of Kalama Reimbursement | M02 | General Administration |  |  |  |  | 0
M12 | Channel Deepening | Channel Deepening - Other Reimbursements | 901920 | Other Reimbursements-Port of Longview Reimbursement | M02 | General Administration |  |  |  |  | 0
M12 | Channel Deepening | Channel Deepening - Other Reimbursements | 901930 | Other Reimbursements-Port of Vancouver Reimbursemen | M02 | General Administration |  |  |  |  | 0
M12 | Channel Deepening | Channel Deepening - Other Reimbursements | 901940 | Other Reimbursements-Port of Woodland Reimbursement | M02 | General Administration |  |  |  |  | 0
M12 | Channel Deepening | Channel Deepening - Other Reimbursements | 902000 | Other Reimbursements-Port of St. Helens Reimburseme | M02 | General Administration |  |  |  |  | 0
M12 | Channel Deepening | Channel Deepening - Other Reimbursements | 902100 | Other Reimbursements-State of Oregon Reimbursement | M02 | General Administration |  |  |  |  | 0
M12 | Channel Deepening | Channel Deepening - Other Reimbursements | 902200 | Other Reimbursements-OECDD - $27.7M | M02 | General Administration |  |  |  |  | 0
M13 | Properties | Properties - Acquisition | 161000 | Acquisition-General | M04 | Execute/Build | LBR |  |  |  | 0
M13 | Properties | Properties - Acquisition | 161110 | Acquisition-Payments to WA Ports | M04 | Execute/Build |  |  |  |  | 0
M13 | Properties | Properties - Acquisition | 161200 | Acquisition-Demolition | M04 | Execute/Build | LBR |  |  |  | 0
M13 | Properties | Properties - Acquisition | 161300 | Acquisition-Relocation Assistance | M04 | Execute/Build | LBR |  |  |  | 0
M13 | Properties | Properties - Acquisition | 161400 | Acquisition-Appraisals | M04 | Execute/Build | LBR |  |  |  | 0
M13 | Properties | Properties - Acquisition | 161500 | Acquisition-Environmental Assessments | M04 | Execute/Build | LBR |  |  |  | 0
M13 | Properties | Properties - Acquisition | 161700 | Acquisition-Inspection | M04 | Execute/Build | LBR |  |  |  | 0
M13 | Properties | Properties - Acquisition | 162200 | Acquisition-Survey | M04 | Execute/Build | LBR |  |  |  | 0
M13 | Properties | Properties - Development | 171510 | Development-Outside Design Services | M04 | Execute/Build |  |  |  |  | 0
M13 | Properties | Properties - Implementation | 181000 | Implementation-Remedial Action | M04 | Execute/Build | LBR |  |  |  | 0
M13 | Properties | Properties - Implementation | 181100 | Implementation-O&M-Systems | M04 | Execute/Build | LBR |  |  |  | 0
M13 | Properties | Properties - Implementation | 181200 | Implementation-O&M-Monitoring | M04 | Execute/Build | LBR |  |  |  | 0
M13 | Properties | Properties - Implementation | 181300 | Implementation-Restoration | M04 | Execute/Build | LBR |  |  |  | 0
M13 | Properties | Properties - Implementation | 181310 | Implementation-NRD Restoration/Settlement | M04 | Execute/Build | LBR |  |  |  | 0
M13 | Properties | Properties - Implementation | 181320 | Implementation-Restoration Implementation | M04 | Execute/Build | LBR |  |  |  | 0
M13 | Properties | Properties - Maintenance | 221400 | Maintenance-Monitoring | M04 | Execute/Build | LBR |  |  |  | 0
M13 | Properties | Properties - Maintenance | 221500 | Maintenance-General | M04 | Execute/Build | LBR |  |  |  | 0
M13 | Properties | Properties - Cost Recovery | 301000 | Cost Recovery-PRP Pursuit | M04 | Execute/Build | LBR |  |  |  | 0
M13 | Properties | Properties - Cost Recovery | 301100 | Cost Recovery-Insurance Cost Recovery | M04 | Execute/Build | LBR |  |  |  | 0
M13 | Properties | Properties - Project Close Out | 781000 | Project Close Out-General | M05 | Close-out | LBR |  |  |  | 0
M13 | Properties | Properties - Contingency | 790000 | Contingency-Contingency | M02 | General Administration |  |  |  |  | 0
M13 | Properties | Properties - Capitalized Alloc Sup Svs | 908550 | Capitalized Alloc Sup Svs-Annual Engineering Adjustment | M02 | General Administration |  |  |  |  | 0
M13 | Properties | Properties - Capitalized Alloc Sup Svs | 909000 | Capitalized Alloc Sup Svs-Capitalized Allocated Supp Svs | M02 | General Administration |  |  |  |  | 0
M14 | Master Planning | Master Planning - Project Admin & Mgmt | 101000 | Project Admin & Mgmt-General | M02 | General Administration | LBR |  |  |  | 0
M14 | Master Planning | Master Planning - Project Admin & Mgmt | 101200 | Project Admin & Mgmt-Project Mgmt | M02 | General Administration | LBR |  |  |  | 0
M14 | Master Planning | Master Planning - Planning | 151000 | Planning-General | M03 | Design | LBR |  |  |  | 0
M14 | Master Planning | Master Planning - Planning | 151100 | Planning-Assessment/Planning | M03 | Design | LBR |  |  |  | 0
M14 | Master Planning | Master Planning - Planning | 151400 | Planning-Forecasts | M03 | Design | LBR |  |  |  | 0
M14 | Master Planning | Master Planning - Planning | 151500 | Planning-Alternatives Definition | M03 | Design | LBR |  |  |  | 0
M14 | Master Planning | Master Planning - Survey | 211200 | Survey-Analysis | M04 | Execute/Build | LBR |  |  |  | 0
M14 | Master Planning | Master Planning - Outreach | 251000 | Outreach-General | M02 | General Administration | LBR |  |  |  | 0
M14 | Master Planning | Master Planning - Project Close Out | 781000 | Project Close Out-General | M05 | Close-out | LBR |  |  |  | 0
M14 | Master Planning | Master Planning - Contingency | 790000 | Contingency-Contingency | M02 | General Administration |  |  |  |  | 0
M14 | Master Planning | Master Planning - Capitalized Alloc Sup Svs | 909000 | Capitalized Alloc Sup Svs-Capitalized Allocated Supp Svs | M02 | General Administration |  | 63 |  |  | 0
M15 | Business Case Planning | Business Case Planning - Project Admin & Mgmt | 101000 | Project Admin & Mgmt-General | M02 | General Administration | LBR |  |  |  | 0
M15 | Business Case Planning | Business Case Planning - Analysis & Requirements Defin. | 121000 | Analysis & Requirements Defin.-General | M01 | Project Planning | LBR |  |  |  | 0
M15 | Business Case Planning | Business Case Planning - Design | 141000 | Design-General | M03 | Design | LBR |  |  |  | 0
M15 | Business Case Planning | Business Case Planning - Construction | 191000 | Construction-Contract | M04 | Execute/Build | LBR |  |  |  | 0
M15 | Business Case Planning | Business Case Planning - Project Close Out | 781000 | Project Close Out-General | M05 | Close-out | LBR |  |  |  | 0
M15 | Business Case Planning | Business Case Planning - Contingency | 790000 | Contingency-Contingency | M02 | General Administration |  |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Project Admin & Mgmt | 101000 | Project Admin & Mgmt-General | M05 | Close-out | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Project Admin & Mgmt | 101010 | Project Admin & Mgmt-Upland Source Cont. Program Co | M05 | Close-out | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Project Admin & Mgmt | 101020 | Project Admin & Mgmt-Program Management | M05 | Close-out | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Project Admin & Mgmt | 101100 | Project Admin & Mgmt-Meetings | M05 | Close-out | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Project Admin & Mgmt | 101200 | Project Admin & Mgmt-Project Mgmt | M05 | Close-out | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Project Admin & Mgmt | 101300 | Project Admin & Mgmt-Development | M05 | Close-out | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Project Admin & Mgmt | 101400 | Project Admin & Mgmt-Design | M05 | Close-out | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Project Admin & Mgmt | 101500 | Project Admin & Mgmt-Construction | M05 | Close-out | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Project Admin & Mgmt | 101600 | Project Admin & Mgmt-Land Acquisition | M05 | Close-out | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Project Admin & Mgmt | 101700 | Project Admin & Mgmt-Financial Support | M05 | Close-out | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Analysis & Requirements Defin. | 121000 | Analysis & Requirements Defin.-General | M01 | Project Planning | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Analysis & Requirements Defin. | 121100 | Analysis & Requirements Defin.-Develop & Issue RFP | M01 | Project Planning | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Analysis & Requirements Defin. | 121200 | Analysis & Requirements Defin.-Select Vendor | M01 | Project Planning | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Security | 131000 | Security-General | M05 | Close-out | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Design | 141000 | Design-General | M03 | Design | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Design | 141010 | Design-Outside Design Services | M03 | Design |  |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Design | 141100 | Design-Specification Development | M03 | Design | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Design | 141200 | Design-R&D | M03 | Design | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Design | 141400 | Design-Remedial Design | M03 | Design | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Design | 141500 | Design-Restoration | M03 | Design | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Design | 141510 | Design-Restore. Plan & Dev, incl. Des | M03 | Design | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Design | 141600 | Design-Environmental | M03 | Design | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Design | 141700 | Design-PE Design | M03 | Design | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Design | 141800 | Design-Survey | M03 | Design | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Design | 141900 | Design-Drawing and Development | M03 | Design | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Design | 142000 | Design-Public Affairs | M03 | Design | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Design | 142100 | Design-Construction/Inspection Suppor | M03 | Design | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Design | 142600 | Design-IT Design Support | M03 | Design | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Design | 142700 | Design-Maintenance Design Support | M03 | Design | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Design | 142900 | Design-Identity Development | M03 | Design | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Planning | 151000 | Planning-General | M03 | Design | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Planning | 151100 | Planning-Assessment/Planning | M03 | Design | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Planning | 151110 | Planning-Preliminary Assessment | M03 | Design | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Planning | 151120 | Planning-Strategy/Planning | M03 | Design | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Planning | 151130 | Planning-Injury Assessment | M03 | Design | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Planning | 151140 | Planning-Capacity Analysis | M03 | Design | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Planning | 151150 | Planning-Environ. Assess/Action Plan | M03 | Design | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Planning | 151200 | Planning-Site Investigation | M03 | Design | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Planning | 151210 | Planning-EE(Site Characterization) | M03 | Design | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Planning | 151240 | Planning-General Storm Water Pipes | M03 | Design | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Planning | 151300 | Planning-Remedial Investigation | M03 | Design | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Planning | 151310 | Planning-Cargill OU1 | M03 | Design | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Planning | 151320 | Planning-OU2 | M03 | Design | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Planning | 151400 | Planning-Forecasts | M03 | Design | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Planning | 151410 | Planning-Cargo | M03 | Design | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Planning | 151420 | Planning-Future Technology | M03 | Design | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Planning | 151500 | Planning-Alternatives Definition | M03 | Design | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Planning | 151510 | Planning-Facility | M03 | Design | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Planning | 151520 | Planning-Master Plan | M03 | Design | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Planning | 151530 | Planning-Transportation Improvement | M03 | Design | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Planning | 151600 | Planning-Feasibility Study | M03 | Design | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Planning | 151800 | Planning-Transportation Analysis | M03 | Design | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Planning | 151900 | Planning-Technical Support | M03 | Design | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Planning | 152200 | Planning-Event | M03 | Design | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Planning | 152500 | Planning-Multimedia Presentations | M03 | Design | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Acquisition | 161000 | Acquisition-General | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Acquisition | 161110 | Acquisition-Payments to WA Ports | M04 | Execute/Build |  |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Acquisition | 161200 | Acquisition-Demolition | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Acquisition | 161300 | Acquisition-Relocation Assistance | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Acquisition | 161400 | Acquisition-Appraisals | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Acquisition | 161500 | Acquisition-Environmental Assessments | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Acquisition | 161700 | Acquisition-Inspection | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Acquisition | 162200 | Acquisition-Survey | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Acquisition | 162300 | Acquisition-Contract | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Acquisition | 162400 | Acquisition-Procurement | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Acquisition | 162500 | Acquisition-Delivery | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Development | 171000 | Development-Database Administration | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Development | 171100 | Development-Software Develop. & Config. | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Development | 171200 | Development-Integration Development | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Development | 171300 | Development-Interface Development | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Development | 171400 | Development-Conversion Development | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Development | 171500 | Development-Conceptual Design | M03 | Design | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Development | 171510 | Development-Outside Design Services | M04 | Execute/Build |  |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Development | 171600 | Development-PE Design/Support | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Development | 171700 | Development-Survey | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Development | 171800 | Development-Contracts/Drawing | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Development | 171900 | Development-Environmental | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Development | 171910 | Development-Action Plan | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Development | 172100 | Development-Planning | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Development | 172200 | Development-Maintenance | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Development | 172300 | Development-IT | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Development | 172400 | Development-Construction/Inspection Suppor | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Implementation | 181000 | Implementation-Remedial Action | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Implementation | 181100 | Implementation-O&M-Systems | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Implementation | 181200 | Implementation-O&M-Monitoring | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Implementation | 181300 | Implementation-Restoration | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Implementation | 181310 | Implementation-NRD Restoration/Settlement | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Implementation | 181320 | Implementation-Restoration Implementation | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Implementation | 181400 | Implementation-Hardware Installation | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Implementation | 181500 | Implementation-Database Installation | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Implementation | 181600 | Implementation-Software Installation | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Implementation | 181700 | Implementation-IT Conversion | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Implementation | 181800 | Implementation-Equipment Installation | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Construction | 191000 | Construction-Contract | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Construction | 191100 | Construction-Equipment Contracts | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Construction | 191200 | Construction-Management | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Construction | 191300 | Construction-Inspection | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Construction | 191400 | Construction-Testing | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Construction | 191500 | Construction-Survey | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Construction | 191600 | Construction-Environmental | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Construction | 191700 | Construction-Public Affairs | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Construction | 191800 | Construction-Engineering Support | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Construction | 191810 | Construction-Outside Construction Services | M04 | Execute/Build |  |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Construction | 191900 | Construction-Maintenance | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Construction | 192000 | Construction-IT | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Construction | 192200 | Construction-Tenant Access | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Construction | 192300 | Construction-Operating Dept Support | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Construction | 192510 | Construction-Premium-Workers' Compensation | M04 | Execute/Build |  |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Construction | 192520 | Construction-Premium-General Liability | M04 | Execute/Build |  |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Construction | 192530 | Construction-Premium-Excess Liability | M04 | Execute/Build |  |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Construction | 192540 | Construction-Premium-Contractors' Poll Liab | M04 | Execute/Build |  |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Construction | 192550 | Construction-Premium-Builders' Risk | M04 | Execute/Build |  |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Construction | 192560 | Construction-Premium-Broker/Admin Fee | M04 | Execute/Build |  |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Construction | 192600 | Construction-Insurance Claims | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Construction | 192610 | Construction-Claims-Workers' Compensation | M04 | Execute/Build |  |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Construction | 192620 | Construction-Claims-General Liability | M04 | Execute/Build |  |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Construction | 192630 | Construction-Claims-Excess Liability | M04 | Execute/Build |  |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Construction | 192640 | Construction-Claims-Contractors' Poll Liab | M04 | Execute/Build |  |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Construction | 192650 | Construction-Claims-Builders' Risk | M04 | Execute/Build |  |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Construction | 192710 | Construction-Workers' Compensation | M04 | Execute/Build |  |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Permitting | 201000 | Permitting-General | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Permitting | 201100 | Permitting-Corps | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Permitting | 201200 | Permitting-Federal | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Permitting | 201300 | Permitting-State | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Permitting | 201400 | Permitting-City | M02 | General Administration | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Survey | 211200 | Survey-Analysis | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Survey | 211210 | Survey-Transportation Condition | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Survey | 211220 | Survey-Environmental Condition | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Survey | 211230 | Survey-Facility Condition | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Survey | 211240 | Survey-Update Harbor History | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Survey | 211500 | Survey-Engineering Support | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Maintenance | 221000 | Maintenance-Environmental | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Maintenance | 221400 | Maintenance-Monitoring | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Maintenance | 221500 | Maintenance-General | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Legal/Regulatory | 231000 | Legal/Regulatory-Design | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Legal/Regulatory | 231300 | Legal/Regulatory-Pre-Litigation Preparation | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Legal/Regulatory | 231400 | Legal/Regulatory-Litigation Defense | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Legal/Regulatory | 231500 | Legal/Regulatory-Litigate | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Legal/Regulatory | 231600 | Legal/Regulatory-Closure Report/NFA | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Legal/Regulatory | 231900 | Legal/Regulatory-Action Memo | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Legal/Regulatory | 232000 | Legal/Regulatory-Compliance | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Legal/Regulatory | 232010 | Legal/Regulatory-WRDA | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Legal/Regulatory | 232015 | Legal/Regulatory-WRDA-Internal Cost Tracking | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Legal/Regulatory | 232100 | Legal/Regulatory-Negotiations | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Legal/Regulatory | 232110 | Legal/Regulatory-AOC Negotiations | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Legal/Regulatory | 232120 | Legal/Regulatory-CD/AO/UO Negotiations | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Legal/Regulatory | 232130 | Legal/Regulatory-NRD Negotiations | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Legal/Regulatory | 232140 | Legal/Regulatory-Trustee Negotiations | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Legal/Regulatory | 232300 | Legal/Regulatory-Identity Development | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Legal/Regulatory | 232400 | Legal/Regulatory-Print Media | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Public Records Request | 241000 | Public Records Request-General | M05 | Close-out | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Outreach | 251000 | Outreach-General | M05 | Close-out | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Outreach | 251010 | Outreach-Community Relations | M05 | Close-out | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Documentation | 261000 | Documentation-Technical Documentation | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Documentation | 261400 | Documentation-Training Materials | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Records Management | 271000 | Records Management-General | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Records Management | 271100 | Records Management-Coding/Scanning | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Records Management | 271300 | Records Management-Hardware/Software | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Testing | 281000 | Testing-General | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Training | 291000 | Training-Core User Training | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Training | 291100 | Training-End User Training | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Training | 291200 | Training-Support Team Training | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Training | 291500 | Training-Event | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Cost Recovery | 301000 | Cost Recovery-PRP Pursuit | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Cost Recovery | 301050 | Cost Recovery-PRP Search | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Cost Recovery | 301100 | Cost Recovery-Insurance Cost Recovery | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Operations | 311000 | Operations-Level Green/Yellow | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Operations | 311100 | Operations-Level Orange | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Operations | 311300 | Operations-Kenneling & Care | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Operations | 311500 | Operations-Veterinary Care | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Operations | 311700 | Operations-Misc K9 Costs | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Prop Mgmt Revenues | 311910 | Prop Mgmt Revenues-Taxes | M04 | Execute/Build |  |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Prop Mgmt Revenues | 311920 | Prop Mgmt Revenues-Lease Rental Income | M04 | Execute/Build |  |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Prop Mgmt Revenues | 311930 | Prop Mgmt Revenues-Sand Sales Income | M04 | Execute/Build |  |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Prop Mgmt Expenses | 312010 | Prop Mgmt Expenses-General | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Sand Sales Expenses | 312021 | Sand Sales Expenses-Management | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Sand Sales Expenses | 312022 | Sand Sales Expenses-Royalty Payments to DSL | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Payments | 321000 | Payments-Group Payments | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Payments | 321200 | Payments-LWG Group Payments | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Payments | 321300 | Payments-Oversight Costs | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Payments | 321310 | Payments-Oversight Costs-EPA | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Payments | 321320 | Payments-Oversight Costs-DEQ | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Payments | 321330 | Payments-Oversight Costs-Tribes | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Payments | 321340 | Payments-Oversight Costs-Trustees | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Payments | 321350 | Payments-EPA Investigation | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Payments | 321360 | Payments-EPA Cleanup | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Payments | 321370 | Payments-DEQ Investigation | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Payments | 321380 | Payments-EPA Cleanup | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Identity Development | 331000 | Identity Development-Print | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Identity Development | 331100 | Identity Development-Copy Writing | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Print Media | 341000 | Print Media-Print | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Event | 351500 | Event-Special Promotion | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Multimedia Presentations | 381300 | Multimedia Presentations-Advertising | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Insurance/FEMA Tracking | 391000 | Insurance/FEMA Tracking-Preservation/Prevention | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Insurance/FEMA Tracking | 391100 | Insurance/FEMA Tracking-Clean-Up (Removal of Debris) | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Insurance/FEMA Tracking | 391200 | Insurance/FEMA Tracking-Damages (Cost To Repair Dam | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Insurance/FEMA Tracking | 391300 | Insurance/FEMA Tracking-EOC 1. Extra Expense to Supp | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - ICTSI Reimbursable | 600110 | ICTSI Reimbursable-Cranes | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - ICTSI Reimbursable | 600120 | ICTSI Reimbursable-Gate | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - ICTSI Reimbursable | 600130 | ICTSI Reimbursable-Container Yard (604-606) | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - ICTSI Reimbursable | 600140 | ICTSI Reimbursable-Breakbulk Yard (603) | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - ICTSI Reimbursable | 600150 | ICTSI Reimbursable-Berths 603-605 Dock | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - ICTSI Reimbursable | 600160 | ICTSI Reimbursable-Intermodal Rail Yard | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - ICTSI Reimbursable | 600170 | ICTSI Reimbursable-Maintenance/Administrative | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - ICTSI Reimbursable | 600230 | ICTSI Reimbursable-Security Allocation | M04 | Execute/Build |  |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - ICTSI Reimbursable | 600240 | ICTSI Reimbursable-MFM Allocation | M04 | Execute/Build |  |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - ICTSI Reimbursable | 600250 | ICTSI Reimbursable-Electrical Allocation | M04 | Execute/Build |  |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - ICTSI Reimbursable | 600260 | ICTSI Reimbursable-Gearlocker Allocation | M04 | Execute/Build |  |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - ICTSI Reimbursable | 600270 | ICTSI Reimbursable-Corporate Overhead | M04 | Execute/Build |  |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - ICTSI Reimbursable | 600280 | ICTSI Reimbursable-Marine Overhead | M04 | Execute/Build |  |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Project Close Out | 781000 | Project Close Out-General | M05 | Close-out | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Project Close Out | 781100 | Project Close Out-As Builts | M05 | Close-out | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Project Close Out | 781200 | Project Close Out-Survey | M05 | Close-out | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Project Close Out | 781300 | Project Close Out-Technical Reference Center | M05 | Close-out | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Project Close Out | 781400 | Project Close Out-Geographic Information System | M05 | Close-out | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Contingency | 790000 | Contingency-Contingency | M02 | General Administration |  |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Dredge Production | 800010 | Dredge Production-Dredge Labor | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Dredge Production | 800020 | Dredge Production-Dredge Survey | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Dredge Production | 800030 | Dredge Production-Shore Labor | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Dredge Production | 800040 | Dredge Production-Services | M04 | Execute/Build |  |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Dredge Production | 800050 | Dredge Production-Materials & Supplies | M04 | Execute/Build |  |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Dredge Production | 800060 | Dredge Production-Fuel, Lube, Oil | M04 | Execute/Build |  |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Dredge Production | 800070 | Dredge Production-Port Equipment Rented to Corps | M04 | Execute/Build |  |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Dredge Production | 800080 | Dredge Production-Out of Town | M04 | Execute/Build |  |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Major Maintenance | 810010 | Major Maintenance-Dredge Labor | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Major Maintenance | 810020 | Major Maintenance-Dredge Survey | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Major Maintenance | 810030 | Major Maintenance-Shore Labor | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Major Maintenance | 810040 | Major Maintenance-Services | M04 | Execute/Build |  |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Major Maintenance | 810050 | Major Maintenance-Materials & Supplies | M04 | Execute/Build |  |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Major Maintenance | 810060 | Major Maintenance-Fuel, Lube, Oil | M04 | Execute/Build |  |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Major Maintenance | 810070 | Major Maintenance-Out of Town | M04 | Execute/Build |  |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Major Maintenance | 810080 | Major Maintenance-Port Equipment Rented to Corps | M04 | Execute/Build |  |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Mob/Demob | 820010 | Mob/Demob-Dredge Labor | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Mob/Demob | 820020 | Mob/Demob-Dredge Survey | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Mob/Demob | 820030 | Mob/Demob-Shore Labor | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Mob/Demob | 820040 | Mob/Demob-Services | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Mob/Demob | 820050 | Mob/Demob-Materials & Supplies | M04 | Execute/Build |  |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Mob/Demob | 820060 | Mob/Demob-Fuel, Lube, Oil | M04 | Execute/Build |  |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Mob/Demob | 820070 | Mob/Demob-Out of Town | M04 | Execute/Build |  |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Mob/Demob | 820080 | Mob/Demob-Port Equipment Rented to Corps | M04 | Execute/Build |  |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Standby | 830010 | Standby-Dredge Labor | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Standby | 830020 | Standby-Dredge Survey | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Standby | 830030 | Standby-Shore Labor | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Standby | 830040 | Standby-Services | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Standby | 830050 | Standby-Materials & Supplies | M04 | Execute/Build |  |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Standby | 830060 | Standby-Fuel, Lube, Oil | M04 | Execute/Build |  |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Standby | 830070 | Standby-Out of Town | M04 | Execute/Build |  |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Standby | 830080 | Standby-Port Equipment Rented to Corps | M04 | Execute/Build |  |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Standby Full Crew | 840010 | Standby Full Crew-Dredge Labor | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Standby Full Crew | 840020 | Standby Full Crew-Dredge Survey | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Standby Full Crew | 840030 | Standby Full Crew-Shore Labor | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Standby Full Crew | 840040 | Standby Full Crew-Services | M04 | Execute/Build |  |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Standby Full Crew | 840050 | Standby Full Crew-Materials & Supplies | M04 | Execute/Build |  |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Standby Full Crew | 840060 | Standby Full Crew-Fuel, Lube, Oil | M04 | Execute/Build |  |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Standby Full Crew | 840070 | Standby Full Crew-Out of Town | M04 | Execute/Build |  |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Standby Full Crew | 840080 | Standby Full Crew-Port Equipment Rented to Corps | M04 | Execute/Build |  |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Nav Office Operations | 850010 | Nav Office Operations-Staff Labor | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Nav Office Operations | 850020 | Nav Office Operations-Materials & Supplies | M04 | Execute/Build |  |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Nav Office Operations | 850030 | Nav Office Operations-Services | M04 | Execute/Build |  |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Nav Office Operations | 850040 | Nav Office Operations-Utilities | M04 | Execute/Build |  |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Nav Office Operations | 850050 | Nav Office Operations-Cost Offsets | M04 | Execute/Build |  |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Nav Office Operations | 850070 | Nav Office Operations-Out of Town | M04 | Execute/Build |  |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Nav Div Overhead | 860010 | Nav Div Overhead-Depreciation | M04 | Execute/Build |  |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Nav Div Overhead | 860020 | Nav Div Overhead-Property/Liability Claims | M04 | Execute/Build |  |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Nav Div Overhead | 860030 | Nav Div Overhead-Operating Engr Trust 701 Local | M04 | Execute/Build |  |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Nav Div Overhead | 860040 | Nav Div Overhead-Unemployment | M04 | Execute/Build |  |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Nav Div Overhead | 860050 | Nav Div Overhead-Workers Comp Fees/Claims | M04 | Execute/Build |  |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Nav Div Overhead | 860060 | Nav Div Overhead-Pensions | M04 | Execute/Build |  |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Nav Div Overhead | 860090 | Nav Div Overhead-Safety Incentive Program | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Interdepartment Support | 870010 | Interdepartment Support-Engineering Support | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Interdepartment Support | 870020 | Interdepartment Support-Projects Support | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Interdepartment Support | 870030 | Interdepartment Support-Financial Support | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Interdepartment Support | 870040 | Interdepartment Support-Marine Support | M04 | Execute/Build | LBR |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - General & Admin (G&A) 15% | 880010 | General & Admin (G&A) 15%-Allocated Support Services | M04 | Execute/Build |  |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - General & Admin (G&A) 15% | 880020 | General & Admin (G&A) 15%-Cost of Money Rate | M04 | Execute/Build |  |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Other Reimbursements | 901000 | Other Reimbursements-Environ. Remediation - PRP | M05 | Close-out |  |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Other Reimbursements | 901100 | Other Reimbursements-Insurance Reimbursements | M05 | Close-out |  |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Other Reimbursements | 901200 | Other Reimbursements-Third Party Shared Costs | M05 | Close-out |  |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Other Reimbursements | 901300 | Other Reimbursements-Business Development | M05 | Close-out |  |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Other Reimbursements | 901400 | Other Reimbursements-COE Dredge Operations | M05 | Close-out |  |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Other Reimbursements | 901500 | Other Reimbursements-TSA Agreements | M05 | Close-out |  |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Other Reimbursements | 901600 | Other Reimbursements-Business Energy Tax Credit | M05 | Close-out |  |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Other Reimbursements | 901700 | Other Reimbursements-SEP Program | M05 | Close-out |  |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Other Reimbursements | 901800 | Other Reimbursements-Intergovernmental Agreemen | M05 | Close-out |  |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Other Reimbursements | 901910 | Other Reimbursements-Port of Kalama Reimbursement | M05 | Close-out |  |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Other Reimbursements | 901920 | Other Reimbursements-Port of Longview Reimbursement | M05 | Close-out |  |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Other Reimbursements | 901930 | Other Reimbursements-Port of Vancouver Reimbursemen | M05 | Close-out |  |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Other Reimbursements | 901940 | Other Reimbursements-Port of Woodland Reimbursement | M05 | Close-out |  |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Other Reimbursements | 902000 | Other Reimbursements-Port of St. Helens Reimburseme | M05 | Close-out |  |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Other Reimbursements | 902100 | Other Reimbursements-State of Oregon Reimbursement | M05 | Close-out |  |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Other Reimbursements | 902200 | Other Reimbursements-OECDD - $27.7M | M05 | Close-out |  |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Other Reimbursements | 902300 | Other Reimbursements-ICTSI Estimated Reimbursement | M05 | Close-out |  |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Other Reimbursements | 902310 | Other Reimbursements-ICTSI Lease Reimbursements | M05 | Close-out |  |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Other Reimbursements | 902400 | Other Reimbursements-Equitable Sharing-Treasury Dep | M05 | Close-out |  |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Other Reimbursements | 902450 | Other Reimbursements-Equitable Sharing-Justice Dept | M05 | Close-out |  |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Capitalized Alloc Sup Svs | 908550 | Capitalized Alloc Sup Svs-Annual Engineering Adjustment | M02 | General Administration |  |  |  |  | 0
M99 | MW Master Chart April 2016 | MW Master Chart April 2016 - Capitalized Alloc Sup Svs | 909000 | Capitalized Alloc Sup Svs-Capitalized Allocated Supp Svs | M05 | Close-out |  |  |  |  | 0
*Warning - Number of Hours Do Not Match Schedule and Resource Form
Instructions:
Estimating Method (Percentage Based)
STEP 1: Select "Percentage Based" under Estimating Method
STEP 2: Enter % Soft Cost (as percentage of Hard Cost)
Estimating Method (Hourly Estimate)
STEP 1: Select "Hourly Estimate" under Estimating Method
STEP 2: Fill in Unit Rates/ Quantities and Unit Fields, or as an option, utilize the schedule and resource form to calculate hours based on project schedule (Quantities reference the optional & resource form, if the form is not utilized, the formulas can be overwritten by desired quantities).

## Optional - Sch & Resource Form
Schedule & Resource Estimate Form
Project Title: | Taxiway K West Rehabiltation/ Reconstruction (w/o M&I btwn Rwy 3-21 and NRWY)
Project #: | 701219
Rev #: | 0
Rev # Date: | 2023-07-28
Estimated Schedule
Phase | Start Date | End Date | Duration (Wks)
Project Administration |  |  | 0
Design |  |  | 0
Execute/Build |  |  | 0
Close-Out |  |  | 0
Estimated Resources
Role | Avg. Hrs/Wk | Total Hours
Project Manager |  | 0
| TOTAL | 0 | 101000 - Project Admin & Mgmt-General
Spec Writer |  | 0
| TOTAL | 0 | 141100 - Design-Specification Development
Environmental Planner |  | 0
| TOTAL | 0 | 141600 - Design-Environmental
Project Engineer |  | 0
Electrical Engineer |  | 0
Facility Engineer |  | 0
| TOTAL | 0 | 141700 - Design-PE Design
Surveyor |  | 0
Locates |  | 0
| TOTAL | 0 | 141800 - Design-Survey
CAD Tech |  | 0
BIM Tech |  | 0
TRC Tech |  | 0
| TOTAL | 0 | 141900 - Design-Drawing and Development
Construction Manager |  | 0
Inspector |  | 0
| TOTAL | 0 | 142100 - Design-Construction/Inspection Support
IT Resource |  | 0
| TOTAL | 0 | 142600 - Design-IT Design Support
Construction Manager |  | 0
| TOTAL | 0 | 191200 - Construction-Management
Civil Inspector |  | 0
Electrical Inspector |  | 0
Mechanical Inspector |  | 0
| TOTAL | 0 | 191300 - Construction-Inspection
Surveyor |  | 0
Locates |  | 0
| TOTAL | 0 | 191500 - Construction-Survey
Environmental Specialist |  | 0
| TOTAL | 0 | 191600 - Construction-Environmental
Project Engineer |  | 0
Electrical Engineer |  | 0
Facility Engineer |  | 0
| TOTAL | 0 | 191800 - Construction-Engineering Support
Maintenance Personnel |  | 0
| TOTAL | 0 | 191900 - Construction-Maintenance
IT Resource |  | 0
| TOTAL | 0 | 192000 - Construction-IT
Project Engineer |  | 0
CAD Tech |  | 0
BIM Tech |  | 0
| TOTAL | 0 | 781100 - Project Close Out-As Builts
Surveyor |  | 0
| TOTAL | 0 | 781200 - Project Close Out-Survey
TRC Tech |  | 0
| TOTAL | 0 | 781300 - Project Close Out-Technical Reference Center
GIS Analyst |  | 0
| TOTAL | 0 | 781400 - Project Close Out-Geographic Information System
CASS |  | 0
| TOTAL | 0 | 909000 - Capitalized Alloc Sup Svs-Capitalized Allocated Supp Svs
| Total Hours | 0
Formulas:
Duration (Wks) = IFERROR(DATEDIF([Start Date],[End Date],"d")/7,0)
Instructions:
1. Enter estimated start and end dates for different phases of project.
2. Enter in average hours/ week for each role for the duration of project (for all 4 phases listed)
3. Hours will populate to the soft cost estimating form if formulas have not been modified.
4. CASS is calculated based on the number of total hours

## Dashboard
ESTIMATE DASHBOARD
Project Title: |  | Taxiway K West Rehabiltation/ Reconstruction (w/o M&I btwn Rwy 3-21 and NRWY)
Project #: |  | 701219
Rev # |  | 0
Rev # Date |  | 2023-07-28
Project Estimate Chart
Chart is auto-populated from 'Project Estimate' table below
Project Estimate
Risk = Contingency + Escalation | [5 empty] | Performance Metric
| Hard ($) | Soft ($) | Contingency ($) | Escalation ($) | Estimate ($) | Low Range ($) | High Range ($)
Project Charter
Business Case - Gate 1
Preliminary Design - Gate 2
100% Design/ Pre-Bid - Gate 3
Bid Acceptance - Gate 4
Project Closeout - Gate 5

## Sections
Pavement Sections
Section 1: | 136800 | S.F. | [6 empty] | Pulled area from 8-25-2022 "2026 Taxiway K West Rehabiltiation" estimate
Description: | Pavement inlay (3" AC mill and inlay) | [7 empty] | 7-25-2023 Revised to remove section from Taxiway K/NRWY hold line to Taxiway K/E hold line.
| Average | Subbase | Crushed Base | Pavement | AC Surface | Bituminous | PCC | Total
| Fill Depth | Course | Course | Milling1 | Course | Base | Pavement | Section
| (in) | (in) | (in) | (in) | (in) | (in) | (in) | (in)
Removed | 0 | 0 | 0 | 3 |  | 0 | 0 | 3
Added | 0 | 0 | 0 |  | 3 | 0 | 0 | 3
Pavement Prep Items |  | Quantity | Units |  | Pavement Section Items |  | Quantity | Units
PCC Pavement Removal |  | 0 | CY |  | Borrow |  | 0 | CY
AC Pavement Removal |  | 0 | CY |  | Subbase Course |  | 0 | CY
Agg Base Removal |  | 0 | CY |  | Aggregate Base |  | 0 | CY
Common Excavation |  | 0 | CY |  | AC Surface Course |  | 2730 | TON
Unsuitable Excavation2 |  | 0 | CY |  | Bituminous Base Course |  | 0 | TON
Asphalt Milling 0-3 Inches |  | 15200 | SY |  | PCC Pavement |  | 0 | SY
Asphalt Milling 3-6 Inches |  | 0 | SY | 1- | Milling over 9 inches is considered AC pavement Removal
Asphalt Milling 6-9 Inches1 |  | 0 | SY | 2- | 5% | of Common Ex is Unsuiltable
Section 2: | 16550 | S.F. | (<--Same total area as Original Twy K Estimate as it only applies to reconstruction areas)
Description: | Pavement tie in areas (3" mill and inlay) - 15-foot transition width
| Average | Subbase | Crushed Base | Pavement | AC Surface | Bituminous | PCC | Total
| Fill Depth | Course | Course | Milling1 | Course | Base | Pavement | Section
| (in) | (in) | (in) | (in) | (in) | (in) | (in) | (in)
Removed | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 3
Added | 0 | 0 | 0 |  | 3 | 0 | 0 | 3
Pavement Prep Items |  | Quantity | Units |  | Pavement Section Items |  | Quantity | Units
PCC Pavement Removal |  | 0 | CY |  | Borrow |  | 0 | CY
AC Pavement Removal |  | 0 | CY |  | Subbase Course |  | 0 | CY
Agg Base Removal |  | 0 | CY |  | Aggregate Base |  | 0 | CY
Common Excavation |  | 0 | CY |  | AC Surface Course |  | 330 | TON
Unsuitable Excavation2 |  | 0 | CY |  | Bituminous Base Course |  | 0 | TON
Asphalt Milling 0-3 Inches |  | 1840 | SY |  | PCC Pavement |  | 0 | SY
Asphalt Milling 3-6 Inches |  | 0 | SY | 1- | Milling over 9 inches is considered AC pavement Removal
Asphalt Milling 6-9 Inches1 |  | 0 | SY | 2- | 5% | of Common Ex is Unsuiltable
Section 3: | 133371 | S.F.
Description: | Taxiway pavement rehabilitation (4" surface AC, 14 base course, 6" agg, 29" sand subbase)
| Average | Subbase | Crushed Base | Pavement | AC Surface | Bituminous | PCC | Total
| Fill Depth | Course | Course | Milling1 | Course | Base | Pavement | Section
| (in) | (in) | (in) | (in) | (in) | (in) | (in) | (in)
Removed | 0 | 29 | 13 | 0 | 5 | 6 | 0 | 53
Added | 0 | 29 | 6 |  | 4 | 14 | 0 | 53
Pavement Prep Items |  | Quantity | Units |  | Pavement Section Items |  | Quantity | Units
PCC Pavement Removal |  | 0 | CY |  | Borrow |  | 0 | CY
AC Pavement Removal |  | 14818 | SY |  | Subbase |  | 11940 | CY | revised CY estimate to be SY
Agg Base Removal |  | 5360 | CY |  | Aggregate Base |  | 2470 | CY
Common Excavation |  | 11940 | CY |  | AC Surface Course |  | 3550 | TON
Unsuitable Excavation2 |  | 600 | CY |  | Bituminous Base Course |  | 12410 | TON
Asphalt Milling 0-3 Inches |  | 0 | SY |  | PCC Pavement |  | 0 | SY
Asphalt Milling 3-6 Inches |  | 0 | SY | 1- | Milling over 9 inches is considered AC pavement Removal
Asphalt Milling 6-9 Inches1 |  | 0 | SY | 2- | 5% | of Common Ex is Unsuiltable
Section 4: | 234144 | S.F.
Description: | Taxiway apron pavement rehabilitation (4" surface AC, 11 base course, 6" agg, 13" sand subbase)
| Average | Subbase | Crushed Base | Pavement | AC Surface | Bituminous | PCC | Total
| Fill Depth | Course | Course | Milling1 | Course | Base | Pavement | Section
| (in) | (in) | (in) | (in) | (in) | (in) | (in) | (in)
Removed | 0 | 15 | 10 | 0 | 4 | 5 | 0 | 34
Added | 0 | 13 | 6 |  | 4 | 11 | 0 | 34
Pavement Prep Items |  | Quantity | Units |  | Pavement Section Items |  | Quantity | Units
PCC Pavement Removal |  | 0 | CY |  | Borrow |  | 0 | CY
AC Pavement Removal |  | 26015 | SY |  | Subbase |  | 9400 | CY | revised CY estimate to be SY
Agg Base Removal |  | 7230 | CY |  | Aggregate Base |  | 4340 | CY
Common Excavation |  | 10840 | CY |  | AC Surface Course |  | 6230 | TON
Unsuitable Excavation2 |  | 550 | CY |  | Bituminous Base Course |  | 17120 | TON
Asphalt Milling 0-3 Inches |  | 0 | SY |  | PCC Pavement |  | 0 | SY
Asphalt Milling 3-6 Inches |  | 0 | SY | 1- | Milling over 9 inches is considered AC pavement Removal
Asphalt Milling 6-9 Inches1 |  | 0 | SY | 2- | 5% | of Common Ex is Unsuiltable
Section 5: | 0 | S.F.
Description: | Replace 5' of taxiway shoulder section where next to full depth reconstruction (4" AC, 8" agg, recompact existing subbase)
| Average | Subbase | Crushed Base | Pavement | AC Surface | Bituminous | PCC | Total
| Fill Depth | Course | Course | Milling1 | Course | Base | Pavement | Section
| (in) | (in) | (in) | (in) | (in) | (in) | (in) | (in)
Removed | 0 | 0 | 8 | 4 | 0 | 0 | 0 | 12
Added | 0 | 0 | 8 |  | 4 | 0 | 0 | 12
Pavement Prep Items |  | Quantity | Units |  | Pavement Section Items |  | Quantity | Units
PCC Pavement Removal |  | 0 | CY |  | Borrow |  | 0 | CY
AC Pavement Removal |  | 0 | CY |  | Subbase |  | 0 | CY
Agg Base Removal |  | 0 | CY |  | Aggregate Base |  | 0 | CY
Common Excavation |  | 0 | CY |  | AC Surface Course |  | 0 | TON
Unsuitable Excavation2 |  | 0 | CY |  | Bituminous Base Course |  | 0 | TON
Asphalt Milling 0-3 Inches |  | 0 | SY |  | PCC Pavement |  | 0 | SY
Asphalt Milling 3-6 Inches |  | 0 | SY | 1- | Milling over 9 inches is considered AC pavement Removal
Asphalt Milling 6-9 Inches1 |  | 0 | SY | 2- | 5% | of Common Ex is Unsuiltable
Section 6: | 0 | S.F.
Description:
| Average | Subbase | Crushed Base | Pavement | AC Surface | Bituminous | PCC | Total
| Fill Depth | Course | Course | Milling1 | Course | Base | Pavement | Section
| (in) | (in) | (in) | (in) | (in) | (in) | (in) | (in)
Removed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Added | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Pavement Prep Items |  | Quantity | Units |  | Pavement Section Items |  | Quantity | Units
PCC Pavement Removal |  | 0 | CY |  | Borrow |  | 0 | CY
AC Pavement Removal |  | 0 | CY |  | Subbase |  | 0 | CY
Agg Base Removal |  | 0 | CY |  | Aggregate Base |  | 0 | CY
Common Excavation |  | 0 | CY |  | AC Surface Course |  | 0 | TON
Unsuitable Excavation2 |  | 0 | CY |  | Bituminous Base Course |  | 0 | TON
Asphalt Milling 0-3 Inches |  | 0 | SY |  | PCC Pavement |  | 0 | SY
Asphalt Milling 3-6 Inches |  | 0 | SY | 1- | Milling over 9 inches is considered AC pavement Removal
Asphalt Milling 6-9 Inches1 |  | 0 | SY | 2- | 5% | of Common Ex is Unsuiltable
Section 7: | 0 | S.F.
Description:
| Average | Subbase | Crushed Base | Pavement | AC Surface | Bituminous | PCC | Total
| Fill Depth | Course | Course | Milling1 | Course | Base | Pavement | Section
| (in) | (in) | (in) | (in) | (in) | (in) | (in) | (in)
Removed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Added | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Pavement Prep Items |  | Quantity | Units |  | Pavement Section Items |  | Quantity | Units
PCC Pavement Removal |  | 0 | CY |  | Borrow |  | 0 | CY
AC Pavement Removal |  | 0 | CY |  | Subbase |  | 0 | CY
Agg Base Removal |  | 0 | CY |  | Aggregate Base |  | 0 | CY
Common Excavation |  | 0 | CY |  | AC Surface Course |  | 0 | TON
Unsuitable Excavation2 |  | 0 | CY |  | Bituminous Base Course |  | 0 | TON
Asphalt Milling 0-3 Inches |  | 0 | SY |  | PCC Pavement |  | 0 | SY
Asphalt Milling 3-6 Inches |  | 0 | SY | 1- | Milling over 9 inches is considered AC pavement Removal
Asphalt Milling 6-9 Inches1 |  | 0 | SY | 2- | 5% | of Common Ex is Unsuiltable
Section 8: | 0 | S.F. | [7 empty] | Total Section 8 Area: | 128466 | SF
Decription:
| Average | Subbase | Crushed Base | Pavement | AC Surface | Bituminous | PCC | Total
| Fill Depth | Course | Course | Milling1 | Course | Base | Pavement | Section
| (in) | (in) | (in) | (in) | (in) | (in) | (in) | (in)
Removed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Added | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Pavement Prep Items |  | Quantity | Units |  | Pavement Section Items |  | Quantity | Units
PCC Pavement Removal |  | 0 | CY |  | Borrow |  | 0 | CY
AC Pavement Removal |  | 0 | CY |  | Subbase |  | 0 | CY
Agg Base Removal |  | 0 | CY |  | Aggregate Base |  | 0 | CY
Common Excavation |  | 0 | CY |  | AC Surface Course |  | 0 | TON
Unsuitable Excavation2 |  | 0 | CY |  | Bituminous Base Course |  | 0 | TON
Asphalt Milling 0-3 Inches |  | 0 | SY |  | PCC Pavement |  | 0 | SY
Asphalt Milling 3-6 Inches |  | 0 | SY | 1- | Milling over 9 inches is considered AC pavement Removal
Asphalt Milling 6-9 Inches1 |  | 0 | SY | 2- | 5% | of Common Ex is Unsuiltable

## DivisionCostCodeLookup (hidden)
Division | CostCode | Division Number | DivisionLookup | Description | CostCode | Division Number | CostCodeSeg 2 | CostCodeSeg 3 | Description | Costcode | SUBGROUP: GENERAL REQUIREMENTS
01 General Requirements | 10000 | 1 | Division01 |  | 10000 | 1 | 00 | 00 | PROJECT MANAGEMENT | 100000 | Division 01 - General Requirements
02 Existing Conditions | 20000 | 2 | Division02 | Contractor'sManagementandCoordination | 13100 | 1 | 31 | 00 | DESIGN | 140000 | 13100 | Contractor's Management and Coordination
03 Concrete | 30000 | 3 | Division03 | SubmittalProcedures | 13300 | 1 | 33 | 0 | DEVELOPMENT | 170000 | 13300 | Submittal Procedures
04 Masonry | 40000 | 4 | Division04 | SecurityControl | 13500 | 1 | 35 | 0 | CONSTRUCTION | 190000 | 13500 | Security Control
05 Metals | 50000 | 5 | Division05 | Escort | 13501 | 1 | 35 | 1 | PERMITTING | 200000 | 13501 | Escort
06 Wood Plastics And Composites | 60000 | 6 | Division06 | Permits | 14100 | 1 | 14 | 0 |  |  | 14100 | Permits
07 Thermaland Moisture Protection | 70000 | 7 | Division07 | MobilizationandDemobilization | 15000 | 1 | 50 | 00 | PROJECT CLOSE-OUT | 780000 | 15000 | Mobilization and Demobilization
08 Openings | 80000 | 8 | Division08 | TrafficControl | 15001 | 1 | 50 | 1 | CONTINGENCY | 790000 | 15001 | Traffic Control
09 Finishes | 90000 | 9 | Division09 | Sweeping | 15002 | 1 | 50 | 2 | CASS | 909000 | 15002 | Sweeping
10 Specialties | 100000 | 10 | Division10 | TemporaryHeating,CoolingandVentilating | 15123 | 1 | 51 | 23 | CONVERSION | 0 | 15123 | Temporary Heating, Cooling and Ventilating
11 Equipment | 110000 | 11 | Division11 | TemporaryRamps | 15323 | 1 | 53 | 23 |  |  | 15323 | Temporary Ramps
12 Furnishings | 120000 | 12 | Division12 | ConstructionAids | 15400 | 1 | 54 | 0 |  |  | 15400 | Construction Aids
13 Special Construction | 130000 | 13 | Division13 | VehicularAccessandParking | 15500 | 1 | 55 | 0 |  |  | 15500 | Vehicular Access and Parking
14 Conveying Equipment | 140000 | 14 | Division14 | TemporaryBarriersandEnclosures | 15600 | 1 | 56 | 0 |  |  | 15600 | Temporary Barriers and Enclosures
21 Fire Suppression | 210000 | 21 | Division21 | TemporaryErosion,Sediment,andPollutionControl | 15713 | 1 | 57 | 13 |  |  | 15713 | Temporary Erosion, Sediment, and Pollution Control
22 Plumbing | 220000 | 22 | Division22 | ProductStorageandHandlingRequirements | 16600 | 1 | 66 | 0 |  |  | 16600 | Product Storage and Handling Requirements
23 Heating Ventilating And Air Conditioning | 230000 | 23 | Division23 | CuttingandPatching | 17329 | 1 | 73 | 29 |  |  | 17329 | Cutting and Patching
26 Electrical | 260000 | 26 | Division26 | CleaningandWasteManagement | 17400 | 1 | 74 | 00 |  |  | 17400 | Cleaning and Waste Management
27 Communications | 270000 | 27 | Division27 | ConstructionWasteRecycling | 17419 | 1 | 74 | 19 |  |  | 17419 | Construction Waste Recycling
28 Electronic Safety And Security | 280000 | 28 | Division28 | Commissioning | 19100 | 1 | 91 | 0 |  |  | 19100 | Commissioning
31 Earthwork | 310000 | 31 | Division31 | [7 empty] | SUBGROUP: FACILITY CONSTRUCTION
32 Exterior Improvements | 320000 | 32 | Division32 |  | 20000 | 2 | 00 | 00 |  |  | Division 02 - Existing Conditions
33 Utilities | 330000 | 33 | Divsion33 | CommonWorkResultsforExistingConditions | 20500 | 2 | 05 | 00 |  |  | 20500 | Common Work Results for Existing Conditions
34 Transportation | 340000 | 34 | Division34 | SiteDemolition | 24113 | 2 | 41 | 13 |  |  | 24113 | Site Demolition
35 Waterway And Marine | 350000 | 35 | Division35 | SelectiveInteriorDemolition | 24119 | 2 | 41 | 19 |  |  | 24119 | Selective Interior Demolition
41 Material Proc And Handling Eq. | 410000 | 41 | Divsion41 | SiteRemediation | 25000 | 2 | 50 | 00 |  |  | 25000 | Site Remediation
51 Earthwork FAA | 510000 | 51 | Division51 | RemovalandDisposalofContaminatedSoils | 26100 | 2 | 61 | 00 |  |  | 26100 | Removal and Disposal of Contaminated Soils
52 Flexible Base Courses FAA | 520000 | 52 | Division52 | UndergroundStorageTankRemoval | 26500 | 2 | 65 | 00 |  |  | 26500 | Underground Storage Tank Removal
53 Rigid Base Courses FAA | 530000 | 53 | Division53 | GroundwaterTreatment | 27100 | 2 | 71 | 0 |  |  | 27100 | Groundwater Treatment
54 Flexible Surface Courses FAA | 540000 | 54 | Division54 | AsbestosAbatement | 28213 | 2 | 82 | 13 |  |  | 28213 | Asbestos Abatement
55 Rigid Pavement FAA | 550000 | 55 | Division55 | AsbestosManagement | 28216 | 2 | 82 | 16 |  |  | 28216 | Asbestos Management
56 Miscellaneous FAA | 560000 | 56 | Division56 | Lead_BasedPaintManagement | 28313 | 2 | 83 | 13 |  |  | 28313 | Lead-Based Paint Management
57 Fencing FAA | 570000 | 57 | Division57 | Lead_BasedPaintAbatement | 28319 | 2 | 83 | 19 |  |  | 28319 | Lead-Based Paint Abatement
58 Drainage FAA | 580000 | 58 | Division58 | PCBRemediation | 28400 | 2 | 84 | 00 |  |  | 28400 | PCB Remediation
59 Turfing FAA | 590000 | 59 | Division59
60 Lighting Installation FAA | 600000 | 60 | Division60 |  | 30000 | 3 | 00 | 00 |  |  | Division 03 - Concrete
|  |  |  | CommonWorkResultsforConcrete | 30500 | 3 | 05 | 00 |  |  | 30500 | Common Work Results for Concrete
|  |  |  | ConcreteFormwork | 31100 | 3 | 11 | 00 |  |  | 31100 | Concrete Formwork
|  |  |  | ConcreteAccessories | 31500 | 3 | 15 | 00 |  |  | 31500 | Concrete Accessories
|  |  |  | ConcreteReinforcing | 32000 | 3 | 20 | 00 |  |  | 32000 | Concrete Reinforcing
|  |  |  | Cast_In_PlaceConcrete | 33000 | 3 | 30 | 00 |  |  | 33000 | Cast-In-Place Concrete
|  |  |  | ConcreteGrouting | 36000 | 3 | 60 | 00 |  |  | 36000 | Concrete Grouting
[5 empty] | 40000 | 4 | 00 | 00 |  |  | Division 04 - Masonry
|  |  |  | CommonWorkResultsforMasonry | 40500 | 4 | 05 | 00 |  |  | 40500 | Common Work Results for Masonry
|  |  |  | MasonryMortarandGrout | 40513 | 4 | 05 | 13 |  |  | 40513 | Masonry Mortar and Grout
|  |  |  | MasonryAccessories | 40523 | 4 | 05 | 23 |  |  | 40523 | Masonry Accessories
|  |  |  | BrickMasonry | 42113 | 4 | 21 | 13 |  |  | 42113 | Brick Masonry
|  |  |  | ConcreteUnitMasonry | 42200 | 4 | 22 | 00 |  |  | 42200 | Concrete Unit Masonry
[5 empty] | 50000 | 5 | 00 | 00 |  |  | Division 05 - Metals
|  |  |  | CommonWorkResultsforMetals | 50500 | 5 | 05 | 00 |  |  | 50500 | Common Work Results for Metals
|  |  |  | GalvanicCoatings | 50513 | 5 | 05 | 13 |  |  | 50513 | Galvanic Coatings
|  |  |  | StructuralSteelFraming | 51200 | 5 | 12 | 00 |  |  | 51200 | Structural Steel Framing
|  |  |  | ArchitecturallyExposedStructuralSteelFraming | 51213 | 5 | 12 | 13 |  |  | 51213 | Architecturally Exposed Structural Steel Framing
|  |  |  | SteelJoistFraming | 52100 | 5 | 21 | 00 |  |  | 52100 | Steel Joist Framing
|  |  |  | SteelDecking | 53100 | 5 | 31 | 00 |  |  | 53100 | Steel Decking
|  |  |  | Cold_FormedMetalFraming | 54000 | 5 | 40 | 00 |  |  | 54000 | Cold-Formed Metal Framing
|  |  |  | MetalFabrications | 55000 | 5 | 50 | 00 |  |  | 55000 | Metal Fabrications
|  |  |  | MetalRailings | 55200 | 5 | 52 | 00 |  |  | 55200 | Metal Railings
|  |  |  | StainlessSteelFabrications | 57050 | 5 | 70 | 50 |  |  | 57050 | Stainless Steel Fabrications
|  |  |  | GlazedDecorativeMetalRailings | 57300 | 5 | 73 | 00 |  |  | 57300 | Glazed Decorative Metal Railings
|  |  |  | DecorativeFormedMetal | 57500 | 5 | 75 | 00 |  |  | 57500 | Decorative Formed Metal
[5 empty] | 60000 | 6 | 00 | 00 |  |  | Division 06 - Wood, Plastics & Composites
|  |  |  | CommonWorkResultsforWood.Plastics&Composites | 60500 | 6 | 05 | 00 |  |  | 60500 | Common Work Results for Wood, Plastics & Composites
|  |  |  | MaintenanceofWood.Plastics.andComposites | 60100 | 6 | 01 | 00 |  |  | 60100 | Maintenance of Wood, Plastics, and Composites
|  |  |  | RoughCarpentry | 61000 | 6 | 10 | 00 |  |  | 61000 | Rough Carpentry
|  |  |  | FramingandSheathing | 61100 | 6 | 11 | 00 |  |  | 61100 | Framing and Sheathing
|  |  |  | TreatedWoodforRoofRepairs | 61400 | 6 | 14 | 00 |  |  | 61400 | Treated Wood for Roof Repairs
|  |  |  | FinishCarpentry | 62000 | 6 | 20 | 00 |  |  | 62000 | Finish Carpentry
|  |  |  | ArchitecturalWoodwork | 64000 | 6 | 40 | 00 |  |  | 64000 | Architectural Woodwork
|  |  |  | CustomCabinets | 64100 | 6 | 41 | 00 |  |  | 64100 | Custom Cabinets
|  |  |  | WoodPaneling | 64200 | 6 | 42 | 00 |  |  | 64200 | Wood Paneling
|  |  |  | CustomCasework | 64600 | 6 | 46 | 00 |  |  | 64600 | Custom Casework
|  |  |  | PlasticStructuralLumber | 65113 | 6 | 51 | 13 |  |  | 65113 | Plastic Structural Lumber
|  |  |  | PlasticFabrications | 66000 | 6 | 60 | 00 |  |  | 66000 | Plastic Fabrications
[5 empty] | 70000 | 7 | 00 | 00 |  |  | Division 07 - Thermal and Moisture Protection
|  |  |  | CommonWorkResultsforThermalandMoistureProtection | 70500 | 7 | 05 | 00 |  |  | 70500 | Common Work Results for Thermal and Moisture Protection
|  |  |  | ModifiedBituminousSheetRoofingSystemRepairs | 70152 | 7 | 01 | 52 |  |  | 70152 | Modified Bituminous Sheet Roofing System Repairs
|  |  |  | ElastomericSheetRoofingSystemRepairs | 70153 | 7 | 01 | 53 |  |  | 70153 | Elastomeric Sheet Roofing System Repairs
|  |  |  | Waterproofing | 71000 | 7 | 10 | 00 |  |  | 71000 | Waterproofing
|  |  |  | Dampproofing | 71100 | 7 | 11 | 00 |  |  | 71100 | Damp proofing
|  |  |  | TrafficCoatings | 71800 | 7 | 18 | 00 |  |  | 71800 | Traffic Coatings
|  |  |  | ThermalInsulation | 72100 | 7 | 21 | 00 |  |  | 72100 | Thermal Insulation
|  |  |  | VaporRetarders | 72600 | 7 | 26 | 00 |  |  | 72600 | Vapor Retarders
|  |  |  | AirBarriers | 72700 | 7 | 27 | 00 |  |  | 72700 | Air Barriers
|  |  |  | RoofPanels | 74100 | 7 | 41 | 00 |  |  | 74100 | Roof Panels
|  |  |  | WallPanels | 74200 | 7 | 42 | 00 |  |  | 74200 | Wall Panels
|  |  |  | MembraneRoofing | 75000 | 7 | 50 | 00 |  |  | 75000 | Membrane Roofing
|  |  |  | Built_UpBituminousRoofing | 75100 | 7 | 51 | 00 |  |  | 75100 | Built-Up Bituminous Roofing
|  |  |  | ModifiedBituminousSheetRoofingSystem | 75200 | 7 | 52 | 00 |  |  | 75200 | Modified Bituminous Sheet Roofing System
|  |  |  | ElastomericSheetRoofingSystem | 75300 | 7 | 53 | 00 |  |  | 75300 | Elastomeric Sheet Roofing System
|  |  |  | SheetMetalRoofing | 76100 | 7 | 61 | 00 |  |  | 76100 | Sheet Metal Roofing
|  |  |  | SheetMetalFlashingandTrim | 76200 | 7 | 62 | 00 |  |  | 76200 | Sheet Metal Flashing and Trim
|  |  |  | ManufacturedGuttersandDownspouts | 77123 | 7 | 71 | 23 |  |  | 77123 | Manufactured Gutters and Downspouts
|  |  |  | RoofAccessories | 77200 | 7 | 72 | 00 |  |  | 77200 | Roof Accessories
|  |  |  | AppliedFireproofing | 78100 | 7 | 81 | 00 |  |  | 78100 | Applied Fireproofing
|  |  |  | Firestopping | 78400 | 7 | 84 | 00 |  |  | 78400 | Fire stopping
|  |  |  | JointSealants | 79200 | 7 | 92 | 00 |  |  | 79200 | Joint Sealants
|  |  |  | ExpansionControl | 79500 | 7 | 95 | 00 |  |  | 79500 | Expansion Control
[5 empty] | 80000 | 8 | 00 | 00 |  |  | Division 08 - Openings
|  |  |  | CommonWorkResultsforOpenings | 80500 | 8 | 05 | 00 |  |  | 80500 | Common Work Results for Openings
|  |  |  | Door/WindowSchedule | 80600 | 8 | 06 | 00 |  |  | 80600 | Door/Window Schedule
|  |  |  | MetalDoorsandFrames | 81100 | 8 | 11 | 00 |  |  | 81100 | Metal Doors and Frames
|  |  |  | WoodDoors | 81400 | 8 | 14 | 00 |  |  | 81400 | Wood Doors
|  |  |  | AccessDoorsandPanels | 83100 | 8 | 31 | 00 |  |  | 83100 | Access Doors and Panels
|  |  |  | CoilingDoorsandGrilles | 83300 | 8 | 33 | 00 |  |  | 83300 | Coiling Doors and Grilles
|  |  |  | PanelDoors | 83600 | 8 | 36 | 00 |  |  | 83600 | Panel Doors
|  |  |  | AluminumEntrancesandStorefronts | 84113 | 8 | 41 | 13 |  |  | 84113 | Aluminum Entrances and Storefronts
|  |  |  | All_GlassEntrancesandStorefronts | 84126 | 8 | 41 | 26 |  |  | 84126 | All-Glass Entrances and Storefronts
|  |  |  | EntranceDoorSystems | 84200 | 8 | 42 | 00 |  |  | 84200 | Entrance Door Systems
|  |  |  | GlazedCurtainWalls | 84400 | 8 | 44 | 00 |  |  | 84400 | Glazed Curtain Walls
|  |  |  | Windows | 85000 | 8 | 50 | 00 |  |  | 85000 | Windows
|  |  |  | MetalWindows | 85100 | 8 | 51 | 00 |  |  | 85100 | Metal Windows
|  |  |  | SpecialFunctionWindows | 85600 | 8 | 56 | 00 |  |  | 85600 | Special Function Windows
|  |  |  | Skylights | 86000 | 8 | 60 | 00 |  |  | 86000 | Skylights
|  |  |  | FinishHardware | 87000 | 8 | 70 | 00 |  |  | 87000 | Finish Hardware
|  |  |  | DoorHardware | 87100 | 8 | 71 | 00 |  |  | 87100 | Door Hardware
|  |  |  | Glazing | 88000 | 8 | 80 | 00 |  |  | 88000 | Glazing
|  |  |  | LouversandVents | 89000 | 8 | 90 | 00 |  |  | 89000 | Louvers and Vents
[5 empty] | 90000 | 9 | 00 | 00 |  |  | Division 09 - Finishes
|  |  |  | CommonWorkResultsforFinishes | 90500 | 9 | 05 | 00 |  |  | 90500 | Common Work Results for Finishes
|  |  |  | RoomMaterialandFinishSchedule | 90600 | 9 | 06 | 00 |  |  | 90600 | Room Material and Finish Schedule
|  |  |  | PlasterandGypsumBoardAssemblies | 92100 | 9 | 21 | 00 |  |  | 92100 | Plaster and Gypsum Board Assemblies
|  |  |  | SupportsforPlasterandGypsumBoard | 92200 | 9 | 22 | 00 |  |  | 92200 | Supports for Plaster and Gypsum Board
|  |  |  | Non_StructuralMetalStudFraming | 92216 | 9 | 22 | 16 |  |  | 92216 | Non-Structural Metal Stud Framing
|  |  |  | LathandPlaster | 92236 | 9 | 22 | 36 |  |  | 92236 | Lath and Plaster
|  |  |  | VeneerPlaster | 92600 | 9 | 26 | 00 |  |  | 92600 | Veneer Plaster
|  |  |  | Glass_Fiber_ReinforcedPlasterFabrications | 92713 | 9 | 27 | 13 |  |  | 92713 | Glass-Fiber-Reinforced Plaster Fabrications
|  |  |  | GypsumBoard | 92900 | 9 | 29 | 00 |  |  | 92900 | Gypsum Board
|  |  |  | Tile | 93000 | 9 | 30 | 00 |  |  | 93000 | Tile
|  |  |  | CeramicTile | 93013 | 9 | 30 | 13 |  |  | 93013 | Ceramic Tile
|  |  |  | CeramicTileFloorFinish | 93014 | 9 | 30 | 14 |  |  | 93014 | Ceramic Tile Floor Finish
|  |  |  | AcousticalCeilings | 95100 | 9 | 51 | 00 |  |  | 95100 | Acoustical Ceilings
|  |  |  | SpecialtyCeilings(linearmetalceilings.etc.) | 95400 | 9 | 54 | 00 |  |  | 95400 | Specialty Ceilings (linear metal ceilings, etc.)
|  |  |  | FloorTreatment | 96100 | 9 | 61 | 00 |  |  | 96100 | Floor Treatment
|  |  |  | SpecialtyFlooring | 96200 | 9 | 62 | 00 |  |  | 96200 | Specialty Flooring
|  |  |  | MasonryFlooring | 96300 | 9 | 63 | 00 |  |  | 96300 | Masonry Flooring
|  |  |  | StoneFlooring | 96340 | 9 | 63 | 40 |  |  | 96340 | Stone Flooring
|  |  |  | WoodFlooring | 96400 | 9 | 64 | 00 |  |  | 96400 | Wood Flooring
|  |  |  | ResilientFlooring | 96500 | 9 | 65 | 00 |  |  | 96500 | Resilient Flooring
|  |  |  | ResilientTileFlooring | 96519 | 9 | 65 | 19 |  |  | 96519 | Resilient Tile Flooring
|  |  |  | TerrazzoFlooring | 96600 | 9 | 66 | 00 |  |  | 96600 | Terrazzo Flooring
|  |  |  | Carpeting | 96800 | 9 | 68 | 00 |  |  | 96800 | Carpeting
|  |  |  | AccessFlooring | 96900 | 9 | 69 | 00 |  |  | 96900 | Access Flooring
|  |  |  | WallCoverings | 97200 | 9 | 72 | 00 |  |  | 97200 | Wall Coverings
|  |  |  | StoneFacing | 97500 | 9 | 75 | 00 |  |  | 97500 | Stone Facing
|  |  |  | SpecialWallSurfaces | 97700 | 9 | 77 | 00 |  |  | 97700 | Special Wall Surfaces
|  |  |  | AcousticRoomComponents(AcousticPanels) | 98400 | 9 | 84 | 00 |  |  | 98400 | Acoustic Room Components (Acoustic Panels)
|  |  |  | Painting(forinteriorAndexteriorarchitecturalpainting) | 99100 | 9 | 91 | 00 |  |  | 99100 | Painting (for interior & exterior architectural painting)
|  |  |  | SpecialCoatings(forpaintingconcrete.masonry.steel.etc.) | 99700 | 9 | 97 | 00 |  |  | 99700 | Special Coatings (for painting concrete, masonry, steel, etc.)
[5 empty] | 100000 | 10 | 00 | 00 |  |  | Division 10 - Specialties
|  |  |  | CommonWorkResultsforSpecialties | 100500 | 10 | 05 | 00 |  |  | 100500 | Common Work Results for Specialties
|  |  |  | VisualDisplaySurfaces | 101100 | 10 | 11 | 00 |  |  | 101100 | Visual Display Surfaces
|  |  |  | IdentifyingDevices(identityAndwayfindingsignage) | 101400 | 10 | 14 | 00 |  |  | 101400 | Identifying Devices (identity & way finding signage)
|  |  |  | TrafficSignage | 101453 | 10 | 14 | 53 |  |  | 101453 | Traffic Signage
|  |  |  | BaggageInformationDisplaySystem | 101463 | 10 | 14 | 63 |  |  | 101463 | Baggage Information Display System
|  |  |  | ToiletCompartments | 102113 | 10 | 21 | 13 |  |  | 102113 | Toilet Compartments
|  |  |  | OperablePartitions | 102226 | 10 | 22 | 26 |  |  | 102226 | Operable Partitions
|  |  |  | ServiceWalls | 102500 | 10 | 25 | 00 |  |  | 102500 | Service Walls
|  |  |  | WallandDoorProtection | 102600 | 10 | 26 | 00 |  |  | 102600 | Wall and Door Protection
|  |  |  | ToiletandBathAccessories | 102800 | 10 | 28 | 00 |  |  | 102800 | Toilet and Bath Accessories
|  |  |  | FireProtectionSpecialties | 104400 | 10 | 44 | 00 |  |  | 104400 | Fire Protection Specialties
|  |  |  | Lockers | 105100 | 10 | 51 | 00 |  |  | 105100 | Lockers
|  |  |  | BusStopShelters | 107343 | 10 | 73 | 43 |  |  | 107343 | Bus Stop Shelters
|  |  |  | Flagpoles | 107500 | 10 | 75 | 00 |  |  | 107500 | Flagpoles
[5 empty] | 110000 | 11 | 00 | 00 |  |  | Division 11 - Equipment
|  |  |  | CommonWorkResultsforEquipment | 110500 | 11 | 05 | 00 |  |  | 110500 | Common Work Results for Equipment
|  |  |  | VehicleServiceEquipment | 111100 | 11 | 11 | 00 |  |  | 111100 | Vehicle Service Equipment
|  |  |  | ParkingControlEquipment | 111200 | 11 | 12 | 00 |  |  | 111200 | Parking Control Equipment
|  |  |  | LoadingDockEquipment | 111300 | 11 | 13 | 00 |  |  | 111300 | Loading Dock Equipment
|  |  |  | FoodServiceEquipment | 114000 | 11 | 40 | 00 |  |  | 114000 | Food Service Equipment
|  |  |  | ProjectionScreens | 115213 | 11 | 52 | 13 |  |  | 115213 | Projection Screens
|  |  |  | SolidWasteHandlingEquipment | 118200 | 11 | 82 | 00 |  |  | 118200 | Solid Waste Handling Equipment
[5 empty] | 120000 | 12 | 00 | 00 |  |  | Division 12 - Furnishings
|  |  |  | CommonWorkResultsforFurnishings | 120500 | 12 | 05 | 00 |  |  | 120500 | Common Work Results for Furnishings
|  |  |  | Art | 121000 | 12 | 10 | 00 |  |  | 121000 | Art
|  |  |  | WindowTreatments | 122000 | 12 | 20 | 00 |  |  | 122000 | Window Treatments
|  |  |  | FurnishingsandAccessories | 124000 | 12 | 40 | 00 |  |  | 124000 | Furnishings and Accessories
|  |  |  | Clocks | 124619 | 12 | 46 | 19 |  |  | 124619 | Clocks
|  |  |  | FloorMats | 124843 | 12 | 48 | 43 |  |  | 124843 | Floor Mats
|  |  |  | Furniture | 125000 | 12 | 50 | 00 |  |  | 125000 | Furniture
|  |  |  | MultipleSeating | 126000 | 12 | 60 | 00 |  |  | 126000 | Multiple Seating
|  |  |  | InteriorPlantsandPlanters | 129200 | 12 | 92 | 00 |  |  | 129200 | Interior Plants and Planters
[5 empty] | 130000 | 13 | 00 | 00 |  |  | Division 13 - Special Construction
|  |  |  | CommonWorkResultsforSpecialConstruction | 130500 | 13 | 05 | 00 |  |  | 130500 | Common Work Results for Special Construction
|  |  |  | Pre_EngineeredBuildings | 133400 | 13 | 34 | 00 |  |  | 133400 | Pre-Engineered Buildings
[5 empty] | 140000 | 14 | 00 | 00 |  |  | Division 14 - Conveying Equipment
|  |  |  | CommonWorkResultsforConveyingEquipment | 140500 | 14 | 05 | 00 |  |  | 140500 | Common Work Results for Conveying Equipment
|  |  |  | Elevators | 142000 | 14 | 20 | 00 |  |  | 142000 | Elevators
|  |  |  | Escalators | 143100 | 14 | 31 | 00 |  |  | 143100 | Escalators
|  |  |  | MovingWalks | 143200 | 14 | 32 | 00 |  |  | 143200 | Moving Walks
|  |  |  | Lifts | 144000 | 14 | 40 | 00 |  |  | 144000 | Lifts
[5 empty] | 210000 | 21 | 00 | 00 |  |  | Division 21 - Fire Suppression
|  |  |  | CommonWorkResultsforFireSuppression | 210500 | 21 | 05 | 00 |  |  | 210500 | Common Work Results for Fire Suppression
|  |  |  | GaugesforFireSuppressionSystems | 210519 | 21 | 05 | 19 |  |  | 210519 | Gauges for Fire Suppression Systems
|  |  |  | PipingSpecialtiesforWater_BasedFireSuppressionPiping | 210520 | 21 | 05 | 20 |  |  | 210520 | Piping Specialties for Water-Based Fire Suppression Piping
|  |  |  | GeneralDutyValvesforWater_BasedFireSuppressionPiping | 210523 | 21 | 05 | 23 |  |  | 210523 | General Duty Valves for Water-Based Fire Suppression Piping
|  |  |  | HangersAndSupportsforFireSuppressionPipingandEquipment | 210529 | 21 | 05 | 29 |  |  | 210529 | Hangers & Supports for Fire Suppression Piping and Equipment
|  |  |  | VibrationandSeismicControlsforFireSuppressionPipingandEquipment | 210548 | 21 | 05 | 48 |  |  | 210548 | Vibration and Seismic Controls for Fire Suppression Piping and Equipment
|  |  |  | IdentificationforFireSuppressionPipingAndEquipment | 210553 | 21 | 05 | 53 |  |  | 210553 | Identification for Fire Suppression Piping & Equipment
|  |  |  | PressureTestingofFireSuppressionSystems | 210590 | 21 | 05 | 90 |  |  | 210590 | Pressure Testing of Fire Suppression Systems
|  |  |  | FireSuppressionSystemsInsulation | 210719 | 21 | 07 | 19 |  |  | 210719 | Fire Suppression Systems Insulation
|  |  |  | FireSuppressionPiping | 211100 | 21 | 11 | 00 |  |  | 211100 | Fire Suppression Piping
|  |  |  | FireSuppressionPumps | 211120 | 21 | 11 | 20 |  |  | 211120 | Fire Suppression Pumps
|  |  |  | FireSuppressionSystems | 212000 | 21 | 20 | 00 |  |  | 212000 | Fire Suppression Systems
|  |  |  | FireDetection/InergenSuppressionSystem | 212200 | 21 | 22 | 00 |  |  | 212200 | Fire Detection/Inergen Suppression System
[5 empty] | 220000 | 22 | 00 | 00 |  |  | Division 22 - Plumbing
|  |  |  | CommonWorkResultsforPlumbing | 220500 | 22 | 05 | 00 |  |  | 220500 | Common Work Results for Plumbing
|  |  |  | MetersandGaugesforPlumbingPiping | 220519 | 22 | 05 | 19 |  |  | 220519 | Meters and Gauges for Plumbing Piping
|  |  |  | PipingSpecialtiesforPlumbingPiping | 220520 | 22 | 05 | 20 |  |  | 220520 | Piping Specialties for Plumbing Piping
|  |  |  | GeneralDutyValvesforPlumbingPiping | 220523 | 22 | 05 | 23 |  |  | 220523 | General Duty Valves for Plumbing Piping
|  |  |  | HangersAndSupportsforPlumbingPipingAndEquip. | 220529 | 22 | 05 | 29 |  |  | 220529 | Hangers & Supports for Plumbing Piping & Equip.
|  |  |  | SeismicRestraintsforPlumbingPipingandEquipment | 220545 | 22 | 05 | 45 |  |  | 220545 | Seismic Restraints for Plumbing Piping and Equipment
|  |  |  | VibrationAndSeismicControlsforPlumbingPipingAndEquipment | 220548 | 22 | 05 | 48 |  |  | 220548 | Vibration & Seismic Controls for Plumbing Piping & Equipment
|  |  |  | IdentificationforPlumbingPipingandEquipment | 220553 | 22 | 05 | 53 |  |  | 220553 | Identification for Plumbing Piping and Equipment
|  |  |  | PressureTestingofPlumbingSystems | 220590 | 22 | 05 | 90 |  |  | 220590 | Pressure Testing of Plumbing Systems
|  |  |  | PlumbingInsulation | 220719 | 22 | 07 | 19 |  |  | 220719 | Plumbing Insulation
|  |  |  | PlumbingPiping | 221100 | 22 | 11 | 00 |  |  | 221100 | Plumbing Piping
|  |  |  | PlumbingPumps | 221120 | 22 | 11 | 20 |  |  | 221120 | Plumbing Pumps
|  |  |  | LiquidGreaseCollectionSystem | 221319 | 22 | 13 | 19 |  |  | 221319 | Liquid Grease Collection System
|  |  |  | PlumbingEquipment | 223000 | 22 | 30 | 00 |  |  | 223000 | Plumbing Equipment
|  |  |  | PlumbingFixtures | 224000 | 22 | 40 | 00 |  |  | 224000 | Plumbing Fixtures
[5 empty] | 230000 | 23 | 00 | 00 |  |  | Division 23 - Heating Ventilating & Air Conditioning
|  |  |  | CommonWorkResultsforHVAC | 230500 | 23 | 05 | 00 |  |  | 230500 | Common Work Results for HVAC
|  |  |  | ExpansionCompensation | 230518 | 23 | 05 | 18 |  |  | 230518 | Expansion Compensation
|  |  |  | MetersandGaugesforHVACPiping | 230519 | 23 | 05 | 19 |  |  | 230519 | Meters and Gauges for HVAC Piping
|  |  |  | PipingSpecialtiesforHVACPiping | 230520 | 23 | 05 | 20 |  |  | 230520 | Piping Specialties for HVAC Piping
|  |  |  | GeneralDutyValvesforHVACPiping | 230523 | 23 | 05 | 23 |  |  | 230523 | General Duty Valves for HVAC Piping
|  |  |  | HangersAndSupportsforHVACPipingandEquipment | 230529 | 23 | 05 | 29 |  |  | 230529 | Hangers & Supports for HVAC Piping and Equipment
|  |  |  | SeismicRestraintsforHVACPipingAndEquipment | 230545 | 23 | 05 | 45 |  |  | 230545 | Seismic Restraints for HVAC Piping & Equipment
|  |  |  | VibrationAndSeismicControlsforHVACPipingAndEquip | 230548 | 23 | 05 | 48 |  |  | 230548 | Vibration & Seismic Controls for HVAC Piping & Equip
|  |  |  | IdentificationforHVACPipingandEquipment | 230553 | 23 | 05 | 53 |  |  | 230553 | Identification for HVAC Piping and Equipment
|  |  |  | PressureTestingofHVACSystems | 230590 | 23 | 05 | 90 |  |  | 230590 | Pressure Testing of HVAC Systems
|  |  |  | Testing.Adjusting.andBalancing | 230593 | 23 | 05 | 93 |  |  | 230593 | Testing, Adjusting, and Balancing
|  |  |  | HVACInsulation | 230719 | 23 | 07 | 19 |  |  | 230719 | HVAC Insulation
|  |  |  | InstrumentationandControlsforHVAC | 230900 | 23 | 09 | 00 |  |  | 230900 | Instrumentation and Controls for HVAC
|  |  |  | GasolineDispensingPumps | 231216 | 23 | 12 | 16 |  |  | 231216 | Gasoline Dispensing Pumps
|  |  |  | HVACPiping | 232000 | 23 | 20 | 00 |  |  | 232000 | HVAC Piping
|  |  |  | SteamandCondensateSpecialties | 232215 | 23 | 22 | 15 |  |  | 232215 | Steam and Condensate Specialties
|  |  |  | HVACPumps | 232220 | 23 | 22 | 20 |  |  | 232220 | HVAC Pumps
|  |  |  | PrefabricatedPipingSystems | 232400 | 23 | 24 | 00 |  |  | 232400 | Prefabricated Piping Systems
|  |  |  | HVACWaterTreatment | 232500 | 23 | 25 | 00 |  |  | 232500 | HVAC Water Treatment
|  |  |  | Variable_FrequencyDrives | 232923 | 23 | 29 | 23 |  |  | 232923 | Variable-Frequency Drives
|  |  |  | LowPressureDuctwork | 233113 | 23 | 31 | 13 |  |  | 233113 | Low Pressure Ductwork
|  |  |  | MediumPressureDuctwork | 233114 | 23 | 31 | 14 |  |  | 233114 | Medium Pressure Ductwork
|  |  |  | HighPressureDuctwork | 233115 | 23 | 31 | 15 |  |  | 233115 | High Pressure Ductwork
|  |  |  | AirDuctAccessories | 233300 | 23 | 33 | 00 |  |  | 233300 | Air Duct Accessories
|  |  |  | SoundAttenuators | 233319 | 23 | 33 | 19 |  |  | 233319 | Sound Attenuators
|  |  |  | HVACFans | 233400 | 23 | 34 | 00 |  |  | 233400 | HVAC Fans
|  |  |  | VehicleExhaustExtractionSystem | 233443 | 23 | 34 | 43 |  |  | 233443 | Vehicle Exhaust Extraction System
|  |  |  | AirTerminalUnits | 233600 | 23 | 36 | 00 |  |  | 233600 | Air Terminal Units
|  |  |  | AirOutletsandInlets | 233700 | 23 | 37 | 00 |  |  | 233700 | Air Outlets and Inlets
|  |  |  | HVACAirCleaningDevices | 234000 | 23 | 40 | 00 |  |  | 234000 | HVAC Air Cleaning Devices
|  |  |  | Breechings.Chimneys.andStacks | 235100 | 23 | 51 | 00 |  |  | 235100 | Breechings, Chimneys, and Stacks
|  |  |  | HeatingBoilersandAccessories | 235200 | 23 | 52 | 00 |  |  | 235200 | Heating Boilers and Accessories
|  |  |  | Fuel_FiredHeaters | 235500 | 23 | 55 | 00 |  |  | 235500 | Fuel-Fired Heaters
|  |  |  | Gas_FiredRadiantHeater | 235523 | 23 | 55 | 23 |  |  | 235523 | Gas-Fired Radiant Heater
|  |  |  | HeatExchangersforHVAC | 235700 | 23 | 57 | 00 |  |  | 235700 | Heat Exchangers for HVAC
|  |  |  | PackagedWaterChillers | 236400 | 23 | 64 | 00 |  |  | 236400 | Packaged Water Chillers
|  |  |  | CentralHVACEquipment | 237000 | 23 | 70 | 00 |  |  | 237000 | Central HVAC Equipment
|  |  |  | DecentralizedUnitaryHVACEquipment | 238100 | 23 | 81 | 00 |  |  | 238100 | Decentralized Unitary HVAC Equipment
|  |  |  | ComputerRoomAirConditioners | 238116 | 23 | 81 | 16 |  |  | 238116 | Computer Room Air Conditioners
|  |  |  | ConvectionHeatingandCoolingUnits | 238200 | 23 | 82 | 00 |  |  | 238200 | Convection Heating and Cooling Units
[5 empty] | 260000 | 26 | 00 | 00 |  |  | Division 26 - Electrical
|  |  |  | CommonWorkResultsforElectrical | 260500 | 26 | 05 | 00 |  |  | 260500 | Common Work Results for Electrical
|  |  |  | Medium_VoltageCables | 260513 | 26 | 05 | 13 |  |  | 260513 | Medium-Voltage Cables
|  |  |  | Low_VoltageElectricalPowerConductorsandCables | 260519 | 26 | 05 | 19 |  |  | 260519 | Low-Voltage Electrical Power Conductors and Cables
|  |  |  | GroundingandBondingforElectricalSystems | 260526 | 26 | 05 | 26 |  |  | 260526 | Grounding and Bonding for Electrical Systems
|  |  |  | HangersandSupportsforElectricalSystems | 260529 | 26 | 05 | 29 |  |  | 260529 | Hangers and Supports for Electrical Systems
|  |  |  | RacewayandBoxesforElectricalSystems | 260533 | 26 | 05 | 33 |  |  | 260533 | Raceway and Boxes for Electrical Systems
|  |  |  | CableTraysforElectricalSystems | 260536 | 26 | 05 | 36 |  |  | 260536 | Cable Trays for Electrical Systems
|  |  |  | UndergroundDuctsandRacewaysforElectricalSystems | 260543 | 26 | 05 | 43 |  |  | 260543 | Underground Ducts and Raceways for Electrical Systems
|  |  |  | IdentificationforElectricalSystems | 260553 | 26 | 05 | 53 |  |  | 260553 | Identification for Electrical Systems
|  |  |  | ElectricalSystemsAnalysis | 260573 | 26 | 05 | 73 |  |  | 260573 | Electrical Systems Analysis
|  |  |  | AcceptanceTesting | 260800 | 26 | 08 | 00 |  |  | 260800 | Acceptance Testing
|  |  |  | ElectricalPowerMonitoringandControl | 260913 | 26 | 09 | 13 |  |  | 260913 | Electrical Power Monitoring and Control
|  |  |  | NetworkLightingControls | 260943 | 26 | 09 | 43 |  |  | 260943 | Network Lighting Controls
|  |  |  | Substations | 261100 | 26 | 11 | 00 |  |  | 261100 | Substations
|  |  |  | CastCoilSubstationTransformers | 261216 | 26 | 12 | 16 |  |  | 261216 | Cast Coil Substation Transformers
|  |  |  | Low_VoltageTransformers | 262200 | 26 | 22 | 00 |  |  | 262200 | Low-Voltage Transformers
|  |  |  | Low_VoltageDraw_OutMetal_EnclosedSwitchgear | 262300 | 26 | 23 | 00 |  |  | 262300 | Low-Voltage Draw-Out Metal-Enclosed Switchgear
|  |  |  | SwitchboardsandPanelboards | 262400 | 26 | 24 | 00 |  |  | 262400 | Switchboards and Panel boards
|  |  |  | EnclosedBusAssemblies | 262500 | 26 | 25 | 00 |  |  | 262500 | Enclosed Bus Assemblies
|  |  |  | WiringDevices | 262726 | 26 | 27 | 26 |  |  | 262726 | Wiring Devices
|  |  |  | EnclosedSwitchesandCircuitBreakers | 262816 | 26 | 28 | 16 |  |  | 262816 | Enclosed Switches and Circuit Breakers
|  |  |  | MotorControllers | 262900 | 26 | 29 | 00 |  |  | 262900 | Motor Controllers
|  |  |  | PackagedGeneratorAssembliesforEmergencyPower | 263200 | 26 | 32 | 00 |  |  | 263200 | Packaged Generator Assemblies for Emergency Power
|  |  |  | StaticUninterruptiblePowerSupply | 263353 | 26 | 33 | 53 |  |  | 263353 | Static Uninterruptible Power Supply
|  |  |  | TransferSwitches | 263600 | 26 | 36 | 00 |  |  | 263600 | Transfer Switches
|  |  |  | Lighting | 265000 | 26 | 50 | 00 |  |  | 265000 | Lighting
|  |  |  | RoadwayLighting | 265619 | 26 | 56 | 19 |  |  | 265619 | Roadway Lighting
|  |  |  | ApronLighting | 265623 | 26 | 56 | 23 |  |  | 265623 | Apron Lighting
[5 empty] | 270000 | 27 | 00 | 00 |  |  | Division 27 - Communications
|  |  |  | CommonWorkResultsforCommunications | 270500 | 27 | 05 | 00 |  |  | 270500 | Common Work Results for Communications
|  |  |  | IdentificationforTelecommunicationSystems | 270553 | 27 | 05 | 53 |  |  | 270553 | Identification for Telecommunication Systems
|  |  |  | StructuredCabling | 271000 | 27 | 10 | 00 |  |  | 271000 | Structured Cabling
|  |  |  | NetworkEquipment | 272100 | 27 | 21 | 00 |  |  | 272100 | Network Equipment
|  |  |  | WirelessAccessPoints | 272133 | 27 | 21 | 33 |  |  | 272133 | Wireless Access Points
|  |  |  | IT_Hardware | 272200 | 27 | 22 | 00 |  |  | 272200 | IT Hardware
|  |  |  | Servers | 272219 | 27 | 22 | 19 |  |  | 272219 | Servers
|  |  |  | Desktops | 272223 | 27 | 22 | 23 |  |  | 272223 | Desktops
|  |  |  | Laptops | 272226 | 27 | 22 | 26 |  |  | 272226 | Laptops
|  |  |  | Monitors_(desktop) | 272232 | 27 | 22 | 32 |  |  | 272232 | Monitors (desktop)
|  |  |  | Monitors_(large screen) | 272234 | 27 | 22 | 34 |  |  | 272234 | Monitors (large screen)
|  |  |  | Radios,Repeaters_and_Antennas | 272236 | 27 | 22 | 36 |  |  | 272236 | Radios, Repeaters and Antennas
|  |  |  | Printers | 272413 | 27 | 24 | 13 |  |  | 272413 | Printers
|  |  |  | SoftwareAcquisition_and_Licensing | 272500 | 27 | 25 | 00 |  |  | 272500 | Software Acquisition and Licensing
|  |  |  | PhoneCommunications | 273000 | 27 | 30 | 00 |  |  | 273000 | Phone Communications
|  |  |  | Audio_VideoSystems | 274100 | 27 | 41 | 00 |  |  | 274100 | Audio-Video Systems
|  |  |  | PublicAddressandMassNotificationSystems | 275116 | 27 | 51 | 16 |  |  | 275116 | Public Address and Mass Notification Systems
|  |  |  | InternalCellular,Paging_and_AntennaSystems | 275319 | 27 | 53 | 19 |  |  | 275319 | Internal Cellular, Paging and Antenna Systems
[5 empty] | 280000 | 28 | 00 | 00 |  |  | Division 28 - Electronic Safety & Security
|  |  |  | CommonWorkResultsforElectronicSafetyandSecurity | 280500 | 28 | 05 | 00 |  |  | 280500 | Common Work Results for Electronic Safety and Security
|  |  |  | ConductorsandCablesforElectronicSafetyandSecurity | 280513 | 28 | 05 | 13 |  |  | 280513 | Conductors and Cables for Electronic Safety and Security
|  |  |  | SecurityAccessControlSystem | 281300 | 28 | 13 | 00 |  |  | 281300 | Security Access Control System
|  |  |  | VideoSurveillance(CCTVSystem) | 282300 | 28 | 23 | 00 |  |  | 282300 | Video Surveillance (CCTV System)
|  |  |  | LicensesforMonitoringinterfaces | 282316 | 28 | 23 | 16 |  |  | 282316 | Licenses for Monitoring interfaces
|  |  |  | Recorders | 282319 | 28 | 23 | 19 |  |  | 282319 | Recorders
|  |  |  | CamerasandSensors | 282329 | 28 | 23 | 29 |  |  | 282329 | Cameras and Sensors
|  |  |  | RemoteCardreaders | 281323 | 28 | 13 | 23 |  |  | 281323 | Remote Card readers
|  |  |  | FireDetectionandAlarm | 283100 | 28 | 31 | 00 |  |  | 283100 | Fire Detection and Alarm
SUBGROUP: SITE AND INFRASTRUCTURE
[5 empty] | 310000 | 31 | 00 | 00 |  |  | Division 31 - Earthwork
|  |  |  | CommonWorkResultsforEarthwork | 310500 | 31 | 05 | 00 |  |  | 310500 | Common Work Results for Earthwork
|  |  |  | SiteClearingandEarthwork | 312000 | 31 | 20 | 00 |  |  | 312000 | Site Clearing and Earthwork
|  |  |  | Trenching,Backfilling,andCompacting | 312300 | 31 | 23 | 00 |  |  | 312300 | Trenching, Backfilling, and Compacting
|  |  |  | Dewatering | 312319 | 31 | 23 | 19 |  |  | 312319 | Dewatering
|  |  |  | SoilStabilization | 313200 | 31 | 32 | 00 |  |  | 313200 | Soil Stabilization
|  |  |  | Riprap(land) | 313700 | 31 | 37 | 00 |  |  | 313700 | Riprap (land)
|  |  |  | ConcretePiles(land) | 316213 | 31 | 62 | 13 |  |  | 316213 | Concrete Piles (land)
|  |  |  | Precast,PrestressedConcretePiles(land) | 316214 | 31 | 62 | 14 |  |  | 316214 | Precast, Prestressed Concrete Piles (land)
|  |  |  | SteelPiles(land) | 316216 | 31 | 62 | 16 |  |  | 316216 | Steel Piles (land)
|  |  |  | SteelSheetPiles(land) | 316217 | 31 | 62 | 17 |  |  | 316217 | Steel Sheet Piles (land)
|  |  |  | BoredPiles(land) | 316300 | 31 | 63 | 00 |  |  | 316300 | Bored Piles (land)
|  |  |  | LightPoleBasePiles | 316329 | 31 | 63 | 29 |  |  | 316329 | Light Pole Base Piles
[5 empty] | 320000 | 32 | 00 | 00 |  |  | Division 32 - Exterior Improvements
|  |  |  | CommonWorkResultsforExteriorImprovements | 320500 | 32 | 05 | 00 |  |  | 320500 | Common Work Results for Exterior Improvements
|  |  |  | PavementRepair | 320117 | 32 | 01 | 17 |  |  | 320117 | Pavement Repair
|  |  |  | CrackSealinginFlexiblePavements | 320118 | 32 | 01 | 18 |  |  | 320118 | Crack Sealing in Flexible Pavements
|  |  |  | SealingCracksAndRepairingSurfaceImperfectionsinRigidPavements | 320128 | 32 | 01 | 28 |  |  | 320128 | Sealing Cracks & Repairing Surface Imperfections in Rigid Pavements
|  |  |  | AggregateBaseCourse | 321123 | 32 | 11 | 23 |  |  | 321123 | Aggregate Base Course
|  |  |  | Cement_TreatedBaseCourse | 321133 | 32 | 11 | 33 |  |  | 321133 | Cement-Treated Base Course
|  |  |  | AsphaltConcretePaving | 321200 | 32 | 12 | 00 |  |  | 321200 | Asphalt Concrete Paving
|  |  |  | BituminousFogSealCoat | 321236 | 32 | 12 | 36 |  |  | 321236 | Bituminous Fog Seal Coat
|  |  |  | CapeSeal | 321238 | 32 | 12 | 38 |  |  | 321238 | Cape Seal
|  |  |  | AsphaltPavementJointSealant | 321273 | 32 | 12 | 73 |  |  | 321273 | Asphalt Pavement Joint Sealant
|  |  |  | PortlandCementConcretePaving | 321300 | 32 | 13 | 00 |  |  | 321300 | Portland Cement Concrete Paving
|  |  |  | CompressionJointSealantsforRigidPavement | 321373 | 32 | 13 | 73 |  |  | 321373 | Compression Joint Sealants for Rigid Pavement
|  |  |  | BrickUnitPaving | 321416 | 32 | 14 | 16 |  |  | 321416 | Brick Unit Paving
|  |  |  | ConcreteCurbsandDriveways | 321613 | 32 | 16 | 13 |  |  | 321613 | Concrete Curbs and Driveways
|  |  |  | ConcreteMowStripandControllerBase | 321614 | 32 | 16 | 14 |  |  | 321614 | Concrete Mow Strip and Controller Base
|  |  |  | ConcreteSidewalk | 321615 | 32 | 16 | 15 |  |  | 321615 | Concrete Sidewalk
|  |  |  | PavementMarkings | 321723 | 32 | 17 | 23 |  |  | 321723 | Pavement Markings
|  |  |  | Chain_LinkFencesandGates | 323113 | 32 | 31 | 13 |  |  | 323113 | Chain-Link Fences and Gates
|  |  |  | AutomaticGateOperatorandControl | 323114 | 32 | 31 | 14 |  |  | 323114 | Automatic Gate Operator and Control
|  |  |  | PlantingIrrigation | 328400 | 32 | 84 | 00 |  |  | 328400 | Planting Irrigation
|  |  |  | LandscapeMaintenance(forPDXprojects) | 329000 | 32 | 90 | 00 |  |  | 329000 | Landscape Maintenance (for PDX projects)
|  |  |  | SoilPreparation | 329113 | 32 | 91 | 13 |  |  | 329113 | Soil Preparation
|  |  |  | LandscapeGrading | 329119 | 32 | 91 | 19 |  |  | 329119 | Landscape Grading
|  |  |  | ClearingandSeeding | 329200 | 32 | 92 | 00 |  |  | 329200 | Clearing and Seeding
|  |  |  | Seeding | 329219 | 32 | 92 | 19 |  |  | 329219 | Seeding
|  |  |  | Seeding(Airfield) | 329219 | 32 | 92 | 19 |  |  | 329219 | Seeding (Airfield)
|  |  |  | Sodding | 329223 | 32 | 92 | 23 |  |  | 329223 | Sodding
|  |  |  | Trees.Shrubs.andGroundCovers | 329300 | 32 | 93 | 00 |  |  | 329300 | Trees, Shrubs, and Ground Covers
[5 empty] | 330000 | 33 | 00 | 00 |  |  | Division 33 - Utilities
|  |  |  | CommonWorkResultsforUtilities | 330500 | 33 | 05 | 00 |  |  | 330500 | Common Work Results for Utilities
|  |  |  | UtilityStructures | 330516 | 33 | 05 | 16 |  |  | 330516 | Utility Structures
|  |  |  | SiteWaterUtilityDistributionPlumbing | 331116 | 33 | 11 | 16 |  |  | 331116 | Site Water Utility Distribution Plumbing
|  |  |  | SanitaryUtilitySeweragePiping | 333100 | 33 | 31 | 00 |  |  | 333100 | Sanitary Utility Sewerage Piping
|  |  |  | SanitarySewerPumpStation | 333213 | 33 | 32 | 13 |  |  | 333213 | Sanitary Sewer Pump Station
|  |  |  | StormUtilityDrainagePiping | 334100 | 33 | 41 | 00 |  |  | 334100 | Storm Utility Drainage Piping
[5 empty] | 340000 | 34 | 00 | 00 |  |  | Division 34 - Transportation
|  |  |  | CommonWorkResultsforRailways | 340523 | 34 | 05 | 23 |  |  | 340523 | Common Work Results for Railways
|  |  |  | RailTurnouts | 340524 | 34 | 05 | 24 |  |  | 340524 | Rail Turnouts
|  |  |  | RailWalkways | 340526 | 34 | 05 | 26 |  |  | 340526 | Rail Walkways
|  |  |  | TrackRails | 341113 | 34 | 11 | 13 |  |  | 341113 | Track Rails
|  |  |  | WeldedTrackRails | 341116 | 34 | 11 | 16 |  |  | 341116 | Welded Track Rails
|  |  |  | TrackRailBallast | 341126 | 34 | 11 | 26 |  |  | 341126 | Track Rail Ballast
|  |  |  | TrackAppurtenancesandAccessories | 341193 | 34 | 11 | 93 |  |  | 341193 | Track Appurtenances and Accessories
|  |  |  | TrafficSignals | 344113 | 34 | 41 | 13 |  |  | 344113 | Traffic Signals
|  |  |  | RailwaySignals | 344213 | 34 | 42 | 13 |  |  | 344213 | Railway Signals
|  |  |  | AirfieldLighting | 344300 | 34 | 43 | 00 |  |  | 344300 | Airfield Lighting
|  |  |  | AircraftGuidanceSignage | 344302 | 34 | 43 | 2 |  |  | 344302 | Aircraft Guidance Signage
|  |  |  | GuardPosts | 347113 | 34 | 71 | 13 |  |  | 347113 | Guard Posts
|  |  |  | RailwayEquipment | 347600 | 34 | 76 | 00 |  |  | 347600 | Railway Equipment
|  |  |  | RoadwayCrossingControlEquipment | 347613 | 34 | 76 | 13 |  |  | 347613 | Roadway Crossing Control Equipment
|  |  |  | PassengerLoadingBridges | 347713 | 34 | 77 | 13 |  |  | 347713 | Passenger Loading Bridges
|  |  |  | BaggageConveyors | 347716 | 34 | 77 | 16 |  |  | 347716 | Baggage Conveyors
[5 empty] | 350000 | 35 | 00 | 00 |  |  | Division 35 - Waterway & Marine
|  |  |  | CommonWorkResultsforWaterway&MarineConstruction | 350500 | 35 | 05 | 00 |  |  | 350500 | Common Work Results for Waterway & Marine Construction
|  |  |  | Dredging | 352023 | 35 | 20 | 23 |  |  | 353200 | Woody Debris Structures
|  |  |  | WoodyDebrisStructures | 353200 | 35 | 32 | 00 |  |  | 354000 | Waterway Construction
|  |  |  | WaterwayConstruction | 354000 | 35 | 40 | 00 |  |  | 354237 | Riprap Bank Protection (marine)
|  |  |  | RiprapBankProtection(marine) | 354237 | 35 | 42 | 37 |  |  | 355912 | Heavy Timber Pier Construction
|  |  |  | HeavyTimberPierConstruction | 355912 | 35 | 59 | 12 |  |  | 355913 | Timber Fender Piles
|  |  |  | TimberFenderPiles | 355913 | 35 | 59 | 13 |  |  | 355914 | Marine Fenders
|  |  |  | MarineFenders | 355914 | 35 | 59 | 14 |  |  | 356213 | Concrete Piles (marine)
|  |  |  | ConcretePiles(marine) | 356213 | 35 | 62 | 13 |  |  | 356214 | Precast, Prestressed Concrete Piles (marine)
|  |  |  | Precast.PrestressedConcretePiles(marine) | 356214 | 35 | 62 | 14 |  |  | 356216 | Steel Pipe Piles (marine)
|  |  |  | SteelPipePiles(marine) | 356216 | 35 | 62 | 16 |  |  | 356217 | Steel Sheet Piles (marine)
|  |  |  | SteelSheetPiles(marine) | 356217 | 35 | 62 | 17 |  |  | 352023 | Dredging
SUBGROUP: PROCESS EQUIPMENT
[5 empty] | 410000 | 41 | 00 | 00 |  |  | Division 41 - Material Proc. & Handling Equip.
|  |  |  | Cranes | 412213 | 41 | 22 | 13 |  |  | 412213 | Cranes
|  |  |  | CraneRail | 412214 | 41 | 22 | 14 |  |  | 412214 | Crane Rail
SUBGROUP: FAA CONSTRUCTION
[5 empty] | 510000 | 51 | 0 | 0 |  |  | Division 51 - Earthwork
|  |  |  | Surface Preparation (P-101) | 510101 | 51 | 1 | 1 |  |  | 510101 | Surface Preparation (P-101)
|  |  |  | Clearing and Grubbing (P-151) | 510151 | 51 | 1 | 51 |  |  | 510151 | Clearing and Grubbing (P-151)
|  |  |  | Excavation and Embankment (P-152) | 510152 | 51 | 1 | 52 |  |  | 510152 | Excavation and Embankment (P-152)
|  |  |  | Controlled Low-Strength Material (P-153) | 510153 | 51 | 1 | 53 |  |  | 510153 | Controlled Low-Strength Material (P-153)
|  |  |  | Subbase Course (P-154) | 510154 | 51 | 1 | 54 |  |  | 510154 | Sub base Course (P-154)
|  |  |  | Lime-Treated Subgrade (P-155) | 510155 | 51 | 1 | 55 |  |  | 510155 | Lime-Treated Sub grade (P-155)
|  |  |  | Temporary Air & Water Pollution, Soil Erosion, & Siltation Control (P-156) | 510156 | 51 | 1 | 56 |  |  | 510156 | Temporary Air & Water Pollution, Soil Erosion, & Siltation Control (P-156)
|  |  |  | Fly Ash Treated Subgrade (P-158) | 510158 | 51 | 1 | 58 |  |  | 510158 | Fly Ash Treated Sub grade (P-158)
|  |  |  | Geotextile (P-161) | 510161 | 51 | 1 | 61 |  |  | 510161 | Geotextile (P-161)
[5 empty] | 520000 | 52 | 0 | 0 |  |  | Division 52 - Flexible Base Courses
|  |  |  | Aggregate Base Course (P-208) | 520208 | 52 | 2 | 8 |  |  | 520208 | Aggregate Base Course (P-208)
|  |  |  | Crushed Aggregate Base Course (P-209) | 520209 | 52 | 2 | 9 |  |  | 520209 | Crushed Aggregate Base Course (P-209)
|  |  |  | Caliche Base Course (P-210) | 520210 | 52 | 2 | 10 |  |  | 520210 | Caliche Base Course (P-210)
|  |  |  | Lime Rock Base Course (P-211) | 520211 | 52 | 2 | 11 |  |  | 520211 | Lime Rock Base Course (P-211)
|  |  |  | Shell Base Course (P-212) | 520212 | 52 | 2 | 12 |  |  | 520212 | Shell Base Course (P-212)
|  |  |  | Sand-Clay Base Course (P-213) | 520213 | 52 | 2 | 13 |  |  | 520213 | Sand-Clay Base Course (P-213)
|  |  |  | Aggregate-Turf Pavement (P-217) | 520217 | 52 | 2 | 17 |  |  | 520217 | Aggregate-Turf Pavement (P-217)
[5 empty] | 530000 | 53 | 0 | 0 |  |  | Division 53 - Rigid Base Courses
|  |  |  | Soil Cement Base Course (P-301) | 530301 | 53 | 3 | 1 |  |  | 530301 | Soil Cement Base Course (P-301)
|  |  |  | Cement Treated Base Course (P-304) | 530304 | 53 | 3 | 4 |  |  | 530304 | Cement Treated Base Course (P-304)
|  |  |  | Econocrete Subbase Course (P-306) | 530306 | 53 | 3 | 6 |  |  | 530306 | Econocrete Sub base Course (P-306)
[5 empty] | 540000 | 54 | 0 | 0 |  |  | Division 54 - Flexible Surface Courses
|  |  |  | (Superpave™) Plant Mix Bituminous Pavements (P-401sp) | 540401 | 54 | 4 | 1 |  |  | 540401 | (Superpave™) Plant Mix Bituminous Pavements (P-401sp)
|  |  |  | Porous Friction Course (P-402) | 540402 | 54 | 4 | 2 |  |  | 540402 | Porous Friction Course (P-402)
|  |  |  | (Superpave™) Plant Mix Bituminous Bases (P-403sp) | 540403 | 54 | 4 | 3 |  |  | 540403 | (Superpave™) Plant Mix Bituminous Bases (P-403sp)
[5 empty] | 550000 | 55 | 0 | 0 |  |  | Division 55 - Rigid Pavement
|  |  |  | Portland Cement Concrete Pavement (P-501) | 550501 | 55 | 5 | 1 |  |  | 550501 | Portland Cement Concrete Pavement (P-501)
[5 empty] | 560000 | 56 | 0 | 0 |  |  | Division 56 - Miscellaneous
|  |  |  | Bituminous Prime Coat (P-602) | 560602 | 56 | 6 | 2 |  |  | 560602 | Bituminous Prime Coat (P-602)
|  |  |  | Bituminous Tack Coat (P-603) | 560603 | 56 | 6 | 3 |  |  | 560603 | Bituminous Tack Coat (P-603)
|  |  |  | Compression Joint Seals for Concrete Pavements (Regional) (P-604) | 560604 | 56 | 6 | 4 |  |  | 560604 | Compression Joint Seals for Concrete Pavements (Regional) (P-604)
|  |  |  | Joint Sealing Filler (P-605) | 560605 | 56 | 6 | 5 |  |  | 560605 | Joint Sealing Filler (P-605)
|  |  |  | Adhesive Compounds (P-606) | 560606 | 56 | 6 | 6 |  |  | 560606 | Adhesive Compounds (P-606)
|  |  |  | [ Polymerized ] Bituminous Fog Seal Coat (P-609) | 560609 | 56 | 6 | 9 |  |  | 560609 | [ Polymerized ] Bituminous Fog Seal Coat (P-609)
|  |  |  | Structural Portland Cement Concrete (P-610) | 560610 | 56 | 6 | 10 |  |  | 560610 | Structural Portland Cement Concrete (P-610)
|  |  |  | Runway and Taxiway Painting (P-620) | 560620 | 56 | 6 | 20 |  |  | 560620 | Runway and Taxiway Painting (P-620)
|  |  |  | Saw-Cut Grooves (P-621) | 560621 | 56 | 6 | 21 |  |  | 560621 | Saw-Cut Grooves (P-621)
|  |  |  | Coal-Tar Pitch Emulsion Sealcoat (P-625) | 560625 | 56 | 6 | 25 |  |  | 560625 | Coal-Tar Pitch Emulsion Sealcoat (P-625)
|  |  |  | Emulsified Asphalt Slurry Seal Surface Treatment (P-626) | 560626 | 56 | 6 | 26 |  |  | 560626 | Emulsified Asphalt Slurry Seal Surface Treatment (P-626)
|  |  |  | Refined Coal Tar Emulsion s/Additives, Slurry Seal Surface Treatment (P-631) | 560631 | 56 | 6 | 31 |  |  | 560631 | Refined Coal Tar Emulsion s/Additives, Slurry Seal Surface Treatment (P-631)
[5 empty] | 570000 | 57 | 0 | 0 |  |  | Division 57 - Fencing
|  |  |  | Wire Fence with Wood Posts (F-160) | 570160 | 57 | 1 | 60 |  |  | 570160 | Wire Fence with Wood Posts (F-160)
|  |  |  | Wire Fence with Steel Posts (F-161) | 570161 | 57 | 1 | 61 |  |  | 570161 | Wire Fence with Steel Posts (F-161)
|  |  |  | Chain Link Fences (F-162) | 570162 | 57 | 1 | 62 |  |  | 570162 | Chain Link Fences (F-162)
|  |  |  | Wild-Life Deterrent Fence (F-163) | 570163 | 57 | 1 | 63 |  |  | 570163 | Wild-Life Deterrent Fence (F-163)
[5 empty] | 580000 | 58 | 0 | 0 |  |  | Division 58 - Drainage
|  |  |  | Pipe for Storm Drains and Culverts (D-701) | 580701 | 58 | 7 | 1 |  |  | 580701 | Pipe for Storm Drains and Culverts (D-701)
|  |  |  | Slotted Drains (D-702) | 580702 | 58 | 7 | 2 |  |  | 580702 | Slotted Drains (D-702)
|  |  |  | Pipe Underdrains for Airports (D-705) | 580705 | 58 | 7 | 5 |  |  | 580705 | Pipe Under drains for Airports (D-705)
|  |  |  | Manholes, Catch Basins, Inlets, and Inspection Holes (D-751) | 580751 | 58 | 7 | 51 |  |  | 580751 | Manholes, Catch Basins, Inlets, and Inspection Holes (D-751)
|  |  |  | Concrete Culverts, Headwalls, & Misc. Drainage Structures (D-752) | 580752 | 58 | 7 | 52 |  |  | 580752 | Concrete Culverts, Headwalls, & Misc. Drainage Structures (D-752)
|  |  |  | Concrete Paved Gutters, Ditches, and Flumes (D-754) | 580754 | 58 | 7 | 54 |  |  | 580754 | Concrete Paved Gutters, Ditches, and Flumes (D-754)
[5 empty] | 590000 | 59 | 0 | 0 |  |  | Division 59 - Turfing
|  |  |  | Seeding (T-901) | 590901 | 59 | 9 | 1 |  |  | 590901 | Seeding (T-901)
|  |  |  | Sprigging (T-903) | 590903 | 59 | 9 | 3 |  |  | 590903 | Sprigging (T-903)
|  |  |  | Sodding (T-904) | 590904 | 59 | 9 | 4 |  |  | 590904 | Sodding (T-904)
|  |  |  | Topsoiling (T-905) | 590905 | 59 | 9 | 5 |  |  | 590905 | Topsoiling (T-905)
|  |  |  | Tilling (T-907) | 590907 | 59 | 9 | 7 |  |  | 590907 | Tilling (T-907)
|  |  |  | Mulching (T-908) | 590908 | 59 | 9 | 8 |  |  | 590908 | Mulching (T-908)
[5 empty] | 600000 | 60 | 0 | 0 |  |  | Division 60 - Lighting Installation
|  |  |  | Airport Rotating Beacon (L-101) | 600101 | 60 | 1 | 1 |  |  | 600101 | Airport Rotating Beacon (L-101)
|  |  |  | Airport Hazard Beacon (L-102) | 600102 | 60 | 1 | 2 |  |  | 600102 | Airport Hazard Beacon (L-102)
|  |  |  | Airport Beacon Towers (L-103) | 600103 | 60 | 1 | 3 |  |  | 600103 | Airport Beacon Towers (L-103)
|  |  |  | Airport Wind Cones (L-107) | 600107 | 60 | 1 | 7 |  |  | 600107 | Airport Wind Cones (L-107)
|  |  |  | Airport Underground Cable (L-108) | 600108 | 60 | 1 | 8 |  |  | 600108 | Airport Underground Cable (L-108)
|  |  |  | Airport Transformer Vault and Equipment (L-109) | 600109 | 60 | 1 | 9 |  |  | 600109 | Airport Transformer Vault and Equipment (L-109)
|  |  |  | Airport Underground Electrical Duct (L-110) | 600110 | 60 | 1 | 10 |  |  | 600110 | Airport Underground Electrical Duct (L-110)
|  |  |  | Electrical Manholes and Junction Structures (L-115) | 600115 | 60 | 1 | 15 |  |  | 600115 | Electrical Manholes and Junction Structures (L-115)
|  |  |  | Airport Obstruction Lights (L-119) | 600119 | 60 | 1 | 19 |  |  | 600119 | Airport Obstruction Lights (L-119)

## Soft Cost Codes (hidden)
Shrt | Division | Description | Lookup | SubType | Cost Code | Seg1 | Seg2 | Seg3 | SubType | Cost Code | Seg1 | Seg2 | Seg3
SIT | Division 1 | Channel_Deepening_Site_Channel_Deepening | Channel_Deepening_Site_Channel_Deepening_Acquisition | Acquisition | 160000 | 16 | 0 | 0 | ProjectAdminMgmt | 100000 | 10 | 0 | 0
SIT | Division 1 | Channel_Deepening_Site_Channel_Deepening |  | General | 161000 | 16 | 10 | 0 | General | 101000 | 10 | 10 | 0
SIT | Division 1 | Channel_Deepening_Site_Channel_Deepening |  | Demolition | 161200 | 16 | 12 | 0 | ProjectAdminandMgmt | 100000 | 10 | 0 | 0
SIT | Division 1 | Channel_Deepening_Site_Channel_Deepening |  | RelocationAssistance | 161300 | 16 | 13 | 0 | LandAcquisition | 101600 | 10 | 16 | 0
SIT | Division 1 | Channel_Deepening_Site_Channel_Deepening |  | Appraisals | 161400 | 16 | 14 | 0 | FinancialSupport | 101700 | 10 | 17 | 0
SIT | Division 1 | Channel_Deepening_Site_Channel_Deepening |  | EnvironmentalAssessments | 161500 | 16 | 15 | 0 | LegislativeFunding | 101800 | 10 | 18 | 0
SIT | Division 1 | Channel_Deepening_Site_Channel_Deepening |  | Condemnation | 161600 | 16 | 16 | 0 | Agreements | 101900 | 10 | 19 | 0
SIT | Division 1 | Channel_Deepening_Site_Channel_Deepening |  | Inspection | 161700 | 16 | 17 | 0 | ProjectMgmt | 101200 | 10 | 12 | 0
SIT | Division 1 | Channel_Deepening_Site_Channel_Deepening |  | TitleWork | 161800 | 16 | 18 | 0 | UplandSourceControlProgramCoordination | 101010 | 10 | 10 | 10
SIT | Division 1 | Channel_Deepening_Site_Channel_Deepening |  | Survey | 162200 | 16 | 22 | 0 | ProgramManagement | 101020 | 10 | 10 | 20
SIT | Division 1 | Channel_Deepening_Site_Channel_Deepening | Channel_Deepening_Site_Channel_Deepening_Permitting | Permitting | 200000 | 20 | 0 | 0 | Meetings | 101100 | 10 | 11 | 0
SIT | Division 1 | Channel_Deepening_Site_Channel_Deepening |  | General | 201000 | 20 | 10 | 0 | Development | 101300 | 10 | 13 | 0
SIT | Division 1 | Channel_Deepening_Site_Channel_Deepening | Channel_Deepening_Site_Channel_Deepening_Contingency | Contingency | 790000 | 79 | 0 | 0 | Design | 101400 | 10 | 14 | 0
UPL | Division 1 | Upland_Control_Sites_Lower_Willamette | Upland_Control_Sites_Lower_Willamette_ProjectAdminMgmt | ProjectAdminMgmt | 100000 | 10 | 0 | 0 | Construction | 101500 | 10 | 15 | 0
UPL | Division 1 | Upland_Control_Sites_Lower_Willamette |  | General | 101000 | 10 | 10 | 0 | Develop | 101300 | 10 | 13 | 0
UPL | Division 1 | Upland_Control_Sites_Lower_Willamette | Upland_Control_Sites_Lower_Willamette_Design | Design | 140000 | 14 | 0 | 0 | BusinessContinuity | 110000 | 11 | 0 | 0
UPL | Division 1 | Upland_Control_Sites_Lower_Willamette |  | OutsideDesignServices | 141010 | 14 | 10 | 10 | General | 111000 | 11 | 10 | 0
UPL | Division 1 | Upland_Control_Sites_Lower_Willamette |  | TreatabilityStudy_PilotTesting | 141300 | 14 | 13 | 0 | AnalysisandRequirementsDefinition | 120000 | 12 | 0 | 0
UPL | Division 1 | Upland_Control_Sites_Lower_Willamette |  | RemedialDesign | 141400 | 14 | 14 | 0 | General | 121000 | 12 | 10 | 0
UPL | Division 1 | Upland_Control_Sites_Lower_Willamette |  | Enviornmental | 141600 | 14 | 16 | 0 | DevelopandIssueRFP | 121100 | 12 | 11 | 0
UPL | Division 1 | Upland_Control_Sites_Lower_Willamette |  | PEDesign | 141700 | 14 | 17 | 0 | SelectVendor | 121200 | 12 | 12 | 0
UPL | Division 1 | Upland_Control_Sites_Lower_Willamette |  | ITDesignSupport | 142600 | 14 | 26 | 0 | Security | 130000 | 13 | 0 | 0
UPL | Division 1 | Upland_Control_Sites_Lower_Willamette |  | MaintenanceDesignSupport | 142700 | 14 | 27 | 0 | General | 131000 | 13 | 10 | 0
UPL | Division 1 | Upland_Control_Sites_Lower_Willamette | Upland_Control_Sites_Lower_Willamette_Planning | Planning | 150000 | 15 | 0 | 0 | Design | 140000 | 14 | 0 | 0
UPL | Division 1 | Upland_Control_Sites_Lower_Willamette |  | AssessmentPlanning | 151100 | 15 | 11 | 0 | OutsideDesignServices | 141010 | 14 | 10 | 10
UPL | Division 1 | Upland_Control_Sites_Lower_Willamette |  | PreliminaryAssessment | 151110 | 15 | 11 | 10 | TreatabilityStudy_PilotTesting | 141300 | 14 | 13 | 0
UPL | Division 1 | Upland_Control_Sites_Lower_Willamette |  | SiteInvestigation | 151200 | 15 | 12 | 0 | RemedialDesign | 141400 | 14 | 14 | 0
UPL | Division 1 | Upland_Control_Sites_Lower_Willamette |  | RemedialInvestigation | 151300 | 15 | 13 | 0 | Enviornmental | 141600 | 14 | 16 | 0
UPL | Division 1 | Upland_Control_Sites_Lower_Willamette |  | CargillOU1 | 151310 | 15 | 13 | 10 | PEDesign | 141700 | 14 | 17 | 0
UPL | Division 1 | Upland_Control_Sites_Lower_Willamette |  | OU2 | 151320 | 15 | 13 | 20 | ITDesignSupport | 142600 | 14 | 26 | 0
UPL | Division 1 | Upland_Control_Sites_Lower_Willamette |  | FeasibilityStudy | 151600 | 15 | 16 | 0 | MaintenanceDesignSupport | 142700 | 14 | 27 | 0
UPL | Division 1 | Upland_Control_Sites_Lower_Willamette |  | CulturalResources | 151700 | 15 | 17 | 0 | Environmental | 141600 | 14 | 16 | 0
UPL | Division 1 | Upland_Control_Sites_Lower_Willamette | Upland_Control_Sites_Lower_Willamette_Development | Development | 170000 | 17 | 0 | 0 | Survey | 141800 | 14 | 18 | 0
UPL | Division 1 | Upland_Control_Sites_Lower_Willamette |  | OutsideDesignServices | 171510 | 17 | 15 | 10 | CAD | 142200 | 14 | 22 | 0
UPL | Division 1 | Upland_Control_Sites_Lower_Willamette | Upland_Control_Sites_Lower_Willamette_Implementation | Implementation | 180000 | 18 | 0 | 0 | BidPackage | 142300 | 14 | 23 | 0
UPL | Division 1 | Upland_Control_Sites_Lower_Willamette |  | RemedialAction | 181000 | 18 | 10 | 0 | General | 141000 | 14 | 10 | 0
UPL | Division 1 | Upland_Control_Sites_Lower_Willamette |  | OandM_Systems | 181100 | 18 | 11 | 0 | ESAReconsulation | 142400 | 14 | 24 | 0
UPL | Division 1 | Upland_Control_Sites_Lower_Willamette |  | OandM_Monitoring | 181200 | 18 | 12 | 0 | UtilityRelocations | 142500 | 14 | 25 | 0
UPL | Division 1 | Upland_Control_Sites_Lower_Willamette | Upland_Control_Sites_Lower_Willamette_Construction | Construction | 190000 | 19 | 0 | 0 | Restoration | 141500 | 14 | 15 | 0
UPL | Division 1 | Upland_Control_Sites_Lower_Willamette |  | OutsideConstructionService | 191810 | 19 | 18 | 10 | RestorationPlanandDev,includingDesign | 141510 | 14 | 15 | 10
UPL | Division 1 | Upland_Control_Sites_Lower_Willamette | Upland_Control_Sites_Lower_Willamette_Legal_Regulatory | Legal_Regulatory | 230000 | 23 | 0 | 0 | IdentityDevelopment | 142900 | 14 | 29 | 0
UPL | Division 1 | Upland_Control_Sites_Lower_Willamette |  | Pre_LitigationPreparation | 231300 | 23 | 13 | 0 | PrintMedia | 143000 | 14 | 30 | 0
UPL | Division 1 | Upland_Control_Sites_Lower_Willamette |  | LitigationDefense | 231400 | 23 | 14 | 0 | Event | 143100 | 14 | 31 | 0
UPL | Division 1 | Upland_Control_Sites_Lower_Willamette |  | ClosureReplort_NFA | 231600 | 23 | 16 | 0 | Website | 143200 | 14 | 32 | 0
UPL | Division 1 | Upland_Control_Sites_Lower_Willamette |  | EnforcementDocuments | 231700 | 23 | 17 | 0 | Photography | 143300 | 14 | 33 | 0
UPL | Division 1 | Upland_Control_Sites_Lower_Willamette |  | FiveYearReview | 231800 | 23 | 18 | 0 | MultimediaPresentations | 143400 | 14 | 34 | 0
UPL | Division 1 | Upland_Control_Sites_Lower_Willamette |  | TenantCleanupOversight | 232900 | 23 | 29 | 0 | SpecificationDevelopment | 141100 | 14 | 11 | 0
UPL | Division 1 | Upland_Control_Sites_Lower_Willamette | Upland_Control_Sites_Lower_Willamette_PublicRecordsRequest | PublicRecordsRequest | 240000 | 24 | 0 | 0 | RandD | 141200 | 14 | 12 | 0
UPL | Division 1 | Upland_Control_Sites_Lower_Willamette |  | General | 241000 | 24 | 10 | 0 | DrawingandDevelopment | 141900 | 14 | 19 | 0
UPL | Division 1 | Upland_Control_Sites_Lower_Willamette | Upland_Control_Sites_Lower_Willamette_Outreach | Outreach | 250000 | 25 | 0 | 0 | PublicAffairs | 142000 | 14 | 20 | 0
UPL | Division 1 | Upland_Control_Sites_Lower_Willamette |  | General | 251000 | 25 | 10 | 0 | Construction_InspectionSupport | 142100 | 14 | 21 | 0
UPL | Division 1 | Upland_Control_Sites_Lower_Willamette |  | CommunityRelations | 251010 | 25 | 10 | 10 | ITDesignSupportContract | 142600 | 14 | 26 | 0
UPL | Division 1 | Upland_Control_Sites_Lower_Willamette | Upland_Control_Sites_Lower_Willamette_CostRecovery | CostRecovery | 300000 | 30 | 0 | 0 | Restore.PlanandDev,Incl.Des. | 141510 | 14 | 15 | 10
UPL | Division 1 | Upland_Control_Sites_Lower_Willamette |  | PRPPursuit | 301000 | 30 | 10 | 0 | Planning | 150000 | 15 | 0 | 0
UPL | Division 1 | Upland_Control_Sites_Lower_Willamette | Upland_Control_Sites_Lower_Willamette_Payments | Payments | 320000 | 32 | 0 | 0 | AssessmentPlanning | 151100 | 15 | 11 | 0
UPL | Division 1 | Upland_Control_Sites_Lower_Willamette |  | PRPGroupPayments | 321100 | 32 | 11 | 0 | PreliminaryAssessment | 151110 | 15 | 11 | 10
UPL | Division 1 | Upland_Control_Sites_Lower_Willamette |  | OversightCosts | 321300 | 32 | 13 | 0 | SiteInvestigation | 151200 | 15 | 12 | 0
UPL | Division 1 | Upland_Control_Sites_Lower_Willamette |  | EPA | 321310 | 32 | 13 | 10 | RemedialInvestigation | 151300 | 15 | 13 | 0
UPL | Division 1 | Upland_Control_Sites_Lower_Willamette |  | DEQ | 321320 | 32 | 13 | 20 | CargillOU1 | 151310 | 15 | 13 | 10
UPL | Division 1 | Upland_Control_Sites_Lower_Willamette |  | Tribes | 321330 | 32 | 13 | 30 | OU2 | 151320 | 15 | 13 | 20
UPL | Division 1 | Upland_Control_Sites_Lower_Willamette |  | Trustees | 321340 | 32 | 13 | 40 | FeasibilityStudy | 151600 | 15 | 16 | 0
UPL | Division 1 | Upland_Control_Sites_Lower_Willamette | Upland_Control_Sites_Lower_Willamette_Contingency | Contingency | 790000 | 79 | 0 | 0 | CulturalResources | 151700 | 15 | 17 | 0
UPL | Division 1 | Upland_Control_Sites_Lower_Willamette |  | CASS | 909000 | 90 | 90 | 0 | Strategy_Planning | 151120 | 15 | 11 | 20
WIK | Division 1 | Work_in_Kind_Channel_Deepening | Work_in_Kind_Channel_Deepening_ProjectAdminandMgmt | ProjectAdminandMgmt | 100000 | 10 | 0 | 0 | InjuryAssessment | 151130 | 15 | 11 | 30
WIK | Division 1 | Work_in_Kind_Channel_Deepening |  | General | 101000 | 10 | 10 | 0 | General | 151000 | 15 | 10 | 0
WIK | Division 1 | Work_in_Kind_Channel_Deepening | Work_in_Kind_Channel_Deepening_Design | Design | 140000 | 14 | 0 | 0 | CapacityAnalysis | 151140 | 15 | 11 | 40
WIK | Division 1 | Work_in_Kind_Channel_Deepening |  | Environmental | 141600 | 14 | 16 | 0 | EnvironmentalAssessment_ActionPlan | 151150 | 15 | 11 | 50
WIK | Division 1 | Work_in_Kind_Channel_Deepening |  | Survey | 141800 | 14 | 18 | 0 | Forecasts | 151400 | 15 | 14 | 0
WIK | Division 1 | Work_in_Kind_Channel_Deepening |  | CAD | 142200 | 14 | 22 | 0 | Cargo | 151410 | 15 | 14 | 10
WIK | Division 1 | Work_in_Kind_Channel_Deepening |  | BidPackage | 142300 | 14 | 23 | 0 | FutureTechnology | 151420 | 15 | 14 | 20
WIK | Division 1 | Work_in_Kind_Channel_Deepening | Work_in_Kind_Channel_Deepening_Construction | Construction | 190000 | 19 | 0 | 0 | Capital | 151430 | 15 | 14 | 30
WIK | Division 1 | Work_in_Kind_Channel_Deepening |  | Contract | 191000 | 19 | 10 | 0 | AlternativesDefinition | 151500 | 15 | 15 | 0
WIK | Division 1 | Work_in_Kind_Channel_Deepening |  | EquipmentContracts | 191100 | 19 | 11 | 0 | Facility | 151510 | 15 | 15 | 10
WIK | Division 1 | Work_in_Kind_Channel_Deepening |  | Management | 191200 | 19 | 12 | 0 | MasterPlan | 151520 | 15 | 15 | 20
WIK | Division 1 | Work_in_Kind_Channel_Deepening |  | Inspection | 191300 | 19 | 13 | 0 | TransportationImprovement | 151530 | 15 | 15 | 30
WIK | Division 1 | Work_in_Kind_Channel_Deepening |  | Testing | 191400 | 19 | 14 | 0 | IdentityDevelopment | 152000 | 15 | 20 | 0
WIK | Division 1 | Work_in_Kind_Channel_Deepening |  | Environmental | 191600 | 19 | 16 | 0 | PrintMedia | 152100 | 15 | 21 | 0
WIK | Division 1 | Work_in_Kind_Channel_Deepening |  | EngineeringSupport | 191800 | 19 | 18 | 0 | Event | 152200 | 15 | 22 | 0
WIK | Division 1 | Work_in_Kind_Channel_Deepening |  | NavigationSupport | 192100 | 19 | 21 | 0 | Website | 152300 | 15 | 23 | 0
WIK | Division 1 | Work_in_Kind_Channel_Deepening |  | TenantAccess | 192200 | 19 | 22 | 0 | Photography | 152400 | 15 | 24 | 0
WIK | Division 1 | Work_in_Kind_Channel_Deepening |  | OperatingDeptSupport | 192300 | 19 | 23 | 0 | MultimediaPresentations | 152500 | 15 | 25 | 0
WIK | Division 1 | Work_in_Kind_Channel_Deepening | Work_in_Kind_Channel_Deepening_Permitting | Permitting | 200000 | 20 | 0 | 0 | GeneralStormWaterPipes | 151240 | 15 | 12 | 40
WIK | Division 1 | Work_in_Kind_Channel_Deepening |  | General | 201000 | 20 | 10 | 0 | TechnicalSupport | 151900 | 15 | 19 | 0
WIK | Division 1 | Work_in_Kind_Channel_Deepening | Work_in_Kind_Channel_Deepening_Survey | Survey | 210000 | 21 | 0 | 0 | EE(SiteCharacterization) | 151210 | 15 | 12 | 10
WIK | Division 1 | Work_in_Kind_Channel_Deepening |  | Reconnaissance | 211000 | 21 | 10 | 0 | EE_CAWorkPlan | 151220 | 15 | 12 | 20
WIK | Division 1 | Work_in_Kind_Channel_Deepening |  | Design | 211100 | 21 | 11 | 0 | EE_CAPreparation | 151230 | 15 | 12 | 30
WIK | Division 1 | Work_in_Kind_Channel_Deepening |  | CAD | 211300 | 21 | 13 | 0 | Assessment_Planning | 151100 | 15 | 11 | 0
WIK | Division 1 | Work_in_Kind_Channel_Deepening |  | BidPackage | 211400 | 21 | 14 | 0 | Environ.Assess_ActionPlan | 151150 | 15 | 11 | 50
WIK | Division 1 | Work_in_Kind_Channel_Deepening |  | EngineeringSupport | 211500 | 21 | 15 | 0 | TransportationAnalysis | 151800 | 15 | 18 | 0
WIK | Division 1 | Work_in_Kind_Channel_Deepening |  | OperatingDeptSupport | 211600 | 21 | 16 | 0 | Acquisition | 160000 | 16 | 0 | 0
WIK | Division 1 | Work_in_Kind_Channel_Deepening | Work_in_Kind_Channel_Deepening_Maintenance | Maintenance | 220000 | 22 | 0 | 0 | General | 161000 | 16 | 10 | 0
WIK | Division 1 | Work_in_Kind_Channel_Deepening |  | Environmental | 221000 | 22 | 10 | 0 | Demolition | 161200 | 16 | 12 | 0
WIK | Division 1 | Work_in_Kind_Channel_Deepening |  | EngineeringSupport | 221100 | 22 | 11 | 0 | RelocationAssistance | 161300 | 16 | 13 | 0
WIK | Division 1 | Work_in_Kind_Channel_Deepening |  | OperatingDeptSupport | 221200 | 22 | 12 | 0 | Appraisals | 161400 | 16 | 14 | 0
WIK | Division 1 | Work_in_Kind_Channel_Deepening |  | BidPackage | 221300 | 22 | 13 | 0 | EnvironmentalAssessments | 161500 | 16 | 15 | 0
WIK | Division 1 | Work_in_Kind_Channel_Deepening |  | Monitoring | 221400 | 22 | 14 | 0 | Condemnation | 161600 | 16 | 16 | 0
WIK | Division 1 | Work_in_Kind_Channel_Deepening | Work_in_Kind_Channel_Deepening_ProjectCloseOut | ProjectCloseOut | 780000 | 78 | 0 | 0 | Inspection | 161700 | 16 | 17 | 0
WIK | Division 1 | Work_in_Kind_Channel_Deepening |  | General | 781000 | 78 | 10 | 0 | TitleWork | 161800 | 16 | 18 | 0
WIK | Division 1 | Work_in_Kind_Channel_Deepening | Work_in_Kind_Channel_Deepening_Contingency | Contingency | 790000 | 79 | 0 | 0 | Survey | 162200 | 16 | 22 | 0
WIK | Division 1 | Work_in_Kind_Channel_Deepening | Work_in_Kind_Channel_Deepening_DredgeProduction | DredgeProduction | 800000 | 80 | 0 | 0 | Equalization | 161100 | 16 | 11 | 0
WIK | Division 1 | Work_in_Kind_Channel_Deepening |  | DredgeLabor | 800010 | 80 | 0 | 10 | PaymentstoWAPorts | 161110 | 16 | 11 | 10
WIK | Division 1 | Work_in_Kind_Channel_Deepening |  | DredgeSurvey | 800020 | 80 | 0 | 20 | Contract | 162300 | 16 | 23 | 0
WIK | Division 1 | Work_in_Kind_Channel_Deepening |  | ShoreLabor | 800030 | 80 | 0 | 30 | Procurement | 162400 | 16 | 24 | 0
WIK | Division 1 | Work_in_Kind_Channel_Deepening |  | DredgeServices | 800040 | 80 | 0 | 40 | Delivery | 162500 | 16 | 25 | 0
WIK | Division 1 | Work_in_Kind_Channel_Deepening |  | DredgeMaterialsandSupplies | 800050 | 80 | 0 | 50 | Development | 170000 | 17 | 0 | 0
WIK | Division 1 | Work_in_Kind_Channel_Deepening |  | ShoreMaterialsandSupplies | 800055 | 80 | 0 | 55 | OutsideDesignServices | 171510 | 17 | 15 | 10
WIK | Division 1 | Work_in_Kind_Channel_Deepening |  | DredgeFuel,Lube,Oil | 800060 | 80 | 0 | 60 | DatabaseAdministration | 171000 | 17 | 10 | 0
WIK | Division 1 | Work_in_Kind_Channel_Deepening |  | ShoreFuel,Lube,Oil | 800065 | 80 | 0 | 65 | SoftwareDevelopmentandConfiguration | 171100 | 17 | 11 | 0
WIK | Division 1 | Work_in_Kind_Channel_Deepening |  | DredgePortEquipRenttoCOE | 800070 | 80 | 0 | 70 | IntegrationDevelopment | 171200 | 17 | 12 | 0
WIK | Division 1 | Work_in_Kind_Channel_Deepening |  | ShorePortEquipRentedtoCOE | 800075 | 80 | 0 | 75 | InterfaceDevelopment | 171300 | 17 | 13 | 0
WIK | Division 1 | Work_in_Kind_Channel_Deepening |  | DredgeOutofTown | 800080 | 80 | 0 | 80 | ConversionDevelopment | 171400 | 17 | 14 | 0
WIK | Division 1 | Work_in_Kind_Channel_Deepening |  | ShoreOutofTown | 800085 | 80 | 0 | 85 | ConceptualDesign | 171500 | 17 | 15 | 0
WIK | Division 1 | Work_in_Kind_Channel_Deepening | Work_in_Kind_Channel_Deepening_MajorMaintenance | MajorMaintenance | 810000 | 81 | 0 | 0 | PEDesign_Support | 171600 | 17 | 16 | 0
WIK | Division 1 | Work_in_Kind_Channel_Deepening |  | DredgeLabor | 810010 | 81 | 0 | 10 | Survey | 171700 | 17 | 17 | 0
WIK | Division 1 | Work_in_Kind_Channel_Deepening |  | DredgeSurvey | 810020 | 81 | 0 | 20 | Contract_Drawings | 171800 | 17 | 18 | 0
WIK | Division 1 | Work_in_Kind_Channel_Deepening |  | ShoreLabor | 810030 | 81 | 0 | 30 | Environmental | 171900 | 17 | 19 | 0
WIK | Division 1 | Work_in_Kind_Channel_Deepening |  | DredgeServices | 810040 | 81 | 0 | 40 | ActionPlan | 171910 | 17 | 19 | 10
WIK | Division 1 | Work_in_Kind_Channel_Deepening |  | ShoreServices | 810045 | 81 | 0 | 45 | PublicAffairs | 172000 | 17 | 20 | 0
WIK | Division 1 | Work_in_Kind_Channel_Deepening |  | DredgeMaterialsandSupplies | 810050 | 81 | 0 | 50 | Planning | 172100 | 17 | 21 | 0
WIK | Division 1 | Work_in_Kind_Channel_Deepening |  | ShoreMaterialsandSupplies | 810055 | 81 | 0 | 55 | Maintenance | 172200 | 17 | 22 | 0
WIK | Division 1 | Work_in_Kind_Channel_Deepening |  | DredgeFuel,Lube,Oil | 810060 | 81 | 0 | 60 | IT | 172300 | 17 | 23 | 0
WIK | Division 1 | Work_in_Kind_Channel_Deepening |  | ShoreFuel,Lube,Oil | 810065 | 81 | 0 | 65 | Construction_InspectionSupport | 172400 | 17 | 24 | 0
WIK | Division 1 | Work_in_Kind_Channel_Deepening |  | DredgeOutofTown | 810070 | 81 | 0 | 70 | PE_DesignSupport | 171600 | 17 | 16 | 0
WIK | Division 1 | Work_in_Kind_Channel_Deepening |  | ShoreOutofTown | 810075 | 81 | 0 | 75 | Implementation | 180000 | 18 | 0 | 0
WIK | Division 1 | Work_in_Kind_Channel_Deepening |  | DredgePortEquipRenttoCOE | 810080 | 81 | 0 | 80 | RemedialAction | 181000 | 18 | 10 | 0
WIK | Division 1 | Work_in_Kind_Channel_Deepening |  | ShorePortEquipRentedtoCOE | 810085 | 81 | 0 | 85 | OandM_Systems | 181100 | 18 | 11 | 0
WIK | Division 1 | Work_in_Kind_Channel_Deepening | Work_in_Kind_Channel_Deepening_Mob_Demob | Mob_Demob | 820000 | 82 | 0 | 0 | OandM_Monitoring | 181200 | 18 | 12 | 0
WIK | Division 1 | Work_in_Kind_Channel_Deepening |  | DredgeLabor | 820010 | 82 | 0 | 10 | Restoration | 181300 | 18 | 13 | 0
WIK | Division 1 | Work_in_Kind_Channel_Deepening |  | DredgeSurvey | 820020 | 82 | 0 | 20 | RestorationImplementation | 181320 | 18 | 13 | 20
WIK | Division 1 | Work_in_Kind_Channel_Deepening |  | ShoreLabor | 820030 | 82 | 0 | 30 | HardwareInstallation | 181400 | 18 | 14 | 0
WIK | Division 1 | Work_in_Kind_Channel_Deepening |  | DredgeServices | 820040 | 82 | 0 | 40 | DatabaseInstallation | 181500 | 18 | 15 | 0
WIK | Division 1 | Work_in_Kind_Channel_Deepening |  | ShoreServices | 820045 | 82 | 0 | 45 | SoftwareInstallation | 181600 | 18 | 16 | 0
WIK | Division 1 | Work_in_Kind_Channel_Deepening |  | DredgeMaterialsandSupplies | 820050 | 82 | 0 | 50 | ITConversion | 181700 | 18 | 17 | 0
WIK | Division 1 | Work_in_Kind_Channel_Deepening |  | ShoreMaterialsandSupplies | 820055 | 82 | 0 | 55 | EquipmentInstallation | 181800 | 18 | 18 | 0
WIK | Division 1 | Work_in_Kind_Channel_Deepening |  | DredgeFuel,Lube,Oil | 820060 | 82 | 0 | 60 | NRDRestoration_Settlement | 181310 | 18 | 13 | 10
WIK | Division 1 | Work_in_Kind_Channel_Deepening |  | ShoreFuel,Lube,Oil | 820065 | 82 | 0 | 65 | Construction | 190000 | 19 | 0 | 0
WIK | Division 1 | Work_in_Kind_Channel_Deepening |  | DredgeOutofTown | 820070 | 82 | 0 | 70 | OutsideConstructionService | 191810 | 19 | 18 | 10
WIK | Division 1 | Work_in_Kind_Channel_Deepening |  | ShoreOutofTown | 820075 | 82 | 0 | 75 | Contract | 191000 | 19 | 10 | 0
WIK | Division 1 | Work_in_Kind_Channel_Deepening |  | DredgePortEquipRenttoCOE | 820080 | 82 | 0 | 80 | EquipmentContracts | 191100 | 19 | 11 | 0
WIK | Division 1 | Work_in_Kind_Channel_Deepening |  | ShorePortEquipRentedtoCOE | 820085 | 82 | 0 | 85 | Management | 191200 | 19 | 12 | 0
WIK | Division 1 | Work_in_Kind_Channel_Deepening | Work_in_Kind_Channel_Deepening_Standby | Standby | 830000 | 83 | 0 | 0 | Inspection | 191300 | 19 | 13 | 0
WIK | Division 1 | Work_in_Kind_Channel_Deepening |  | DredgeLabor | 830010 | 83 | 0 | 10 | Testing | 191400 | 19 | 14 | 0
WIK | Division 1 | Work_in_Kind_Channel_Deepening |  | DredgeSurvey | 830020 | 83 | 0 | 20 | Environmental | 191600 | 19 | 16 | 0
WIK | Division 1 | Work_in_Kind_Channel_Deepening |  | ShoreLabor | 830030 | 83 | 0 | 30 | EngineeringSupport | 191800 | 19 | 18 | 0
WIK | Division 1 | Work_in_Kind_Channel_Deepening |  | DredgeServices | 830040 | 83 | 0 | 40 | NavigationSupport | 192100 | 19 | 21 | 0
WIK | Division 1 | Work_in_Kind_Channel_Deepening |  | ShoreServices | 830045 | 83 | 0 | 45 | TenantAccess | 192200 | 19 | 22 | 0
WIK | Division 1 | Work_in_Kind_Channel_Deepening |  | DredgeMaterialsandSupplies | 830050 | 83 | 0 | 50 | OperatingDeptSupport | 192300 | 19 | 23 | 0
WIK | Division 1 | Work_in_Kind_Channel_Deepening |  | ShoreMaterialsandSupplies | 830055 | 83 | 0 | 55 | OutsideConstructionServices | 191810 | 19 | 18 | 10
WIK | Division 1 | Work_in_Kind_Channel_Deepening |  | DredgeFuel,Lube,Oil | 830060 | 83 | 0 | 60 | Maintenance | 191900 | 19 | 19 | 0
WIK | Division 1 | Work_in_Kind_Channel_Deepening |  | ShoreFuel,Lube,Oil | 830065 | 83 | 0 | 65 | Survey | 191500 | 19 | 15 | 0
WIK | Division 1 | Work_in_Kind_Channel_Deepening |  | DredgeOutofTown | 830070 | 83 | 0 | 70 | PublicAffairs | 191700 | 19 | 17 | 0
WIK | Division 1 | Work_in_Kind_Channel_Deepening |  | ShoreOutofTown | 830075 | 83 | 0 | 75 | IT | 192000 | 19 | 20 | 0
WIK | Division 1 | Work_in_Kind_Channel_Deepening |  | DredgePortEquipRenttoCOE | 830080 | 83 | 0 | 80 | InsurancePremiums | 192500 | 19 | 25 | 0
WIK | Division 1 | Work_in_Kind_Channel_Deepening |  | ShorePortEquipRentedtoCOE | 830085 | 83 | 0 | 85 | Workers'Compensation | 192510 | 19 | 25 | 10
WIK | Division 1 | Work_in_Kind_Channel_Deepening | Work_in_Kind_Channel_Deepening_NavOfficeOperations | NavOfficeOperations | 850000 | 85 | 0 | 0 | GeneralLiability | 192520 | 19 | 25 | 20
WIK | Division 1 | Work_in_Kind_Channel_Deepening |  | StaffLabor | 850010 | 85 | 0 | 10 | ExcessLiability | 192530 | 19 | 25 | 30
WIK | Division 1 | Work_in_Kind_Channel_Deepening |  | MaterialsandSupplies | 850020 | 85 | 0 | 20 | Contractors'PollutionLiability | 192540 | 19 | 25 | 40
WIK | Division 1 | Work_in_Kind_Channel_Deepening |  | Services | 850030 | 85 | 0 | 30 | Builders'Risk | 192550 | 19 | 25 | 50
WIK | Division 1 | Work_in_Kind_Channel_Deepening |  | Utilities | 850040 | 85 | 0 | 40 | Broker_AdminFee | 192560 | 19 | 25 | 60
WIK | Division 1 | Work_in_Kind_Channel_Deepening |  | CostOffsets | 850050 | 85 | 0 | 50 | InsuranceClaims | 192600 | 19 | 26 | 0
WIK | Division 1 | Work_in_Kind_Channel_Deepening | Work_in_Kind_Channel_Deepening_OtherReimbursements | OtherReimbursements | 900000 | 90 | 0 | 0 | Workers'Compensation | 192610 | 19 | 26 | 10
WIK | Division 1 | Work_in_Kind_Channel_Deepening |  | WAPortsReimbursement | 901900 | 90 | 19 | 0 | GeneralLiability | 192620 | 19 | 26 | 20
WIK | Division 1 | Work_in_Kind_Channel_Deepening |  | PortofKalamaReimbursement | 901910 | 90 | 19 | 10 | ExcessLiability | 192630 | 19 | 26 | 30
WIK | Division 1 | Work_in_Kind_Channel_Deepening |  | PortofLongviewReimbursement | 901920 | 90 | 19 | 20 | Contractors'PollutionLiability | 192640 | 19 | 26 | 40
WIK | Division 1 | Work_in_Kind_Channel_Deepening |  | PortofVancouverReimbursement | 901930 | 90 | 19 | 30 | Builders'Risk | 192650 | 19 | 26 | 50
WIK | Division 1 | Work_in_Kind_Channel_Deepening |  | PortofWoodlandReimbursement | 901940 | 90 | 19 | 40 | InsuranceCollateral | 192700 | 19 | 27 | 0
WIK | Division 1 | Work_in_Kind_Channel_Deepening |  | PortofSt.HelensReimbursement | 902000 | 90 | 20 | 0 | Workers'Compensation | 192710 | 19 | 27 | 10
WIK | Division 1 | Work_in_Kind_Channel_Deepening |  | StateofOregonReimbursement | 902100 | 90 | 21 | 0 | SandSales | 192400 | 19 | 24 | 0
PRM | Division 1 | Property_Mgmt_Costs_Channel_Deepening | Property_Mgmt_Costs_Channel_Deepening_Permitting | Permitting | 200000 | 20 | 0 | 0 | Permitting | 200000 | 20 | 0 | 0
PRM | Division 1 | Property_Mgmt_Costs_Channel_Deepening |  | General | 201000 | 20 | 10 | 0 | General | 201000 | 20 | 10 | 0
PRM | Division 1 | Property_Mgmt_Costs_Channel_Deepening | Property_Mgmt_Costs_Channel_Deepening_Maintenance | Maintenance | 220000 | 22 | 0 | 0 | Corps | 201100 | 20 | 11 | 0
PRM | Division 1 | Property_Mgmt_Costs_Channel_Deepening |  | Repairs | 221600 | 22 | 16 | 0 | Federal | 201200 | 20 | 12 | 0
PRM | Division 1 | Property_Mgmt_Costs_Channel_Deepening | Property_Mgmt_Costs_Channel_Deepening_Operations | Operations | 310000 | 31 | 0 | 0 | State | 201300 | 20 | 13 | 0
PRM | Division 1 | Property_Mgmt_Costs_Channel_Deepening |  | PropMgmtRevenues | 311900 | 31 | 19 | 0 | City | 201400 | 20 | 14 | 0
PRM | Division 1 | Property_Mgmt_Costs_Channel_Deepening |  | Taxes | 311910 | 31 | 19 | 10 | Local | 201500 | 20 | 15 | 0
PRM | Division 1 | Property_Mgmt_Costs_Channel_Deepening |  | LeaseRentalIncome | 311920 | 31 | 19 | 20 | Survey | 210000 | 21 | 0 | 0
PRM | Division 1 | Property_Mgmt_Costs_Channel_Deepening |  | SandSalesIncome | 311930 | 31 | 19 | 30 | Reconnaissance | 211000 | 21 | 10 | 0
PRM | Division 1 | Property_Mgmt_Costs_Channel_Deepening |  | PropMgmtExpenses | 312000 | 31 | 20 | 0 | Design | 211100 | 21 | 11 | 0
PRM | Division 1 | Property_Mgmt_Costs_Channel_Deepening |  | General | 312010 | 31 | 20 | 10 | CAD | 211300 | 21 | 13 | 0
PRM | Division 1 | Property_Mgmt_Costs_Channel_Deepening |  | SandSalesExpenses | 312020 | 31 | 20 | 20 | BidPackage | 211400 | 21 | 14 | 0
PRM | Division 1 | Property_Mgmt_Costs_Channel_Deepening |  | Management | 312021 | 31 | 20 | 21 | EngineeringSupport | 211500 | 21 | 15 | 0
PRM | Division 1 | Property_Mgmt_Costs_Channel_Deepening |  | RoyaltyPaymentstoDSL | 312022 | 31 | 20 | 22 | OperatingDeptSupport | 211600 | 21 | 16 | 0
PRM | Division 1 | Property_Mgmt_Costs_Channel_Deepening | Property_Mgmt_Costs_Channel_Deepening_Contingency | Contingency | 790000 | 79 | 0 | 0 | Analysis | 211200 | 21 | 12 | 0
PRG | Division 1 | Programmatic_Channel_Deepening | Programmatic_Channel_Deepening_ProjectAdminandMgmt | ProjectAdminandMgmt | 100000 | 10 | 0 | 0 | TransportationCondition | 211210 | 21 | 12 | 10
PRG | Division 1 | Programmatic_Channel_Deepening |  | General | 101000 | 10 | 10 | 0 | EnvironmentalCondition | 211220 | 21 | 12 | 20
PRG | Division 1 | Programmatic_Channel_Deepening |  | LandAcquisition | 101600 | 10 | 16 | 0 | FacilityCondition | 211230 | 21 | 12 | 30
PRG | Division 1 | Programmatic_Channel_Deepening |  | FinancialSupport | 101700 | 10 | 17 | 0 | UpdateHarborHistory | 211240 | 21 | 12 | 40
PRG | Division 1 | Programmatic_Channel_Deepening |  | LegislativeFunding | 101800 | 10 | 18 | 0 | Maintenance | 220000 | 22 | 0 | 0
PRG | Division 1 | Programmatic_Channel_Deepening |  | Agreements | 101900 | 10 | 19 | 0 | Environmental | 221000 | 22 | 10 | 0
PRG | Division 1 | Programmatic_Channel_Deepening | Programmatic_Channel_Deepening_Design | Design | 140000 | 14 | 0 | 0 | EngineeringSupport | 221100 | 22 | 11 | 0
PRG | Division 1 | Programmatic_Channel_Deepening |  | General | 141000 | 14 | 10 | 0 | OperatingDeptSupport | 221200 | 22 | 12 | 0
PRG | Division 1 | Programmatic_Channel_Deepening |  | Environmental | 141600 | 14 | 16 | 0 | BidPackage | 221300 | 22 | 13 | 0
PRG | Division 1 | Programmatic_Channel_Deepening |  | ESAReconsulation | 142400 | 14 | 24 | 0 | Monitoring | 221400 | 22 | 14 | 0
PRG | Division 1 | Programmatic_Channel_Deepening |  | UtilityRelocations | 142500 | 14 | 25 | 0 | Repairs | 221600 | 22 | 16 | 0
PRG | Division 1 | Programmatic_Channel_Deepening | Programmatic_Channel_Deepening_Acquisition | Acquisition | 160000 | 16 | 0 | 0 | General | 221500 | 22 | 15 | 0
PRG | Division 1 | Programmatic_Channel_Deepening |  | Equalization | 161100 | 16 | 11 | 0 | Legal_Regulatory | 230000 | 23 | 0 | 0
PRG | Division 1 | Programmatic_Channel_Deepening |  | PaymentstoWAPorts | 161110 | 16 | 11 | 10 | Pre_LitigationPreparation | 231300 | 23 | 13 | 0
PRG | Division 1 | Programmatic_Channel_Deepening | Programmatic_Channel_Deepening_Permitting | Permitting | 200000 | 20 | 0 | 0 | LitigationDefense | 231400 | 23 | 14 | 0
PRG | Division 1 | Programmatic_Channel_Deepening |  | General | 201000 | 20 | 10 | 0 | ClosureReplort_NFA | 231600 | 23 | 16 | 0
PRG | Division 1 | Programmatic_Channel_Deepening | Programmatic_Channel_Deepening_Legal_Regulatory | Legal_Regulatory | 230000 | 23 | 0 | 0 | EnforcementDocuments | 231700 | 23 | 17 | 0
PRG | Division 1 | Programmatic_Channel_Deepening |  | Pre_LitigationPreparation | 231300 | 23 | 13 | 0 | FiveYearReview | 231800 | 23 | 18 | 0
PRG | Division 1 | Programmatic_Channel_Deepening |  | Litigate | 231500 | 23 | 15 | 0 | TenantCleanupOversight | 232900 | 23 | 29 | 0
PRG | Division 1 | Programmatic_Channel_Deepening | Programmatic_Channel_Deepening_Outreach | Outreach | 250000 | 25 | 0 | 0 | Litigate | 231500 | 23 | 15 | 0
PRG | Division 1 | Programmatic_Channel_Deepening |  | General | 251000 | 25 | 10 | 0 | ClosureReport_NFA | 231600 | 23 | 16 | 0
PRG | Division 1 | Programmatic_Channel_Deepening |  | CommunityRelations | 251010 | 25 | 10 | 10 | Negotiations | 232100 | 23 | 21 | 0
PRG | Division 1 | Programmatic_Channel_Deepening | Programmatic_Channel_Deepening_Contingency | Contingency | 790000 | 79 | 0 | 0 | TrusteeNegotiations | 232140 | 23 | 21 | 40
PMP | Division 1 | Property_Mgmt_Costs_Programmatic_Chart_Channel_Deepening | Property_Mgmt_Costs_Programmatic_Chart_Channel_Deepening_Acquisition | Acquisition | 160000 | 16 | 0 | 0 | IdentityDevelopment | 232300 | 23 | 23 | 0
PMP | Division 1 | Property_Mgmt_Costs_Programmatic_Chart_Channel_Deepening |  | Equalization | 161100 | 16 | 11 | 0 | PrintMedia | 232400 | 23 | 24 | 0
PMP | Division 1 | Property_Mgmt_Costs_Programmatic_Chart_Channel_Deepening |  | PaymentstoWAPorts | 161110 | 16 | 11 | 10 | Event | 232500 | 23 | 25 | 0
PMP | Division 1 | Property_Mgmt_Costs_Programmatic_Chart_Channel_Deepening | Property_Mgmt_Costs_Programmatic_Chart_Channel_Deepening_Operations | Operations | 310000 | 31 | 0 | 0 | Website | 232600 | 23 | 26 | 0
PMP | Division 1 | Property_Mgmt_Costs_Programmatic_Chart_Channel_Deepening | Property_Mgmt_Costs_Programmatic_Chart_Channel_Deepening_Contingency | Contingency | 790000 | 79 | 0 | 0 | Photography | 232700 | 23 | 27 | 0
PMP | Division 1 | Property_Mgmt_Costs_Programmatic_Chart_Channel_Deepening | Property_Mgmt_Costs_Programmatic_Chart_Channel_Deepening_OtherReimbursements | OtherReimbursements | 900000 | 90 | 0 | 0 | MultimediaPresentations | 232800 | 23 | 28 | 0
PMP | Division 1 | Property_Mgmt_Costs_Programmatic_Chart_Channel_Deepening |  | WAPortsReimbursement | 901900 | 90 | 19 | 0 | Compliance | 232000 | 23 | 20 | 0
PMP | Division 1 | Property_Mgmt_Costs_Programmatic_Chart_Channel_Deepening |  | PortofKalamaReimbursement | 901910 | 90 | 19 | 10 | WRDA | 232010 | 23 | 20 | 10
PMP | Division 1 | Property_Mgmt_Costs_Programmatic_Chart_Channel_Deepening |  | PortofLongviewReimbursement | 901920 | 90 | 19 | 20 | AOCNegotiation | 232110 | 23 | 21 | 10
PMP | Division 1 | Property_Mgmt_Costs_Programmatic_Chart_Channel_Deepening |  | PortofVancouverReimbursement | 901930 | 90 | 19 | 30 | Design | 231000 | 23 | 10 | 0
PMP | Division 1 | Property_Mgmt_Costs_Programmatic_Chart_Channel_Deepening |  | PortofWoodlandReimbursement | 901940 | 90 | 19 | 40 | Construction | 231100 | 23 | 11 | 0
PMP | Division 1 | Property_Mgmt_Costs_Programmatic_Chart_Channel_Deepening |  | PortofSt.HelensReimbursement | 902000 | 90 | 20 | 0 | Development | 231200 | 23 | 12 | 0
PMP | Division 1 | Property_Mgmt_Costs_Programmatic_Chart_Channel_Deepening |  | StateofofOregonReimbursement | 902100 | 90 | 21 | 0 | ActionMemo | 231900 | 23 | 19 | 0
NRD | Division 1 | Natural_Resource_Damages_Lower_Willamette | Natural_Resource_Damages_Lower_Willamette_ProjectAdminandMgmt | ProjectAdminandMgmt | 100000 | 10 | 0 | 0 | AOCNegotiations | 232110 | 23 | 21 | 10
NRD | Division 1 | Natural_Resource_Damages_Lower_Willamette |  | General | 101000 | 10 | 10 | 0 | CD_AU_UONegotiations | 232120 | 23 | 21 | 20
NRD | Division 1 | Natural_Resource_Damages_Lower_Willamette | Natural_Resource_Damages_Lower_Willamette_Design | Design | 140000 | 14 | 0 | 0 | NRDNegotiations | 232130 | 23 | 21 | 30
NRD | Division 1 | Natural_Resource_Damages_Lower_Willamette |  | Restoration | 141500 | 14 | 15 | 0 | FiveYearrevuew | 231800 | 23 | 18 | 0
NRD | Division 1 | Natural_Resource_Damages_Lower_Willamette |  | RestorationPlanandDev,includingDesign | 141510 | 14 | 15 | 10 | CD_AO_UONegotiations | 232120 | 23 | 21 | 20
NRD | Division 1 | Natural_Resource_Damages_Lower_Willamette | Natural_Resource_Damages_Lower_Willamette_Planning | Planning | 150000 | 15 | 0 | 0 | Acquisition | 232200 | 23 | 22 | 0
NRD | Division 1 | Natural_Resource_Damages_Lower_Willamette |  | AssessmentPlanning | 151100 | 15 | 11 | 0 | PublicRecordsRequest | 240000 | 24 | 0 | 0
NRD | Division 1 | Natural_Resource_Damages_Lower_Willamette |  | Strategy_Planning | 151120 | 15 | 11 | 20 | General | 241000 | 24 | 10 | 0
NRD | Division 1 | Natural_Resource_Damages_Lower_Willamette |  | InjuryAssessment | 151130 | 15 | 11 | 30 | Outreach | 250000 | 25 | 0 | 0
NRD | Division 1 | Natural_Resource_Damages_Lower_Willamette |  | CulturalResources | 151700 | 15 | 17 | 0 | General | 251000 | 25 | 10 | 0
NRD | Division 1 | Natural_Resource_Damages_Lower_Willamette | Natural_Resource_Damages_Lower_Willamette_Implementation | Implementation | 180000 | 18 | 0 | 0 | CommunityRelations | 251010 | 25 | 10 | 10
NRD | Division 1 | Natural_Resource_Damages_Lower_Willamette |  | OandM_Monitoring | 181200 | 18 | 12 | 0 | EvaluationProcess | 251400 | 25 | 14 | 0
NRD | Division 1 | Natural_Resource_Damages_Lower_Willamette |  | Restoration | 181300 | 18 | 13 | 0 | Documentation | 260000 | 26 | 0 | 0
NRD | Division 1 | Natural_Resource_Damages_Lower_Willamette |  | RestorationImplementation | 181320 | 18 | 13 | 20 | TechnicalDocumentation | 261000 | 26 | 10 | 0
NRD | Division 1 | Natural_Resource_Damages_Lower_Willamette | Natural_Resource_Damages_Lower_Willamette_Legal_Regulatory | Legal_Regulatory | 230000 | 23 | 0 | 0 | EndUserDocumentation | 261100 | 26 | 11 | 0
NRD | Division 1 | Natural_Resource_Damages_Lower_Willamette |  | Pre_LitigationPreparation | 231300 | 23 | 13 | 0 | MaintenanceDocumentation | 261200 | 26 | 12 | 0
NRD | Division 1 | Natural_Resource_Damages_Lower_Willamette |  | LitigationDefense | 231400 | 23 | 14 | 0 | SupportDocumentation | 261300 | 26 | 13 | 0
NRD | Division 1 | Natural_Resource_Damages_Lower_Willamette |  | ClosureReport_NFA | 231600 | 23 | 16 | 0 | TrainingMaterials | 261400 | 26 | 14 | 0
NRD | Division 1 | Natural_Resource_Damages_Lower_Willamette |  | EnforcementDocuments | 231700 | 23 | 17 | 0 | RecordsManagement | 270000 | 27 | 0 | 0
NRD | Division 1 | Natural_Resource_Damages_Lower_Willamette |  | Negotiations | 232100 | 23 | 21 | 0 | General | 271000 | 27 | 10 | 0
NRD | Division 1 | Natural_Resource_Damages_Lower_Willamette |  | TrusteeNegotiations | 232140 | 23 | 21 | 40 | Coding_Scanning | 271100 | 27 | 11 | 0
NRD | Division 1 | Natural_Resource_Damages_Lower_Willamette | Natural_Resource_Damages_Lower_Willamette_PublicRecordsRequest | PublicRecordsRequest | 240000 | 24 | 0 | 0 | TechnicalSupport | 271200 | 27 | 12 | 0
NRD | Division 1 | Natural_Resource_Damages_Lower_Willamette |  | General | 241000 | 24 | 10 | 0 | Hardware_Software | 271300 | 27 | 13 | 0
NRD | Division 1 | Natural_Resource_Damages_Lower_Willamette | Natural_Resource_Damages_Lower_Willamette_Outreach | Outreach | 250000 | 25 | 0 | 0 | Coding_Scaning | 271100 | 27 | 11 | 0
NRD | Division 1 | Natural_Resource_Damages_Lower_Willamette |  | General | 251000 | 25 | 10 | 0 | Testing | 280000 | 28 | 0 | 0
NRD | Division 1 | Natural_Resource_Damages_Lower_Willamette |  | CommunityRelations | 251010 | 25 | 10 | 10 | General | 281000 | 28 | 10 | 0
NRD | Division 1 | Natural_Resource_Damages_Lower_Willamette | Natural_Resource_Damages_Lower_Willamette_CostRecovery | CostRecovery | 300000 | 30 | 0 | 0 | Training | 290000 | 29 | 0 | 0
NRD | Division 1 | Natural_Resource_Damages_Lower_Willamette |  | PRPPursuit | 301000 | 30 | 10 | 0 | IdentityDevelopment | 291300 | 29 | 13 | 0
NRD | Division 1 | Natural_Resource_Damages_Lower_Willamette | Natural_Resource_Damages_Lower_Willamette_Payments | Payments | 320000 | 32 | 0 | 0 | PrintMedia | 291400 | 29 | 14 | 0
NRD | Division 1 | Natural_Resource_Damages_Lower_Willamette |  | GroupPayments | 321000 | 32 | 10 | 0 | Event | 291500 | 29 | 15 | 0
NRD | Division 1 | Natural_Resource_Damages_Lower_Willamette |  | OversightCosts | 321300 | 32 | 13 | 0 | Website | 291600 | 29 | 16 | 0
NRD | Division 1 | Natural_Resource_Damages_Lower_Willamette |  | EPA | 321310 | 32 | 13 | 10 | Photography | 291700 | 29 | 17 | 0
NRD | Division 1 | Natural_Resource_Damages_Lower_Willamette |  | DEQ | 321320 | 32 | 13 | 20 | MultimediaPresentations | 291800 | 29 | 18 | 0
NRD | Division 1 | Natural_Resource_Damages_Lower_Willamette |  | Tribes | 321330 | 32 | 13 | 30 | CoreUserTraining | 291000 | 29 | 10 | 0
NRD | Division 1 | Natural_Resource_Damages_Lower_Willamette |  | Trustees | 321340 | 32 | 13 | 40 | EndUserTraining | 291100 | 29 | 11 | 0
NRD | Division 1 | Natural_Resource_Damages_Lower_Willamette | Natural_Resource_Damages_Lower_Willamette_Contingency | Contingency | 790000 | 79 | 0 | 0 | SupportTeamTraining | 291200 | 29 | 12 | 0
NRD | Division 1 | Natural_Resource_Damages_Lower_Willamette |  | CASS | 909000 | 90 | 90 | 0 | CostRecovery | 300000 | 30 | 0 | 0
MSP | Division 1 | Master_Planning | Master_Planning_ProjectAdminandMgmt | ProjectAdminandMgmt | 100000 | 10 | 0 | 0 | PRPPursuit | 301000 | 30 | 10 | 0
MSP | Division 1 | Master_Planning |  | General | 101000 | 10 | 10 | 0 | InsuranceCostRecovery | 301100 | 30 | 11 | 0
MSP | Division 1 | Master_Planning |  | ProjectMgmt | 101200 | 10 | 12 | 0 | PRPNegotiations | 301200 | 30 | 12 | 0
MSP | Division 1 | Master_Planning | Master_Planning_Planning | Planning | 150000 | 15 | 0 | 0 | PRP_DoD | 301300 | 30 | 13 | 0
MSP | Division 1 | Master_Planning |  | General | 151000 | 15 | 10 | 0 | Operations | 310000 | 31 | 0 | 0
MSP | Division 1 | Master_Planning |  | AssessmentPlanning | 151100 | 15 | 11 | 0 | PropMgmtRevenues | 311900 | 31 | 19 | 0
MSP | Division 1 | Master_Planning |  | CapacityAnalysis | 151140 | 15 | 11 | 40 | Taxes | 311910 | 31 | 19 | 10
MSP | Division 1 | Master_Planning |  | EnvironmentalAssessment_ActionPlan | 151150 | 15 | 11 | 50 | LeaseRentalIncome | 311920 | 31 | 19 | 20
MSP | Division 1 | Master_Planning |  | Forecasts | 151400 | 15 | 14 | 0 | SandSalesIncome | 311930 | 31 | 19 | 30
MSP | Division 1 | Master_Planning |  | Cargo | 151410 | 15 | 14 | 10 | PropMgmtExpenses | 312000 | 31 | 20 | 0
MSP | Division 1 | Master_Planning |  | FutureTechnology | 151420 | 15 | 14 | 20 | General | 312010 | 31 | 20 | 10
MSP | Division 1 | Master_Planning |  | Capital | 151430 | 15 | 14 | 30 | SandSalesExpenses | 312020 | 31 | 20 | 20
MSP | Division 1 | Master_Planning |  | AlternativesDefinition | 151500 | 15 | 15 | 0 | Management | 312021 | 31 | 20 | 21
MSP | Division 1 | Master_Planning |  | Facility | 151510 | 15 | 15 | 10 | RoyaltyPaymentstoDSL | 312022 | 31 | 20 | 22
MSP | Division 1 | Master_Planning |  | MasterPlan | 151520 | 15 | 15 | 20 | LevelGreen_Yellow | 311000 | 31 | 10 | 0
MSP | Division 1 | Master_Planning |  | TransportationImprovement | 151530 | 15 | 15 | 30 | LevelOrange | 311100 | 31 | 11 | 0
MSP | Division 1 | Master_Planning | Master_Planning_Survey | Survey | 210000 | 21 | 0 | 0 | LevelRed | 311200 | 31 | 12 | 0
MSP | Division 1 | Master_Planning |  | Analysis | 211200 | 21 | 12 | 0 | KennelingandCare | 311300 | 31 | 13 | 0
MSP | Division 1 | Master_Planning |  | TransportationCondition | 211210 | 21 | 12 | 10 | VehicleMgmt | 311400 | 31 | 14 | 0
MSP | Division 1 | Master_Planning |  | EnvironmentalCondition | 211220 | 21 | 12 | 20 | VeternaryCare | 311500 | 31 | 15 | 0
MSP | Division 1 | Master_Planning |  | FacilityCondition | 211230 | 21 | 12 | 30 | Communications | 311600 | 31 | 16 | 0
MSP | Division 1 | Master_Planning |  | UpdateHarborHistory | 211240 | 21 | 12 | 40 | MiscK9Costs | 311700 | 31 | 17 | 0
MSP | Division 1 | Master_Planning | Master_Planning_Outreach | Outreach | 250000 | 25 | 0 | 0 | Payments | 320000 | 32 | 0 | 0
MSP | Division 1 | Master_Planning |  | General | 251000 | 25 | 10 | 0 | PRPGroupPayments | 321100 | 32 | 11 | 0
MSP | Division 1 | Master_Planning | Master_Planning_ProjectCloseOut | ProjectCloseOut | 780000 | 78 | 0 | 0 | OversightCosts | 321300 | 32 | 13 | 0
MSP | Division 1 | Master_Planning |  | General | 781000 | 78 | 10 | 0 | EPA | 321310 | 32 | 13 | 10
MSP | Division 1 | Master_Planning | Master_Planning_Contingency | Contingency | 790000 | 79 | 0 | 0 | DEQ | 321320 | 32 | 13 | 20
MSP | Division 1 | Master_Planning |  | CASS | 909000 | 90 | 90 | 0 | Tribes | 321330 | 32 | 13 | 30
MKT | Division 1 | Marketing | Marketing_Design | Design | 140000 | 14 | 0 | 0 | Trustees | 321340 | 32 | 13 | 40
MKT | Division 1 | Marketing |  | IdentityDevelopment | 142900 | 14 | 29 | 0 | GroupPayments | 321000 | 32 | 10 | 0
MKT | Division 1 | Marketing |  | PrintMedia | 143000 | 14 | 30 | 0 | LWGGroupPayments | 321200 | 32 | 12 | 0
MKT | Division 1 | Marketing |  | Event | 143100 | 14 | 31 | 0 | IdentityDevelopment | 330000 | 33 | 0 | 0
MKT | Division 1 | Marketing |  | Website | 143200 | 14 | 32 | 0 | Print | 331000 | 33 | 10 | 0
MKT | Division 1 | Marketing |  | Photography | 143300 | 14 | 33 | 0 | CopyWriting | 331100 | 33 | 11 | 0
MKT | Division 1 | Marketing |  | MultimediaPresentations | 143400 | 14 | 34 | 0 | Photography | 331200 | 33 | 12 | 0
MKT | Division 1 | Marketing | Marketing_Planning | Planning | 150000 | 15 | 0 | 0 | Advertising | 331300 | 33 | 13 | 0
MKT | Division 1 | Marketing |  | IdentityDevelopment | 152000 | 15 | 20 | 0 | Distribution | 331400 | 33 | 14 | 0
MKT | Division 1 | Marketing |  | PrintMedia | 152100 | 15 | 21 | 0 | SpecialPromotion | 331500 | 33 | 15 | 0
MKT | Division 1 | Marketing |  | Event | 152200 | 15 | 22 | 0 | Travel | 331600 | 33 | 16 | 0
MKT | Division 1 | Marketing |  | Website | 152300 | 15 | 23 | 0 | PrintMedia | 340000 | 34 | 0 | 0
MKT | Division 1 | Marketing |  | Photography | 152400 | 15 | 24 | 0 | Print | 341000 | 34 | 10 | 0
MKT | Division 1 | Marketing |  | MultimediaPresentations | 152500 | 15 | 25 | 0 | CopyWriting | 341100 | 34 | 11 | 0
MKT | Division 1 | Marketing | Marketing_Legal_Regulatory | Legal_Regulatory | 230000 | 23 | 0 | 0 | Photography | 341200 | 34 | 12 | 0
MKT | Division 1 | Marketing |  | IdentityDevelopment | 232300 | 23 | 23 | 0 | Advertising | 341300 | 34 | 13 | 0
MKT | Division 1 | Marketing |  | PrintMedia | 232400 | 23 | 24 | 0 | Distribution | 341400 | 34 | 14 | 0
MKT | Division 1 | Marketing |  | Event | 232500 | 23 | 25 | 0 | SpecialPromotion | 341500 | 34 | 15 | 0
MKT | Division 1 | Marketing |  | Website | 232600 | 23 | 26 | 0 | Travel | 341600 | 34 | 16 | 0
MKT | Division 1 | Marketing |  | Photography | 232700 | 23 | 27 | 0 | Event | 350000 | 35 | 0 | 0
MKT | Division 1 | Marketing |  | MultimediaPresentations | 232800 | 23 | 28 | 0 | Print | 351000 | 35 | 10 | 0
MKT | Division 1 | Marketing | Marketing_Training | Training | 290000 | 29 | 0 | 0 | CopyWriting | 351100 | 35 | 11 | 0
MKT | Division 1 | Marketing |  | IdentityDevelopment | 291300 | 29 | 13 | 0 | Photography | 351200 | 35 | 12 | 0
MKT | Division 1 | Marketing |  | PrintMedia | 291400 | 29 | 14 | 0 | Advertising | 351300 | 35 | 13 | 0
MKT | Division 1 | Marketing |  | Event | 291500 | 29 | 15 | 0 | Distribution | 351400 | 35 | 14 | 0
MKT | Division 1 | Marketing |  | Website | 291600 | 29 | 16 | 0 | SpecialPromotion | 351500 | 35 | 15 | 0
MKT | Division 1 | Marketing |  | Photography | 291700 | 29 | 17 | 0 | Travel | 351600 | 35 | 16 | 0
MKT | Division 1 | Marketing |  | MultimediaPresentations | 291800 | 29 | 18 | 0 | Website | 360000 | 36 | 0 | 0
MKT | Division 1 | Marketing | Marketing_IdentityDevelopment | IdentityDevelopment | 330000 | 33 | 0 | 0 | Print | 361000 | 36 | 10 | 0
MKT | Division 1 | Marketing |  | Print | 331000 | 33 | 10 | 0 | CopyWriting | 361100 | 36 | 11 | 0
MKT | Division 1 | Marketing |  | CopyWriting | 331100 | 33 | 11 | 0 | Photography | 361200 | 36 | 12 | 0
MKT | Division 1 | Marketing |  | Photography | 331200 | 33 | 12 | 0 | Advertising | 361300 | 36 | 13 | 0
MKT | Division 1 | Marketing |  | Advertising | 331300 | 33 | 13 | 0 | Distribution | 361400 | 36 | 14 | 0
MKT | Division 1 | Marketing |  | Distribution | 331400 | 33 | 14 | 0 | SpecialPromotion | 361500 | 36 | 15 | 0
MKT | Division 1 | Marketing |  | SpecialPromotion | 331500 | 33 | 15 | 0 | Travel | 361600 | 36 | 16 | 0
MKT | Division 1 | Marketing |  | Travel | 331600 | 33 | 16 | 0 | Photography | 370000 | 37 | 0 | 0
MKT | Division 1 | Marketing | Marketing_PrintMedia | PrintMedia | 340000 | 34 | 0 | 0 | Print | 371000 | 37 | 10 | 0
MKT | Division 1 | Marketing |  | Print | 341000 | 34 | 10 | 0 | CopyWriting | 371100 | 37 | 11 | 0
MKT | Division 1 | Marketing |  | CopyWriting | 341100 | 34 | 11 | 0 | PhotoShooting | 371200 | 37 | 12 | 0
MKT | Division 1 | Marketing |  | Photography | 341200 | 34 | 12 | 0 | Advertising | 371300 | 37 | 13 | 0
MKT | Division 1 | Marketing |  | Advertising | 341300 | 34 | 13 | 0 | Distribution | 371400 | 37 | 14 | 0
MKT | Division 1 | Marketing |  | Distribution | 341400 | 34 | 14 | 0 | SpecialPromotion | 371500 | 37 | 15 | 0
MKT | Division 1 | Marketing |  | SpecialPromotion | 341500 | 34 | 15 | 0 | Travel | 371600 | 37 | 16 | 0
MKT | Division 1 | Marketing |  | Travel | 341600 | 34 | 16 | 0 | MultimediaPresentations | 380000 | 38 | 0 | 0
MKT | Division 1 | Marketing | Marketing_Event | Event | 350000 | 35 | 0 | 0 | Print | 381000 | 38 | 10 | 0
MKT | Division 1 | Marketing |  | Print | 351000 | 35 | 10 | 0 | CopyWriting | 381100 | 38 | 11 | 0
MKT | Division 1 | Marketing |  | CopyWriting | 351100 | 35 | 11 | 0 | PhotoShooting | 381200 | 38 | 12 | 0
MKT | Division 1 | Marketing |  | Photography | 351200 | 35 | 12 | 0 | Advertising | 381300 | 38 | 13 | 0
MKT | Division 1 | Marketing |  | Advertising | 351300 | 35 | 13 | 0 | Distribution | 381400 | 38 | 14 | 0
MKT | Division 1 | Marketing |  | Distribution | 351400 | 35 | 14 | 0 | SpecialPromotion | 381500 | 38 | 15 | 0
MKT | Division 1 | Marketing |  | SpecialPromotion | 351500 | 35 | 15 | 0 | Travel | 381600 | 38 | 16 | 0
MKT | Division 1 | Marketing |  | Travel | 351600 | 35 | 16 | 0 | Insurance_FEMATracking | 390000 | 39 | 0 | 0
MKT | Division 1 | Marketing | Marketing_Website | Website | 360000 | 36 | 0 | 0 | Preservation_Prevention | 391000 | 39 | 10 | 0
MKT | Division 1 | Marketing |  | Print | 361000 | 36 | 10 | 0 | Clean_Up | 391100 | 39 | 11 | 0
MKT | Division 1 | Marketing |  | CopyWriting | 361100 | 36 | 11 | 0 | Damages | 391200 | 39 | 12 | 0
MKT | Division 1 | Marketing |  | Photography | 361200 | 36 | 12 | 0 | EOC | 391300 | 39 | 13 | 0
MKT | Division 1 | Marketing |  | Advertising | 361300 | 36 | 13 | 0 | ProjectCloseOut | 780000 | 78 | 0 | 0
MKT | Division 1 | Marketing |  | Distribution | 361400 | 36 | 14 | 0 | General | 781000 | 78 | 10 | 0
MKT | Division 1 | Marketing |  | SpecialPromotion | 361500 | 36 | 15 | 0 | AsBuilts | 781100 | 78 | 11 | 0
MKT | Division 1 | Marketing |  | Travel | 361600 | 36 | 16 | 0 | Survey | 781200 | 78 | 12 | 0
MKT | Division 1 | Marketing | Marketing_Photography | Photography | 370000 | 37 | 0 | 0 | TechnicalReferenceCenter | 781300 | 78 | 13 | 0
MKT | Division 1 | Marketing |  | Print | 371000 | 37 | 10 | 0 | GeographicInformationSystem | 781400 | 78 | 14 | 0
MKT | Division 1 | Marketing |  | CopyWriting | 371100 | 37 | 11 | 0 | Contingency | 790000 | 79 | 0 | 0
MKT | Division 1 | Marketing |  | PhotoShooting | 371200 | 37 | 12 | 0 | DredgeProduction | 800000 | 80 | 0 | 0
MKT | Division 1 | Marketing |  | Advertising | 371300 | 37 | 13 | 0 | DredgeLabor | 800010 | 80 | 0 | 10
MKT | Division 1 | Marketing |  | Distribution | 371400 | 37 | 14 | 0 | DredgeSurvey | 800020 | 80 | 0 | 20
MKT | Division 1 | Marketing |  | SpecialPromotion | 371500 | 37 | 15 | 0 | ShoreLabor | 800030 | 80 | 0 | 30
MKT | Division 1 | Marketing |  | Travel | 371600 | 37 | 16 | 0 | DredgeServices | 800040 | 80 | 0 | 40
MKT | Division 1 | Marketing | Marketing_MultimediaPresentations | MultimediaPresentations | 380000 | 38 | 0 | 0 | DredgeMaterialsandSupplies | 800050 | 80 | 0 | 50
MKT | Division 1 | Marketing |  | Print | 381000 | 38 | 10 | 0 | ShoreMaterialsandSupplies | 800055 | 80 | 0 | 55
MKT | Division 1 | Marketing |  | CopyWriting | 381100 | 38 | 11 | 0 | DredgeFuel,Lube,Oil | 800060 | 80 | 0 | 60
MKT | Division 1 | Marketing |  | PhotoShooting | 381200 | 38 | 12 | 0 | ShoreFuel,Lube,Oil | 800065 | 80 | 0 | 65
MKT | Division 1 | Marketing |  | Advertising | 381300 | 38 | 13 | 0 | DredgePortEquipRenttoCOE | 800070 | 80 | 0 | 70
MKT | Division 1 | Marketing |  | Distribution | 381400 | 38 | 14 | 0 | ShorePortEquipRentedtoCOE | 800075 | 80 | 0 | 75
MKT | Division 1 | Marketing |  | SpecialPromotion | 381500 | 38 | 15 | 0 | DredgeOutofTown | 800080 | 80 | 0 | 80
MKT | Division 1 | Marketing |  | Travel | 381600 | 38 | 16 | 0 | ShoreOutofTown | 800085 | 80 | 0 | 85
MKT | Division 1 | Marketing | Marketing_Contingency | Contingency | 790000 | 79 | 0 | 0 | MajorMaintenance | 810000 | 81 | 0 | 0
MKT | Division 1 | Marketing |  | CASS | 909000 | 90 | 90 | 0 | DredgeLabor | 810010 | 81 | 0 | 10
MIT | Division 1 | Mitigation | Mitigation_Maintenance | Maintenance | 220000 | 22 | 0 | 0 | DredgeSurvey | 810020 | 81 | 0 | 20
MIT | Division 1 | Mitigation |  | Monitoring | 221400 | 22 | 14 | 0 | ShoreLabor | 810030 | 81 | 0 | 30
MIT | Division 1 | Mitigation |  | General | 221500 | 22 | 15 | 0 | DredgeServices | 810040 | 81 | 0 | 40
MIT | Division 1 | Mitigation | Mitigation_Contingency | Contingency | 790000 | 79 | 0 | 0 | ShoreServices | 810045 | 81 | 0 | 45
LWP | Division 1 | Programmatic_Lower_Willamette | Programmatic_Lower_Willamette_ProjectAdminandMgmt | ProjectAdminandMgmt | 100000 | 10 | 0 | 0 | DredgeMaterialsandSupplies | 810050 | 81 | 0 | 50
LWP | Division 1 | Programmatic_Lower_Willamette |  | General | 101000 | 10 | 10 | 0 | ShoreMaterialsandSupplies | 810055 | 81 | 0 | 55
LWP | Division 1 | Programmatic_Lower_Willamette |  | UplandSourceControlProgramCoordination | 101010 | 10 | 10 | 10 | DredgeFuel,Lube,Oil | 810060 | 81 | 0 | 60
LWP | Division 1 | Programmatic_Lower_Willamette |  | ProgramManagement | 101020 | 10 | 10 | 20 | ShoreFuel,Lube,Oil | 810065 | 81 | 0 | 65
LWP | Division 1 | Programmatic_Lower_Willamette | Programmatic_Lower_Willamette_Planning | Planning | 150000 | 15 | 0 | 0 | DredgeOutofTown | 810070 | 81 | 0 | 70
LWP | Division 1 | Programmatic_Lower_Willamette |  | SiteInvestigation | 151200 | 15 | 12 | 0 | ShoreOutofTown | 810075 | 81 | 0 | 75
LWP | Division 1 | Programmatic_Lower_Willamette |  | GeneralStormWaterPipes | 151240 | 15 | 12 | 40 | DredgePortEquipRenttoCOE | 810080 | 81 | 0 | 80
LWP | Division 1 | Programmatic_Lower_Willamette |  | TechnicalSupport | 151900 | 15 | 19 | 0 | ShorePortEquipRentedtoCOE | 810085 | 81 | 0 | 85
LWP | Division 1 | Programmatic_Lower_Willamette | Programmatic_Lower_Willamette_Legal_Regulatory | Legal_Regulatory | 230000 | 23 | 0 | 0 | Mob_Demob | 820000 | 82 | 0 | 0
LWP | Division 1 | Programmatic_Lower_Willamette |  | TenantCleanupOversight | 232900 | 23 | 29 | 0 | DredgeLabor | 820010 | 82 | 0 | 10
LWP | Division 1 | Programmatic_Lower_Willamette | Programmatic_Lower_Willamette_PublicRecordsRequest | PublicRecordsRequest | 240000 | 24 | 0 | 0 | DredgeSurvey | 820020 | 82 | 0 | 20
LWP | Division 1 | Programmatic_Lower_Willamette |  | General | 241000 | 24 | 10 | 0 | ShoreLabor | 820030 | 82 | 0 | 30
LWP | Division 1 | Programmatic_Lower_Willamette | Programmatic_Lower_Willamette_Outreach | Outreach | 250000 | 25 | 0 | 0 | DredgeServices | 820040 | 82 | 0 | 40
LWP | Division 1 | Programmatic_Lower_Willamette |  | General | 251000 | 25 | 10 | 0 | ShoreServices | 820045 | 82 | 0 | 45
LWP | Division 1 | Programmatic_Lower_Willamette | Programmatic_Lower_Willamette_RecordsManagement | RecordsManagement | 270000 | 27 | 0 | 0 | DredgeMaterialsandSupplies | 820050 | 82 | 0 | 50
LWP | Division 1 | Programmatic_Lower_Willamette |  | General | 271000 | 27 | 10 | 0 | ShoreMaterialsandSupplies | 820055 | 82 | 0 | 55
LWP | Division 1 | Programmatic_Lower_Willamette |  | Coding_Scanning | 271100 | 27 | 11 | 0 | DredgeFuel,Lube,Oil | 820060 | 82 | 0 | 60
LWP | Division 1 | Programmatic_Lower_Willamette |  | TechnicalSupport | 271200 | 27 | 12 | 0 | ShoreFuel,Lube,Oil | 820065 | 82 | 0 | 65
LWP | Division 1 | Programmatic_Lower_Willamette |  | Hardware_Software | 271300 | 27 | 13 | 0 | DredgeOutofTown | 820070 | 82 | 0 | 70
LWP | Division 1 | Programmatic_Lower_Willamette | Programmatic_Lower_Willamette_CostRecovery | CostRecovery | 300000 | 30 | 0 | 0 | ShoreOutofTown | 820075 | 82 | 0 | 75
LWP | Division 1 | Programmatic_Lower_Willamette |  | PRPPursuit | 301000 | 30 | 10 | 0 | DredgePortEquipRenttoCOE | 820080 | 82 | 0 | 80
LWP | Division 1 | Programmatic_Lower_Willamette |  | InsuranceCostRecovery | 301100 | 30 | 11 | 0 | ShorePortEquipRentedtoCOE | 820085 | 82 | 0 | 85
LWP | Division 1 | Programmatic_Lower_Willamette |  | PRPNegotiations | 301200 | 30 | 12 | 0 | Standby | 830000 | 83 | 0 | 0
LWP | Division 1 | Programmatic_Lower_Willamette |  | PRP_DoD | 301300 | 30 | 13 | 0 | DredgeLabor | 830010 | 83 | 0 | 10
LWP | Division 1 | Programmatic_Lower_Willamette | Programmatic_Lower_Willamette_Contingency | Contingency | 790000 | 79 | 0 | 0 | DredgeSurvey | 830020 | 83 | 0 | 20
LWP | Division 1 | Programmatic_Lower_Willamette |  | CASS | 909000 | 90 | 90 | 0 | ShoreLabor | 830030 | 83 | 0 | 30
LWJ | Division 1 | Lower_Willamette_Project_Lower_Willamette | Lower_Willamette_Project_Lower_Willamette_ProjectAdminandMgmt | ProjectAdminandMgmt | 100000 | 10 | 0 | 0 | DredgeServices | 830040 | 83 | 0 | 40
LWJ | Division 1 | Lower_Willamette_Project_Lower_Willamette |  | General | 101000 | 10 | 10 | 0 | ShoreServices | 830045 | 83 | 0 | 45
LWJ | Division 1 | Lower_Willamette_Project_Lower_Willamette | Lower_Willamette_Project_Lower_Willamette_Design | Design | 140000 | 14 | 0 | 0 | DredgeMaterialsandSupplies | 830050 | 83 | 0 | 50
LWJ | Division 1 | Lower_Willamette_Project_Lower_Willamette |  | RemedialDesign | 141400 | 14 | 14 | 0 | ShoreMaterialsandSupplies | 830055 | 83 | 0 | 55
LWJ | Division 1 | Lower_Willamette_Project_Lower_Willamette | Lower_Willamette_Project_Lower_Willamette_Planning | Planning | 150000 | 15 | 0 | 0 | DredgeFuel,Lube,Oil | 830060 | 83 | 0 | 60
LWJ | Division 1 | Lower_Willamette_Project_Lower_Willamette |  | AssessmentPlanning | 151100 | 15 | 11 | 0 | ShoreFuel,Lube,Oil | 830065 | 83 | 0 | 65
LWJ | Division 1 | Lower_Willamette_Project_Lower_Willamette |  | Strategy_Planning | 151120 | 15 | 11 | 20 | DredgeOutofTown | 830070 | 83 | 0 | 70
LWJ | Division 1 | Lower_Willamette_Project_Lower_Willamette |  | RemedialInvestigation | 151300 | 15 | 13 | 0 | ShoreOutofTown | 830075 | 83 | 0 | 75
LWJ | Division 1 | Lower_Willamette_Project_Lower_Willamette |  | FeasibilityStudy | 151600 | 15 | 16 | 0 | DredgePortEquipRenttoCOE | 830080 | 83 | 0 | 80
LWJ | Division 1 | Lower_Willamette_Project_Lower_Willamette |  | CulturalResources | 151700 | 15 | 17 | 0 | ShorePortEquipRentedtoCOE | 830085 | 83 | 0 | 85
LWJ | Division 1 | Lower_Willamette_Project_Lower_Willamette | Lower_Willamette_Project_Lower_Willamette_Implementation | Implementation | 180000 | 18 | 0 | 0 | NavOfficeOperations | 850000 | 85 | 0 | 0
LWJ | Division 1 | Lower_Willamette_Project_Lower_Willamette |  | RemedialAction | 181000 | 18 | 10 | 0 | StaffLabor | 850010 | 85 | 0 | 10
LWJ | Division 1 | Lower_Willamette_Project_Lower_Willamette | Lower_Willamette_Project_Lower_Willamette_Permitting | Permitting | 200000 | 20 | 0 | 0 | MaterialsandSupplies | 850020 | 85 | 0 | 20
LWJ | Division 1 | Lower_Willamette_Project_Lower_Willamette |  | General | 201000 | 20 | 10 | 0 | Services | 850030 | 85 | 0 | 30
LWJ | Division 1 | Lower_Willamette_Project_Lower_Willamette | Lower_Willamette_Project_Lower_Willamette_Legal_Regulatory | Legal_Regulatory | 230000 | 23 | 0 | 0 | Utilities | 850040 | 85 | 0 | 40
LWJ | Division 1 | Lower_Willamette_Project_Lower_Willamette |  | Compliance | 232000 | 23 | 20 | 0 | CostOffsets | 850050 | 85 | 0 | 50
LWJ | Division 1 | Lower_Willamette_Project_Lower_Willamette |  | WRDA | 232010 | 23 | 20 | 10 | CASS | 909000 | 90 | 90 | 0
LWJ | Division 1 | Lower_Willamette_Project_Lower_Willamette |  | Negotiations | 232100 | 23 | 21 | 0 | OtherReimbursements | 900000 | 90 | 0 | 0
LWJ | Division 1 | Lower_Willamette_Project_Lower_Willamette |  | AOCNegotiation | 232110 | 23 | 21 | 10 | WAPortsReimbursement | 901900 | 90 | 19 | 0
LWJ | Division 1 | Lower_Willamette_Project_Lower_Willamette | Lower_Willamette_Project_Lower_Willamette_PublicRecordsRequest | PublicRecordsRequest | 240000 | 24 | 0 | 0 | PortofKalamaReimbursement | 901910 | 90 | 19 | 10
LWJ | Division 1 | Lower_Willamette_Project_Lower_Willamette |  | General | 241000 | 24 | 10 | 0 | PortofLongviewReimbursement | 901920 | 90 | 19 | 20
LWJ | Division 1 | Lower_Willamette_Project_Lower_Willamette | Lower_Willamette_Project_Lower_Willamette_Outreach | Outreach | 250000 | 25 | 0 | 0 | PortofVancouverReimbursement | 901930 | 90 | 19 | 30
LWJ | Division 1 | Lower_Willamette_Project_Lower_Willamette |  | General | 251000 | 25 | 10 | 0 | PortofWoodlandReimbursement | 901940 | 90 | 19 | 40
LWJ | Division 1 | Lower_Willamette_Project_Lower_Willamette |  | CommunityRelations | 251010 | 25 | 10 | 10 | PortofSt.HelensReimbursement | 902000 | 90 | 20 | 0
LWJ | Division 1 | Lower_Willamette_Project_Lower_Willamette | Lower_Willamette_Project_Lower_Willamette_CostRecovery | CostRecovery | 300000 | 30 | 0 | 0 | StateofOregonReimbursement | 902100 | 90 | 21 | 0
LWJ | Division 1 | Lower_Willamette_Project_Lower_Willamette |  | PRPPursuit | 301000 | 30 | 10 | 0 | StateofofOregonReimbursement | 902100 | 90 | 21 | 0
LWJ | Division 1 | Lower_Willamette_Project_Lower_Willamette | Lower_Willamette_Project_Lower_Willamette_Payments | Payments | 320000 | 32 | 0 | 0 | TSAAgreements | 901500 | 90 | 15 | 0
LWJ | Division 1 | Lower_Willamette_Project_Lower_Willamette |  | LWGGroupPayments | 321200 | 32 | 12 | 0 | Environ.Remediation_PR | 901000 | 90 | 10 | 0
LWJ | Division 1 | Lower_Willamette_Project_Lower_Willamette |  | OversightCosts | 321300 | 32 | 13 | 0 | InsuranceReimbursements | 901100 | 90 | 11 | 0
LWJ | Division 1 | Lower_Willamette_Project_Lower_Willamette |  | EPA | 321310 | 32 | 13 | 10 | ThirdPartySharedCosts | 901200 | 90 | 12 | 0
LWJ | Division 1 | Lower_Willamette_Project_Lower_Willamette |  | DEQ | 321320 | 32 | 13 | 20 | BusinessDevelopment | 901300 | 90 | 13 | 0
LWJ | Division 1 | Lower_Willamette_Project_Lower_Willamette |  | Tribes | 321330 | 32 | 13 | 30 | COEDredgeOperations | 901400 | 90 | 14 | 0
LWJ | Division 1 | Lower_Willamette_Project_Lower_Willamette |  | Trustees | 321340 | 32 | 13 | 40 | BusinessEnergyTaxCredi | 901600 | 90 | 16 | 0
LWJ | Division 1 | Lower_Willamette_Project_Lower_Willamette | Lower_Willamette_Project_Lower_Willamette_Contingency | Contingency | 790000 | 79 | 0 | 0 | SEPProgram | 901700 | 90 | 17 | 0
LWJ | Division 1 | Lower_Willamette_Project_Lower_Willamette |  | CASS | 909000 | 90 | 90 | 0 | IntergovernmentalAgreeme | 901800 | 90 | 18 | 0
LND | Division 1 | Land_Acquisition | Land_Acquisition_Acquisition | Acquisition | 160000 | 16 | 0 | 0 | PortofKalamaReimburse | 901910 | 90 | 19 | 10
LND | Division 1 | Land_Acquisition |  | General | 161000 | 16 | 10 | 0 | PortofLongviewReimbur | 901920 | 90 | 19 | 20
LND | Division 1 | Land_Acquisition |  | Equalization | 161100 | 16 | 11 | 0 | PortofVancouverReimbu | 901930 | 90 | 19 | 30
LND | Division 1 | Land_Acquisition |  | Demolition | 161200 | 16 | 12 | 0 | PortofWoodlandReimbur | 901940 | 90 | 19 | 40
LND | Division 1 | Land_Acquisition |  | RelocationAssistance | 161300 | 16 | 13 | 0 | PortofSt.HelensReimbu | 902000 | 90 | 20 | 0
LND | Division 1 | Land_Acquisition |  | Appraisals | 161400 | 16 | 14 | 0 | StateofOregonReimburse | 902100 | 90 | 21 | 0
LND | Division 1 | Land_Acquisition |  | EnvironmentalAssessments | 161500 | 16 | 15 | 0 | OECDD_$27.7M | 902200 | 90 | 22 | 0
LND | Division 1 | Land_Acquisition |  | Condemnation | 161600 | 16 | 16 | 0
LND | Division 1 | Land_Acquisition |  | Inspection | 161700 | 16 | 17 | 0
LND | Division 1 | Land_Acquisition |  | TitleWork | 161800 | 16 | 18 | 0
LND | Division 1 | Land_Acquisition |  | Survey | 162200 | 16 | 22 | 0
LND | Division 1 | Land_Acquisition | Land_Acquisition_Contingency | Contingency | 790000 | 79 | 0 | 0
K9 | Division 1 | K9_Program | K9_Program_ProjectAdminandMgmt | ProjectAdminandMgmt | 100000 | 10 | 0 | 0
K9 | Division 1 | K9_Program |  | General | 101000 | 10 | 10 | 0
K9 | Division 1 | K9_Program |  | Meetings | 101100 | 10 | 11 | 0
K9 | Division 1 | K9_Program |  | ProjectMgmt | 101200 | 10 | 12 | 0
K9 | Division 1 | K9_Program | K9_Program_Training | Training | 290000 | 29 | 0 | 0
K9 | Division 1 | K9_Program |  | CoreUserTraining | 291000 | 29 | 10 | 0
K9 | Division 1 | K9_Program | K9_Program_Operations | Operations | 310000 | 31 | 0 | 0
K9 | Division 1 | K9_Program |  | LevelGreen_Yellow | 311000 | 31 | 10 | 0
K9 | Division 1 | K9_Program |  | LevelOrange | 311100 | 31 | 11 | 0
K9 | Division 1 | K9_Program |  | LevelRed | 311200 | 31 | 12 | 0
K9 | Division 1 | K9_Program |  | KennelingandCare | 311300 | 31 | 13 | 0
K9 | Division 1 | K9_Program |  | VehicleMgmt | 311400 | 31 | 14 | 0
K9 | Division 1 | K9_Program |  | VeternaryCare | 311500 | 31 | 15 | 0
K9 | Division 1 | K9_Program |  | Communications | 311600 | 31 | 16 | 0
K9 | Division 1 | K9_Program |  | MiscK9Costs | 311700 | 31 | 17 | 0
K9 | Division 1 | K9_Program | K9_Program_Contingency | Contingency | 790000 | 79 | 0 | 0
K9 | Division 1 | K9_Program | K9_Program_OtherReimbursements | OtherReimbursements | 900000 | 90 | 0 | 0
K9 | Division 1 | K9_Program |  | TSAAgreements | 901500 | 90 | 15 | 0
K9 | Division 1 | K9_Program |  | CASS | 909000 | 90 | 90 | 0
IT | Division 1 | IT | IT_ProjectAdminandMgmt | ProjectAdminandMgmt | 100000 | 10 | 0 | 0
IT | Division 1 | IT |  | General | 101000 | 10 | 10 | 0
IT | Division 1 | IT |  | Meetings | 101100 | 10 | 11 | 0
IT | Division 1 | IT |  | ProjectMgmt | 101200 | 10 | 12 | 0
IT | Division 1 | IT | IT_BusinessContinuity | BusinessContinuity | 110000 | 11 | 0 | 0
IT | Division 1 | IT |  | General | 111000 | 11 | 10 | 0
IT | Division 1 | IT | IT_AnalysisandRequirementsDefinition | AnalysisandRequirementsDefinition | 120000 | 12 | 0 | 0
IT | Division 1 | IT |  | General | 121000 | 12 | 10 | 0
IT | Division 1 | IT |  | DevelopandIssueRFP | 121100 | 12 | 11 | 0
IT | Division 1 | IT |  | SelectVendor | 121200 | 12 | 12 | 0
IT | Division 1 | IT | IT_Security | Security | 130000 | 13 | 0 | 0
IT | Division 1 | IT |  | General | 131000 | 13 | 10 | 0
IT | Division 1 | IT | IT_Design | Design | 140000 | 14 | 0 | 0
IT | Division 1 | IT |  | General | 141000 | 14 | 10 | 0
IT | Division 1 | IT |  | OutsideDesignServices | 141010 | 14 | 10 | 10
IT | Division 1 | IT |  | SpecificationDevelopment | 141100 | 14 | 11 | 0
IT | Division 1 | IT |  | RandD | 141200 | 14 | 12 | 0
IT | Division 1 | IT |  | ITDesignSupport | 142600 | 14 | 26 | 0
IT | Division 1 | IT |  | MaintenanceDesignSupport | 142700 | 14 | 27 | 0
IT | Division 1 | IT | IT_Acquisition | Acquisition | 160000 | 16 | 0 | 0
IT | Division 1 | IT |  | Contract | 162300 | 16 | 23 | 0
IT | Division 1 | IT |  | Procurement | 162400 | 16 | 24 | 0
IT | Division 1 | IT |  | Delivery | 162500 | 16 | 25 | 0
IT | Division 1 | IT | IT_Development | Development | 170000 | 17 | 0 | 0
IT | Division 1 | IT |  | DatabaseAdministration | 171000 | 17 | 10 | 0
IT | Division 1 | IT |  | SoftwareDevelopmentandConfiguration | 171100 | 17 | 11 | 0
IT | Division 1 | IT |  | IntegrationDevelopment | 171200 | 17 | 12 | 0
IT | Division 1 | IT |  | InterfaceDevelopment | 171300 | 17 | 13 | 0
IT | Division 1 | IT |  | ConversionDevelopment | 171400 | 17 | 14 | 0
IT | Division 1 | IT |  | OutsideDesignServices | 171510 | 17 | 15 | 10
IT | Division 1 | IT | IT_Implementation | Implementation | 180000 | 18 | 0 | 0
IT | Division 1 | IT |  | HardwareInstallation | 181400 | 18 | 14 | 0
IT | Division 1 | IT |  | DatabaseInstallation | 181500 | 18 | 15 | 0
IT | Division 1 | IT |  | SoftwareInstallation | 181600 | 18 | 16 | 0
IT | Division 1 | IT |  | ITConversion | 181700 | 18 | 17 | 0
IT | Division 1 | IT | IT_Construction | Construction | 190000 | 19 | 0 | 0
IT | Division 1 | IT |  | OutsideConstructionServices | 191810 | 19 | 18 | 10
IT | Division 1 | IT | IT_Documentation | Documentation | 260000 | 26 | 0 | 0
IT | Division 1 | IT |  | TechnicalDocumentation | 261000 | 26 | 10 | 0
IT | Division 1 | IT |  | EndUserDocumentation | 261100 | 26 | 11 | 0
IT | Division 1 | IT |  | MaintenanceDocumentation | 261200 | 26 | 12 | 0
IT | Division 1 | IT |  | SupportDocumentation | 261300 | 26 | 13 | 0
IT | Division 1 | IT |  | TrainingMaterials | 261400 | 26 | 14 | 0
IT | Division 1 | IT | IT_Testing | Testing | 280000 | 28 | 0 | 0
IT | Division 1 | IT |  | General | 281000 | 28 | 10 | 0
IT | Division 1 | IT | IT_Training | Training | 290000 | 29 | 0 | 0
IT | Division 1 | IT |  | CoreUserTraining | 291000 | 29 | 10 | 0
IT | Division 1 | IT |  | EndUserTraining | 291100 | 29 | 11 | 0
IT | Division 1 | IT |  | SupportTeamTraining | 291200 | 29 | 12 | 0
IT | Division 1 | IT | IT_ProjectCloseOut | ProjectCloseOut | 780000 | 78 | 0 | 0
IT | Division 1 | IT |  | General | 781000 | 78 | 10 | 0
IT | Division 1 | IT | IT_Contingency | Contingency | 790000 | 79 | 0 | 0
IT | Division 1 | IT |  | CASS | 909000 | 90 | 90 | 0
EMR | Division 1 | Emergency | Emergency_Insurance_FEMATracking | Insurance_FEMATracking | 390000 | 39 | 0 | 0
EMR | Division 1 | Emergency |  | Preservation_Prevention | 391000 | 39 | 10 | 0
EMR | Division 1 | Emergency |  | Clean_Up | 391100 | 39 | 11 | 0
EMR | Division 1 | Emergency |  | Damages | 391200 | 39 | 12 | 0
EMR | Division 1 | Emergency |  | EOC | 391300 | 39 | 13 | 0
EMR | Division 1 | Emergency | Emergency_Contingency | Contingency | 790000 | 79 | 0 | 0
FIN | Division 1 | Financing | Financing_ProjectAdminandMgmt | ProjectAdminandMgmt | 100000 | 10 | 0 | 0
FIN | Division 1 | Financing |  | General | 101000 | 10 | 10 | 0
FIN | Division 1 | Financing |  | FinancialSupport | 101700 | 10 | 17 | 0
FIN | Division 1 | Financing | Financing_Contingency | Contingency | 790000 | 79 | 0 | 0
FIN | Division 1 | Financing |  | CASS | 909000 | 90 | 90 | 0
IMP | Division 1 | Improve_River_Miles_Channel_Deepening | Improve_River_Miles_Channel_Deepening_ProjectAdminandMgmt | ProjectAdminandMgmt | 100000 | 10 | 0 | 0
IMP | Division 1 | Improve_River_Miles_Channel_Deepening |  | General | 101000 | 10 | 10 | 0
IMP | Division 1 | Improve_River_Miles_Channel_Deepening | Improve_River_Miles_Channel_Deepening_Construction | Construction | 190000 | 19 | 0 | 0
IMP | Division 1 | Improve_River_Miles_Channel_Deepening |  | Contract | 191000 | 19 | 10 | 0
IMP | Division 1 | Improve_River_Miles_Channel_Deepening | Improve_River_Miles_Channel_Deepening_Contingency | Contingency | 790000 | 79 | 0 | 0
EQP | Division 1 | Equipment_Purchases | Equipment_Purchases_ProjectAdminandMgmt | ProjectAdminandMgmt | 100000 | 10 | 0 | 0
EQP | Division 1 | Equipment_Purchases |  | General | 101000 | 10 | 10 | 0
EQP | Division 1 | Equipment_Purchases |  | ProjectMgmt | 101200 | 10 | 12 | 0
EQP | Division 1 | Equipment_Purchases | Equipment_Purchases_AnalysisandRequirementsDefinition | AnalysisandRequirementsDefinition | 120000 | 12 | 0 | 0
EQP | Division 1 | Equipment_Purchases |  | General | 121000 | 12 | 10 | 0
EQP | Division 1 | Equipment_Purchases |  | DevelopandIssueRFP | 121100 | 12 | 11 | 0
EQP | Division 1 | Equipment_Purchases |  | SelectVendor | 121200 | 12 | 12 | 0
EQP | Division 1 | Equipment_Purchases | Equipment_Purchases_Design | Design | 140000 | 14 | 0 | 0
EQP | Division 1 | Equipment_Purchases |  | General | 141000 | 14 | 10 | 0
EQP | Division 1 | Equipment_Purchases |  | OutsideDesignServices | 141010 | 14 | 10 | 10
EQP | Division 1 | Equipment_Purchases |  | SpecificationDevelopment | 141100 | 14 | 11 | 0
EQP | Division 1 | Equipment_Purchases |  | RandD | 141200 | 14 | 12 | 0
EQP | Division 1 | Equipment_Purchases |  | PEDesign | 141700 | 14 | 17 | 0
EQP | Division 1 | Equipment_Purchases |  | ITDesignSupport | 142600 | 14 | 26 | 0
EQP | Division 1 | Equipment_Purchases |  | MaintenanceDesignSupport | 142700 | 14 | 27 | 0
EQP | Division 1 | Equipment_Purchases | Equipment_Purchases_Acquisition | Acquisition | 160000 | 16 | 0 | 0
EQP | Division 1 | Equipment_Purchases |  | Contract | 162300 | 16 | 23 | 0
EQP | Division 1 | Equipment_Purchases |  | Procurement | 162400 | 16 | 24 | 0
EQP | Division 1 | Equipment_Purchases |  | Delivery | 162500 | 16 | 25 | 0
EQP | Division 1 | Equipment_Purchases | Equipment_Purchases_Development | Development | 170000 | 17 | 0 | 0
EQP | Division 1 | Equipment_Purchases |  | OutsideDesignServices | 171510 | 17 | 15 | 10
EQP | Division 1 | Equipment_Purchases | Equipment_Purchases_Implementation | Implementation | 180000 | 18 | 0 | 0
EQP | Division 1 | Equipment_Purchases |  | EquipmentInstallation | 181800 | 18 | 18 | 0
EQP | Division 1 | Equipment_Purchases | Equipment_Purchases_Construction | Construction | 190000 | 19 | 0 | 0
EQP | Division 1 | Equipment_Purchases |  | Contract | 191000 | 19 | 10 | 0
EQP | Division 1 | Equipment_Purchases |  | EquipmentContracts | 191100 | 19 | 11 | 0
EQP | Division 1 | Equipment_Purchases |  | Inspection | 191300 | 19 | 13 | 0
EQP | Division 1 | Equipment_Purchases |  | EngineeringSupport | 191800 | 19 | 18 | 0
EQP | Division 1 | Equipment_Purchases |  | OutsideConstructionServices | 191810 | 19 | 18 | 10
EQP | Division 1 | Equipment_Purchases |  | Maintenance | 191900 | 19 | 19 | 0
EQP | Division 1 | Equipment_Purchases | Equipment_Purchases_Outreach | Outreach | 250000 | 25 | 0 | 0
EQP | Division 1 | Equipment_Purchases |  | General | 251000 | 25 | 10 | 0
EQP | Division 1 | Equipment_Purchases |  | EvaluationProcess | 251400 | 25 | 14 | 0
EQP | Division 1 | Equipment_Purchases | Equipment_Purchases_Testing | Testing | 280000 | 28 | 0 | 0
EQP | Division 1 | Equipment_Purchases |  | General | 281000 | 28 | 10 | 0
EQP | Division 1 | Equipment_Purchases | Equipment_Purchases_Training | Training | 290000 | 29 | 0 | 0
EQP | Division 1 | Equipment_Purchases |  | CoreUserTraining | 291000 | 29 | 10 | 0
EQP | Division 1 | Equipment_Purchases |  | EndUserTraining | 291100 | 29 | 11 | 0
EQP | Division 1 | Equipment_Purchases |  | SupportTeamTraining | 291200 | 29 | 12 | 0
EQP | Division 1 | Equipment_Purchases | Equipment_Purchases_ProjectCloseOut | ProjectCloseOut | 780000 | 78 | 0 | 0
EQP | Division 1 | Equipment_Purchases |  | General | 781000 | 78 | 10 | 0
EQP | Division 1 | Equipment_Purchases | Equipment_Purchases_Contingency | Contingency | 790000 | 79 | 0 | 0
EQP | Division 1 | Equipment_Purchases |  | CASS | 909000 | 90 | 90 | 0
ENG | Division 1 | Engineering_Master | Engineering_Master_ProjectAdminandMgmt | ProjectAdminandMgmt | 100000 | 10 | 0 | 0
ENG | Division 1 | Engineering_Master |  | General | 101000 | 10 | 10 | 0
ENG | Division 1 | Engineering_Master |  | Development | 101300 | 10 | 13 | 0
ENG | Division 1 | Engineering_Master |  | Design | 101400 | 10 | 14 | 0
ENG | Division 1 | Engineering_Master |  | Construction | 101500 | 10 | 15 | 0
ENG | Division 1 | Engineering_Master | Engineering_Master_Design | Design | 140000 | 14 | 0 | 0
ENG | Division 1 | Engineering_Master |  | OutsideDesignServices | 141010 | 14 | 10 | 10
ENG | Division 1 | Engineering_Master |  | SpecificationDevelopment | 141100 | 14 | 11 | 0
ENG | Division 1 | Engineering_Master |  | Environmental | 141600 | 14 | 16 | 0
ENG | Division 1 | Engineering_Master |  | PEDesign | 141700 | 14 | 17 | 0
ENG | Division 1 | Engineering_Master |  | Survey | 141800 | 14 | 18 | 0
ENG | Division 1 | Engineering_Master |  | DrawingandDevelopment | 141900 | 14 | 19 | 0
ENG | Division 1 | Engineering_Master |  | PublicAffairs | 142000 | 14 | 20 | 0
ENG | Division 1 | Engineering_Master |  | Construction_InspectionSupport | 142100 | 14 | 21 | 0
ENG | Division 1 | Engineering_Master |  | ITDesignSupport | 142600 | 14 | 26 | 0
ENG | Division 1 | Engineering_Master |  | MaintenanceDesignSupport | 142700 | 14 | 27 | 0
ENG | Division 1 | Engineering_Master | Engineering_Master_Development | Development | 170000 | 17 | 0 | 0
ENG | Division 1 | Engineering_Master |  | ConceptualDesign | 171500 | 17 | 15 | 0
ENG | Division 1 | Engineering_Master |  | OutsideDesignServices | 171510 | 17 | 15 | 10
ENG | Division 1 | Engineering_Master |  | PEDesign_Support | 171600 | 17 | 16 | 0
ENG | Division 1 | Engineering_Master |  | Survey | 171700 | 17 | 17 | 0
ENG | Division 1 | Engineering_Master |  | Contract_Drawings | 171800 | 17 | 18 | 0
ENG | Division 1 | Engineering_Master |  | Environmental | 171900 | 17 | 19 | 0
ENG | Division 1 | Engineering_Master |  | ActionPlan | 171910 | 17 | 19 | 10
ENG | Division 1 | Engineering_Master |  | PublicAffairs | 172000 | 17 | 20 | 0
ENG | Division 1 | Engineering_Master |  | Planning | 172100 | 17 | 21 | 0
ENG | Division 1 | Engineering_Master |  | Maintenance | 172200 | 17 | 22 | 0
ENG | Division 1 | Engineering_Master |  | IT | 172300 | 17 | 23 | 0
ENG | Division 1 | Engineering_Master |  | Construction_InspectionSupport | 172400 | 17 | 24 | 0
ENG | Division 1 | Engineering_Master | Engineering_Master_Construction | Construction | 190000 | 19 | 0 | 0
ENG | Division 1 | Engineering_Master |  | Contract | 191000 | 19 | 10 | 0
ENG | Division 1 | Engineering_Master |  | EquipmentContracts | 191100 | 19 | 11 | 0
ENG | Division 1 | Engineering_Master |  | Management | 191200 | 19 | 12 | 0
ENG | Division 1 | Engineering_Master |  | Inspection | 191300 | 19 | 13 | 0
ENG | Division 1 | Engineering_Master |  | Testing | 191400 | 19 | 14 | 0
ENG | Division 1 | Engineering_Master |  | Survey | 191500 | 19 | 15 | 0
ENG | Division 1 | Engineering_Master |  | Environmental | 191600 | 19 | 16 | 0
ENG | Division 1 | Engineering_Master |  | PublicAffairs | 191700 | 19 | 17 | 0
ENG | Division 1 | Engineering_Master |  | EngineeringSupport | 191800 | 19 | 18 | 0
ENG | Division 1 | Engineering_Master |  | OutsideConstructionServices | 191810 | 19 | 18 | 10
ENG | Division 1 | Engineering_Master |  | Maintenance | 191900 | 19 | 19 | 0
ENG | Division 1 | Engineering_Master |  | IT | 192000 | 19 | 20 | 0
ENG | Division 1 | Engineering_Master |  | InsurancePremiums | 192500 | 19 | 25 | 0
ENG | Division 1 | Engineering_Master |  | Workers'Compensation | 192510 | 19 | 25 | 10
ENG | Division 1 | Engineering_Master |  | GeneralLiability | 192520 | 19 | 25 | 20
ENG | Division 1 | Engineering_Master |  | ExcessLiability | 192530 | 19 | 25 | 30
ENG | Division 1 | Engineering_Master |  | Contractors'PollutionLiability | 192540 | 19 | 25 | 40
ENG | Division 1 | Engineering_Master |  | Builders'Risk | 192550 | 19 | 25 | 50
ENG | Division 1 | Engineering_Master |  | Broker_AdminFee | 192560 | 19 | 25 | 60
ENG | Division 1 | Engineering_Master |  | InsuranceClaims | 192600 | 19 | 26 | 0
ENG | Division 1 | Engineering_Master |  | Workers'Compensation | 192610 | 19 | 26 | 10
ENG | Division 1 | Engineering_Master |  | GeneralLiability | 192620 | 19 | 26 | 20
ENG | Division 1 | Engineering_Master |  | ExcessLiability | 192630 | 19 | 26 | 30
ENG | Division 1 | Engineering_Master |  | Contractors'PollutionLiability | 192640 | 19 | 26 | 40
ENG | Division 1 | Engineering_Master |  | Builders'Risk | 192650 | 19 | 26 | 50
ENG | Division 1 | Engineering_Master |  | InsuranceCollateral | 192700 | 19 | 27 | 0
ENG | Division 1 | Engineering_Master |  | Workers'Compensation | 192710 | 19 | 27 | 10
ENG | Division 1 | Engineering_Master | Engineering_Master_Permitting | Permitting | 200000 | 20 | 0 | 0
ENG | Division 1 | Engineering_Master |  | Corps | 201100 | 20 | 11 | 0
ENG | Division 1 | Engineering_Master |  | Federal | 201200 | 20 | 12 | 0
ENG | Division 1 | Engineering_Master |  | State | 201300 | 20 | 13 | 0
ENG | Division 1 | Engineering_Master |  | City | 201400 | 20 | 14 | 0
ENG | Division 1 | Engineering_Master | Engineering_Master_Legal_Regulatory | Legal_Regulatory | 230000 | 23 | 0 | 0
ENG | Division 1 | Engineering_Master |  | Design | 231000 | 23 | 10 | 0
ENG | Division 1 | Engineering_Master |  | Construction | 231100 | 23 | 11 | 0
ENG | Division 1 | Engineering_Master |  | Development | 231200 | 23 | 12 | 0
ENG | Division 1 | Engineering_Master | Engineering_Master_ProjectCloseOut | ProjectCloseOut | 780000 | 78 | 0 | 0
ENG | Division 1 | Engineering_Master |  | AsBuilts | 781100 | 78 | 11 | 0
ENG | Division 1 | Engineering_Master |  | Survey | 781200 | 78 | 12 | 0
ENG | Division 1 | Engineering_Master |  | TechnicalReferenceCenter | 781300 | 78 | 13 | 0
ENG | Division 1 | Engineering_Master |  | GeographicInformationSystem | 781400 | 78 | 14 | 0
ENG | Division 1 | Engineering_Master | Engineering_Master_Contingency | Contingency | 790000 | 79 | 0 | 0
ENG | Division 1 | Engineering_Master |  | CASS | 909000 | 90 | 90 | 0
REM | Division 1 | Reimbursements | Reimbursements_OtherReimbursements | OtherReimbursements | 900000 | 90 | 0 | 0
REM | Division 1 | Reimbursements |  | Environ.Remediation_PR | 901000 | 90 | 10 | 0
REM | Division 1 | Reimbursements |  | InsuranceReimbursements | 901100 | 90 | 11 | 0
REM | Division 1 | Reimbursements |  | ThirdPartySharedCosts | 901200 | 90 | 12 | 0
REM | Division 1 | Reimbursements |  | BusinessDevelopment | 901300 | 90 | 13 | 0
REM | Division 1 | Reimbursements |  | COEDredgeOperations | 901400 | 90 | 14 | 0
REM | Division 1 | Reimbursements |  | TSAAgreements | 901500 | 90 | 15 | 0
REM | Division 1 | Reimbursements |  | BusinessEnergyTaxCredi | 901600 | 90 | 16 | 0
REM | Division 1 | Reimbursements |  | SEPProgram | 901700 | 90 | 17 | 0
REM | Division 1 | Reimbursements |  | IntergovernmentalAgreeme | 901800 | 90 | 18 | 0
REM | Division 1 | Reimbursements |  | WAPortsReimbursement | 901900 | 90 | 19 | 0
REM | Division 1 | Reimbursements |  | PortofKalamaReimburse | 901910 | 90 | 19 | 10
REM | Division 1 | Reimbursements |  | PortofLongviewReimbur | 901920 | 90 | 19 | 20
REM | Division 1 | Reimbursements |  | PortofVancouverReimbu | 901930 | 90 | 19 | 30
REM | Division 1 | Reimbursements |  | PortofWoodlandReimbur | 901940 | 90 | 19 | 40
REM | Division 1 | Reimbursements |  | PortofSt.HelensReimbu | 902000 | 90 | 20 | 0
REM | Division 1 | Reimbursements |  | StateofOregonReimburse | 902100 | 90 | 21 | 0
REM | Division 1 | Reimbursements |  | OECDD_$27.7M | 902200 | 90 | 22 | 0
EN4 | Division 1 | Engineering_-_Small_Project | Engineering_-_Small_Project_ProjectAdminandMgmt | ProjectAdminandMgmt | 100000 | 10 | 0 | 0
EN4 | Division 1 | Engineering_-_Small_Project |  | General | 101000 | 10 | 10 | 0
EN4 | Division 1 | Engineering_-_Small_Project | Engineering_-_Small_Project_Design | Design | 140000 | 14 | 0 | 0
EN4 | Division 1 | Engineering_-_Small_Project |  | OutsideDesignServices | 141010 | 14 | 10 | 10
EN4 | Division 1 | Engineering_-_Small_Project |  | PEDesign | 141700 | 14 | 17 | 0
EN4 | Division 1 | Engineering_-_Small_Project |  | ITDesignSupportContract | 142600 | 14 | 26 | 0
EN4 | Division 1 | Engineering_-_Small_Project |  | MaintenanceDesignSupport | 142700 | 14 | 27 | 0
EN4 | Division 1 | Engineering_-_Small_Project | Engineering_-_Small_Project_Acquisition | Acquisition | 160000 | 16 | 0 | 0
EN4 | Division 1 | Engineering_-_Small_Project |  | General | 161000 | 16 | 10 | 0
EN4 | Division 1 | Engineering_-_Small_Project | Engineering_-_Small_Project_Development | Development | 170000 | 17 | 0 | 0
EN4 | Division 1 | Engineering_-_Small_Project |  | OutsideDesignServices | 171510 | 17 | 15 | 10
EN4 | Division 1 | Engineering_-_Small_Project | Engineering_-_Small_Project_Construction | Construction | 190000 | 19 | 0 | 0
EN4 | Division 1 | Engineering_-_Small_Project |  | Contract | 191000 | 19 | 10 | 0
EN4 | Division 1 | Engineering_-_Small_Project |  | EquipmentContracts | 191100 | 19 | 11 | 0
EN4 | Division 1 | Engineering_-_Small_Project |  | Inspection | 191300 | 19 | 13 | 0
EN4 | Division 1 | Engineering_-_Small_Project |  | Testing | 191400 | 19 | 14 | 0
EN4 | Division 1 | Engineering_-_Small_Project |  | Survey | 191500 | 19 | 15 | 0
EN4 | Division 1 | Engineering_-_Small_Project |  | EngineeringSupport | 191800 | 19 | 18 | 0
EN4 | Division 1 | Engineering_-_Small_Project | Engineering_-_Small_Project_ProjectCloseOut | ProjectCloseOut | 780000 | 78 | 0 | 0
EN4 | Division 1 | Engineering_-_Small_Project |  | AsBuilts | 781100 | 78 | 11 | 0
EN4 | Division 1 | Engineering_-_Small_Project |  | TechnicalReferenceCenter | 781300 | 78 | 13 | 0
EN4 | Division 1 | Engineering_-_Small_Project | Engineering_-_Small_Project_Contingency | Contingency | 790000 | 79 | 0 | 0
EN4 | Division 1 | Engineering_-_Small_Project |  | CASS | 909000 | 90 | 90 | 0
EN3 | Division 1 | Engineering_with_Environmental | Engineering_with_Environmental_ProjectAdminandMgmt | ProjectAdminandMgmt | 100000 | 10 | 0 | 0
EN3 | Division 1 | Engineering_with_Environmental |  | General | 101000 | 10 | 10 | 0
EN3 | Division 1 | Engineering_with_Environmental |  | Develop | 101300 | 10 | 13 | 0
EN3 | Division 1 | Engineering_with_Environmental |  | Design | 101400 | 10 | 14 | 0
EN3 | Division 1 | Engineering_with_Environmental |  | Construction | 101500 | 10 | 15 | 0
EN3 | Division 1 | Engineering_with_Environmental | Engineering_with_Environmental_Design | Design | 140000 | 14 | 0 | 0
EN3 | Division 1 | Engineering_with_Environmental |  | OutsideDesignServices | 141010 | 14 | 10 | 10
EN3 | Division 1 | Engineering_with_Environmental |  | SpecificationDevelopment | 141100 | 14 | 11 | 0
EN3 | Division 1 | Engineering_with_Environmental |  | Environmental | 141600 | 14 | 16 | 0
EN3 | Division 1 | Engineering_with_Environmental |  | PEDesign | 141700 | 14 | 17 | 0
EN3 | Division 1 | Engineering_with_Environmental |  | Survey | 141800 | 14 | 18 | 0
EN3 | Division 1 | Engineering_with_Environmental |  | DrawingandDevelopment | 141900 | 14 | 19 | 0
EN3 | Division 1 | Engineering_with_Environmental |  | Construction_InspectionSupport | 142100 | 14 | 21 | 0
EN3 | Division 1 | Engineering_with_Environmental |  | ITDesignSupport | 142600 | 14 | 26 | 0
EN3 | Division 1 | Engineering_with_Environmental |  | MaintenanceDesignSupport | 142700 | 14 | 27 | 0
EN3 | Division 1 | Engineering_with_Environmental | Engineering_with_Environmental_Development | Development | 170000 | 17 | 0 | 0
EN3 | Division 1 | Engineering_with_Environmental |  | ConceptualDesign | 171500 | 17 | 15 | 0
EN3 | Division 1 | Engineering_with_Environmental |  | OutsideDesignServices | 171510 | 17 | 15 | 10
EN3 | Division 1 | Engineering_with_Environmental |  | PEDesign_Support | 171600 | 17 | 16 | 0
EN3 | Division 1 | Engineering_with_Environmental |  | Survey | 171700 | 17 | 17 | 0
EN3 | Division 1 | Engineering_with_Environmental |  | Contract_Drawings | 171800 | 17 | 18 | 0
EN3 | Division 1 | Engineering_with_Environmental |  | Environmental | 171900 | 17 | 19 | 0
EN3 | Division 1 | Engineering_with_Environmental |  | ActionPlan | 171910 | 17 | 19 | 10
EN3 | Division 1 | Engineering_with_Environmental |  | Construction_InspectionSupport | 172400 | 17 | 24 | 0
EN3 | Division 1 | Engineering_with_Environmental | Engineering_with_Environmental_Construction | Construction | 190000 | 19 | 0 | 0
EN3 | Division 1 | Engineering_with_Environmental |  | Contract | 191000 | 19 | 10 | 0
EN3 | Division 1 | Engineering_with_Environmental |  | EquipmentContracts | 191100 | 19 | 11 | 0
EN3 | Division 1 | Engineering_with_Environmental |  | Management | 191200 | 19 | 12 | 0
EN3 | Division 1 | Engineering_with_Environmental |  | Inspection | 191300 | 19 | 13 | 0
EN3 | Division 1 | Engineering_with_Environmental |  | Testing | 191400 | 19 | 14 | 0
EN3 | Division 1 | Engineering_with_Environmental |  | Survey | 191500 | 19 | 15 | 0
EN3 | Division 1 | Engineering_with_Environmental |  | EngineeringSupport | 191800 | 19 | 18 | 0
EN3 | Division 1 | Engineering_with_Environmental |  | Maintenance | 191900 | 19 | 19 | 0
EN3 | Division 1 | Engineering_with_Environmental | Engineering_with_Environmental_Permitting | Permitting | 200000 | 20 | 0 | 0
EN3 | Division 1 | Engineering_with_Environmental |  | Federal | 201200 | 20 | 12 | 0
EN3 | Division 1 | Engineering_with_Environmental |  | State | 201300 | 20 | 13 | 0
EN3 | Division 1 | Engineering_with_Environmental |  | City | 201400 | 20 | 14 | 0
EN3 | Division 1 | Engineering_with_Environmental | Engineering_with_Environmental_ProjectCloseOut | ProjectCloseOut | 780000 | 78 | 0 | 0
EN3 | Division 1 | Engineering_with_Environmental |  | AsBuilts | 781100 | 78 | 11 | 0
EN3 | Division 1 | Engineering_with_Environmental |  | Survey | 781200 | 78 | 12 | 0
EN3 | Division 1 | Engineering_with_Environmental |  | TechnicalReferenceCenter | 781300 | 78 | 13 | 0
EN3 | Division 1 | Engineering_with_Environmental |  | GeographicInformationSystem | 781400 | 78 | 14 | 0
EN3 | Division 1 | Engineering_with_Environmental | Engineering_with_Environmental_Contingency | Contingency | 790000 | 79 | 0 | 0
EN3 | Division 1 | Engineering_with_Environmental |  | CASS | 909000 | 90 | 90 | 0
EN2 | Division 1 | Engineering_with_RFP | Engineering_with_RFP_ProjectAdminandMgmt | ProjectAdminandMgmt | 100000 | 10 | 0 | 0
EN2 | Division 1 | Engineering_with_RFP |  | General | 101000 | 10 | 10 | 0
EN2 | Division 1 | Engineering_with_RFP | Engineering_with_RFP_AnalysisandRequirementsDefinition | AnalysisandRequirementsDefinition | 120000 | 12 | 0 | 0
EN2 | Division 1 | Engineering_with_RFP |  | General | 121000 | 12 | 10 | 0
EN2 | Division 1 | Engineering_with_RFP |  | DevelopandIssueRFP | 121100 | 12 | 11 | 0
EN2 | Division 1 | Engineering_with_RFP |  | SelectVendor | 121200 | 12 | 12 | 0
EN2 | Division 1 | Engineering_with_RFP | Engineering_with_RFP_Design | Design | 140000 | 14 | 0 | 0
EN2 | Division 1 | Engineering_with_RFP |  | OutsideDesignServices | 141010 | 14 | 10 | 10
EN2 | Division 1 | Engineering_with_RFP |  | SpecificationDevelopment | 141100 | 14 | 11 | 0
EN2 | Division 1 | Engineering_with_RFP |  | Environmental | 141600 | 14 | 16 | 0
EN2 | Division 1 | Engineering_with_RFP |  | PEDesign | 141700 | 14 | 17 | 0
EN2 | Division 1 | Engineering_with_RFP |  | Survey | 141800 | 14 | 18 | 0
EN2 | Division 1 | Engineering_with_RFP |  | DrawingandDevelopment | 141900 | 14 | 19 | 0
EN2 | Division 1 | Engineering_with_RFP |  | Construction_InspectionSupport | 142100 | 14 | 21 | 0
EN2 | Division 1 | Engineering_with_RFP |  | ITDesignSupport | 142600 | 14 | 26 | 0
EN2 | Division 1 | Engineering_with_RFP |  | MaintenanceDesignSupport | 142700 | 14 | 27 | 0
EN2 | Division 1 | Engineering_with_RFP | Engineering_with_RFP_Acquisition | Acquisition | 160000 | 16 | 0 | 0
EN2 | Division 1 | Engineering_with_RFP |  | General | 161000 | 16 | 10 | 0
EN2 | Division 1 | Engineering_with_RFP | Engineering_with_RFP_Development | Development | 170000 | 17 | 0 | 0
EN2 | Division 1 | Engineering_with_RFP |  | ConceptualDesign | 171500 | 17 | 15 | 0
EN2 | Division 1 | Engineering_with_RFP |  | OutsideDesignServices | 171510 | 17 | 15 | 10
EN2 | Division 1 | Engineering_with_RFP |  | PEDesign_Support | 171600 | 17 | 16 | 0
EN2 | Division 1 | Engineering_with_RFP |  | Survey | 171700 | 17 | 17 | 0
EN2 | Division 1 | Engineering_with_RFP |  | Contract_Drawings | 171800 | 17 | 18 | 0
EN2 | Division 1 | Engineering_with_RFP |  | Environmental | 171900 | 17 | 19 | 0
EN2 | Division 1 | Engineering_with_RFP |  | ActionPlan | 171910 | 17 | 19 | 10
EN2 | Division 1 | Engineering_with_RFP |  | Construction_InspectionSupport | 172400 | 17 | 24 | 0
EN2 | Division 1 | Engineering_with_RFP | Engineering_with_RFP_Construction | Construction | 190000 | 19 | 0 | 0
EN2 | Division 1 | Engineering_with_RFP |  | Contract | 191000 | 19 | 10 | 0
EN2 | Division 1 | Engineering_with_RFP |  | EquipmentContracts | 191100 | 19 | 11 | 0
EN2 | Division 1 | Engineering_with_RFP |  | Management | 191200 | 19 | 12 | 0
EN2 | Division 1 | Engineering_with_RFP |  | Inspection | 191300 | 19 | 13 | 0
EN2 | Division 1 | Engineering_with_RFP |  | Testing | 191400 | 19 | 14 | 0
EN2 | Division 1 | Engineering_with_RFP |  | Survey | 191500 | 19 | 15 | 0
EN2 | Division 1 | Engineering_with_RFP |  | EngineeringSupport | 191800 | 19 | 18 | 0
EN2 | Division 1 | Engineering_with_RFP |  | OutsideConstructionServices | 191810 | 19 | 18 | 10
EN2 | Division 1 | Engineering_with_RFP |  | Maintenance | 191900 | 19 | 19 | 0
EN2 | Division 1 | Engineering_with_RFP | Engineering_with_RFP_Permitting | Permitting | 200000 | 20 | 0 | 0
EN2 | Division 1 | Engineering_with_RFP |  | City | 201400 | 20 | 14 | 0
EN2 | Division 1 | Engineering_with_RFP | Engineering_with_RFP_ProjectCloseOut | ProjectCloseOut | 780000 | 78 | 0 | 0
EN2 | Division 1 | Engineering_with_RFP |  | AsBuilts | 781100 | 78 | 11 | 0
EN2 | Division 1 | Engineering_with_RFP |  | Survey | 781200 | 78 | 12 | 0
EN2 | Division 1 | Engineering_with_RFP |  | TechnicalReferenceCenter | 781300 | 78 | 13 | 0
EN2 | Division 1 | Engineering_with_RFP |  | GeographicInformationSystem | 781400 | 78 | 14 | 0
EN2 | Division 1 | Engineering_with_RFP | Engineering_with_RFP_Contingency | Contingency | 790000 | 79 | 0 | 0
EN2 | Division 1 | Engineering_with_RFP |  | CASS | 909000 | 90 | 90 | 0
EN1 | Division 1 | Engineering_Standard | Engineering_Standard_ProjectAdminandMgmt | ProjectAdminandMgmt | 100000 | 10 | 0 | 0
EN1 | Division 1 | Engineering_Standard |  | General | 101000 | 10 | 10 | 0
EN1 | Division 1 | Engineering_Standard |  | Design | 101400 | 10 | 14 | 0
EN1 | Division 1 | Engineering_Standard |  | Construction | 101500 | 10 | 15 | 0
EN1 | Division 1 | Engineering_Standard | Engineering_Standard_Design | Design | 140000 | 14 | 0 | 0
EN1 | Division 1 | Engineering_Standard |  | OutsideDesignServices | 141010 | 14 | 10 | 10
EN1 | Division 1 | Engineering_Standard |  | SpecificationDevelopment | 141100 | 14 | 11 | 0
EN1 | Division 1 | Engineering_Standard |  | Environmental | 141600 | 14 | 16 | 0
EN1 | Division 1 | Engineering_Standard |  | PEDesign | 141700 | 14 | 17 | 0
EN1 | Division 1 | Engineering_Standard |  | Survey | 141800 | 14 | 18 | 0
EN1 | Division 1 | Engineering_Standard |  | DrawingandDevelopment | 141900 | 14 | 19 | 0
EN1 | Division 1 | Engineering_Standard |  | Construction_InspectionSupport | 142100 | 14 | 21 | 0
EN1 | Division 1 | Engineering_Standard |  | ITDesignSupport | 142600 | 14 | 26 | 0
EN1 | Division 1 | Engineering_Standard |  | MaintenanceDesignSupport | 142700 | 14 | 27 | 0
EN1 | Division 1 | Engineering_Standard | Engineering_Standard_Acquisition | Acquisition | 160000 | 16 | 0 | 0
EN1 | Division 1 | Engineering_Standard |  | General | 161000 | 16 | 10 | 0
EN1 | Division 1 | Engineering_Standard | Engineering_Standard_Development | Development | 170000 | 17 | 0 | 0
EN1 | Division 1 | Engineering_Standard |  | ConceptualDesign | 171500 | 17 | 15 | 0
EN1 | Division 1 | Engineering_Standard |  | OutsideDesignServices | 171510 | 17 | 15 | 10
EN1 | Division 1 | Engineering_Standard |  | PEDesign_Support | 171600 | 17 | 16 | 0
EN1 | Division 1 | Engineering_Standard | Engineering_Standard_Construction | Construction | 190000 | 19 | 0 | 0
EN1 | Division 1 | Engineering_Standard |  | Contract | 191000 | 19 | 10 | 0
EN1 | Division 1 | Engineering_Standard |  | EquipmentContracts | 191100 | 19 | 11 | 0
EN1 | Division 1 | Engineering_Standard |  | Management | 191200 | 19 | 12 | 0
EN1 | Division 1 | Engineering_Standard |  | Inspection | 191300 | 19 | 13 | 0
EN1 | Division 1 | Engineering_Standard |  | Testing | 191400 | 19 | 14 | 0
EN1 | Division 1 | Engineering_Standard |  | Survey | 191500 | 19 | 15 | 0
EN1 | Division 1 | Engineering_Standard |  | EngineeringSupport | 191800 | 19 | 18 | 0
EN1 | Division 1 | Engineering_Standard |  | OutsideConstructionServices | 191810 | 19 | 18 | 10
EN1 | Division 1 | Engineering_Standard |  | Maintenance | 191900 | 19 | 19 | 0
EN1 | Division 1 | Engineering_Standard |  | IT | 192000 | 19 | 20 | 0
EN1 | Division 1 | Engineering_Standard |  | InsurancePremiums | 192500 | 19 | 25 | 0
EN1 | Division 1 | Engineering_Standard |  | Workers'Compensation | 192510 | 19 | 25 | 10
EN1 | Division 1 | Engineering_Standard |  | GeneralLiability | 192520 | 19 | 25 | 20
EN1 | Division 1 | Engineering_Standard |  | ExcessLiability | 192530 | 19 | 25 | 30
EN1 | Division 1 | Engineering_Standard |  | Contractors'PollutionLiability | 192540 | 19 | 25 | 40
EN1 | Division 1 | Engineering_Standard |  | Builders'Risk | 192550 | 19 | 25 | 50
EN1 | Division 1 | Engineering_Standard |  | Broker_AdminFee | 192560 | 19 | 25 | 60
EN1 | Division 1 | Engineering_Standard |  | InsuranceClaims | 192600 | 19 | 26 | 0
EN1 | Division 1 | Engineering_Standard |  | Workers'Compensation | 192610 | 19 | 26 | 10
EN1 | Division 1 | Engineering_Standard |  | GeneralLiability | 192620 | 19 | 26 | 20
EN1 | Division 1 | Engineering_Standard |  | ExcessLiability | 192630 | 19 | 26 | 30
EN1 | Division 1 | Engineering_Standard |  | Contractors'PollutionLiability | 192640 | 19 | 26 | 40
EN1 | Division 1 | Engineering_Standard |  | Builders'Risk | 192650 | 19 | 26 | 50
EN1 | Division 1 | Engineering_Standard |  | InsuranceCollateral | 192700 | 19 | 27 | 0
EN1 | Division 1 | Engineering_Standard |  | Workers'Compensation | 192710 | 19 | 27 | 10
EN1 | Division 1 | Engineering_Standard | Engineering_Standard_Permitting | Permitting | 200000 | 20 | 0 | 0
EN1 | Division 1 | Engineering_Standard |  | City | 201400 | 20 | 14 | 0
EN1 | Division 1 | Engineering_Standard | Engineering_Standard_ProjectCloseout | ProjectCloseout | 780000 | 78 | 0 | 0
EN1 | Division 1 | Engineering_Standard |  | AsBuilts | 781100 | 78 | 11 | 0
EN1 | Division 1 | Engineering_Standard |  | Survey | 781200 | 78 | 12 | 0
EN1 | Division 1 | Engineering_Standard |  | TechnicalReferenceCenter | 781300 | 78 | 13 | 0
EN1 | Division 1 | Engineering_Standard |  | GeographicInformationSystem | 781400 | 78 | 14 | 0
EN1 | Division 1 | Engineering_Standard | Engineering_Standard_Contingency | Contingency | 790000 | 79 | 0 | 0
EN1 | Division 1 | Engineering_Standard |  | CASS | 909000 | 90 | 90 | 0
EAS | Division 1 | Early_Action_Sites_Lower_Willamette | Early_Action_Sites_Lower_Willamette_ProjectAdminandMgmt | ProjectAdminandMgmt | 100000 | 10 | 0 | 0
EAS | Division 1 | Early_Action_Sites_Lower_Willamette |  | General | 101000 | 10 | 10 | 0
EAS | Division 1 | Early_Action_Sites_Lower_Willamette | Early_Action_Sites_Lower_Willamette_Design | Design | 140000 | 14 | 0 | 0
EAS | Division 1 | Early_Action_Sites_Lower_Willamette |  | OutsideDesignServices | 141010 | 14 | 10 | 10
EAS | Division 1 | Early_Action_Sites_Lower_Willamette |  | RemedialDesign | 141400 | 14 | 14 | 0
EAS | Division 1 | Early_Action_Sites_Lower_Willamette |  | ITDesignSupport | 142600 | 14 | 26 | 0
EAS | Division 1 | Early_Action_Sites_Lower_Willamette |  | MaintenanceDesignSupport | 142700 | 14 | 27 | 0
EAS | Division 1 | Early_Action_Sites_Lower_Willamette | Early_Action_Sites_Lower_Willamette_Planning | Planning | 150000 | 15 | 0 | 0
EAS | Division 1 | Early_Action_Sites_Lower_Willamette |  | SiteInvestigation | 151200 | 15 | 12 | 0
EAS | Division 1 | Early_Action_Sites_Lower_Willamette |  | EE(SiteCharacterization) | 151210 | 15 | 12 | 10
EAS | Division 1 | Early_Action_Sites_Lower_Willamette |  | EE_CAWorkPlan | 151220 | 15 | 12 | 20
EAS | Division 1 | Early_Action_Sites_Lower_Willamette |  | EE_CAPreparation | 151230 | 15 | 12 | 30
EAS | Division 1 | Early_Action_Sites_Lower_Willamette |  | CulturalResources | 151700 | 15 | 17 | 0
EAS | Division 1 | Early_Action_Sites_Lower_Willamette | Early_Action_Sites_Lower_Willamette_Development | Development | 170000 | 17 | 0 | 0
EAS | Division 1 | Early_Action_Sites_Lower_Willamette |  | OutsideDesignServices | 171510 | 17 | 15 | 10
EAS | Division 1 | Early_Action_Sites_Lower_Willamette | Early_Action_Sites_Lower_Willamette_Implementation | Implementation | 180000 | 18 | 0 | 0
EAS | Division 1 | Early_Action_Sites_Lower_Willamette |  | RemedialAction | 181000 | 18 | 10 | 0
EAS | Division 1 | Early_Action_Sites_Lower_Willamette |  | OandM_Monitoring | 181200 | 18 | 12 | 0
EAS | Division 1 | Early_Action_Sites_Lower_Willamette |  | Restoration | 181300 | 18 | 13 | 0
EAS | Division 1 | Early_Action_Sites_Lower_Willamette |  | NRDRestoration_Settlement | 181310 | 18 | 13 | 10
EAS | Division 1 | Early_Action_Sites_Lower_Willamette | Early_Action_Sites_Lower_Willamette_Construction | Construction | 190000 | 19 | 0 | 0
EAS | Division 1 | Early_Action_Sites_Lower_Willamette |  | OutsideConstructionServices | 191810 | 19 | 18 | 10
EAS | Division 1 | Early_Action_Sites_Lower_Willamette | Early_Action_Sites_Lower_Willamette_Legal_Regulatory | Legal_Regulatory | 230000 | 23 | 0 | 0
EAS | Division 1 | Early_Action_Sites_Lower_Willamette |  | Pre_LitigationPreparation | 231300 | 23 | 13 | 0
EAS | Division 1 | Early_Action_Sites_Lower_Willamette |  | LitigationDefense | 231400 | 23 | 14 | 0
EAS | Division 1 | Early_Action_Sites_Lower_Willamette |  | ClosureReport_NFA | 231600 | 23 | 16 | 0
EAS | Division 1 | Early_Action_Sites_Lower_Willamette |  | EnforcementDocuments | 231700 | 23 | 17 | 0
EAS | Division 1 | Early_Action_Sites_Lower_Willamette |  | FiveYearReview | 231800 | 23 | 18 | 0
EAS | Division 1 | Early_Action_Sites_Lower_Willamette |  | ActionMemo | 231900 | 23 | 19 | 0
EAS | Division 1 | Early_Action_Sites_Lower_Willamette |  | Negotiations | 232100 | 23 | 21 | 0
EAS | Division 1 | Early_Action_Sites_Lower_Willamette |  | AOCNegotiations | 232110 | 23 | 21 | 10
EAS | Division 1 | Early_Action_Sites_Lower_Willamette |  | CD_AU_UONegotiations | 232120 | 23 | 21 | 20
EAS | Division 1 | Early_Action_Sites_Lower_Willamette |  | NRDNegotiations | 232130 | 23 | 21 | 30
EAS | Division 1 | Early_Action_Sites_Lower_Willamette | Early_Action_Sites_Lower_Willamette_PublicRecordsRequest | PublicRecordsRequest | 240000 | 24 | 0 | 0
EAS | Division 1 | Early_Action_Sites_Lower_Willamette |  | General | 241000 | 24 | 10 | 0
EAS | Division 1 | Early_Action_Sites_Lower_Willamette | Early_Action_Sites_Lower_Willamette_Outreach | Outreach | 250000 | 25 | 0 | 0
EAS | Division 1 | Early_Action_Sites_Lower_Willamette |  | General | 251000 | 25 | 10 | 0
EAS | Division 1 | Early_Action_Sites_Lower_Willamette |  | CommunityRelations | 251010 | 25 | 10 | 10
EAS | Division 1 | Early_Action_Sites_Lower_Willamette | Early_Action_Sites_Lower_Willamette_CostRecovery | CostRecovery | 300000 | 30 | 0 | 0
EAS | Division 1 | Early_Action_Sites_Lower_Willamette |  | PRPPursuit | 301000 | 30 | 10 | 0
EAS | Division 1 | Early_Action_Sites_Lower_Willamette | Early_Action_Sites_Lower_Willamette_Payments | Payments | 320000 | 32 | 0 | 0
EAS | Division 1 | Early_Action_Sites_Lower_Willamette |  | GroupPayments | 321000 | 32 | 10 | 0
EAS | Division 1 | Early_Action_Sites_Lower_Willamette |  | LWGGroupPayments | 321200 | 32 | 12 | 0
EAS | Division 1 | Early_Action_Sites_Lower_Willamette |  | OversightCosts | 321300 | 32 | 13 | 0
EAS | Division 1 | Early_Action_Sites_Lower_Willamette |  | EPA | 321310 | 32 | 13 | 10
EAS | Division 1 | Early_Action_Sites_Lower_Willamette |  | DEQ | 321320 | 32 | 13 | 20
EAS | Division 1 | Early_Action_Sites_Lower_Willamette |  | Tribes | 321330 | 32 | 13 | 30
EAS | Division 1 | Early_Action_Sites_Lower_Willamette |  | Trustees | 321340 | 32 | 13 | 40
EAS | Division 1 | Early_Action_Sites_Lower_Willamette | Early_Action_Sites_Lower_Willamette_Contingency | Contingency | 790000 | 79 | 0 | 0
EAS | Division 1 | Early_Action_Sites_Lower_Willamette |  | CASS | 909000 | 90 | 90 | 0
CON | Division 1 | Construction_Site_Channel_Deepening | Construction_Site_Channel_Deepening_ProjectAdminandMgmt | ProjectAdminandMgmt | 100000 | 10 | 0 | 0
CON | Division 1 | Construction_Site_Channel_Deepening |  | General | 101000 | 10 | 10 | 0
CON | Division 1 | Construction_Site_Channel_Deepening |  | Development | 101300 | 10 | 13 | 0
CON | Division 1 | Construction_Site_Channel_Deepening |  | Design | 101400 | 10 | 14 | 0
CON | Division 1 | Construction_Site_Channel_Deepening |  | Construction | 101500 | 10 | 15 | 0
CON | Division 1 | Construction_Site_Channel_Deepening | Construction_Site_Channel_Deepening_Design | Design | 140000 | 14 | 0 | 0
CON | Division 1 | Construction_Site_Channel_Deepening |  | SpecificationDevelopment | 141100 | 14 | 11 | 0
CON | Division 1 | Construction_Site_Channel_Deepening |  | Environmental | 141600 | 14 | 16 | 0
CON | Division 1 | Construction_Site_Channel_Deepening |  | PEDesign | 141700 | 14 | 17 | 0
CON | Division 1 | Construction_Site_Channel_Deepening |  | Survey | 141800 | 14 | 18 | 0
CON | Division 1 | Construction_Site_Channel_Deepening |  | DrawingandDevelopment | 141900 | 14 | 19 | 0
CON | Division 1 | Construction_Site_Channel_Deepening |  | PublicAffairs | 142000 | 14 | 20 | 0
CON | Division 1 | Construction_Site_Channel_Deepening |  | Construction_InspectionSupport | 142100 | 14 | 21 | 0
CON | Division 1 | Construction_Site_Channel_Deepening | Construction_Site_Channel_Deepening_Acquisition | Acquisition | 160000 | 16 | 0 | 0
CON | Division 1 | Construction_Site_Channel_Deepening |  | General | 161000 | 16 | 10 | 0
CON | Division 1 | Construction_Site_Channel_Deepening |  | Demolition | 161200 | 16 | 12 | 0
CON | Division 1 | Construction_Site_Channel_Deepening |  | RelocationAssistance | 161300 | 16 | 13 | 0
CON | Division 1 | Construction_Site_Channel_Deepening |  | Appraisals | 161400 | 16 | 14 | 0
CON | Division 1 | Construction_Site_Channel_Deepening |  | EnvironmentalAssessments | 161500 | 16 | 15 | 0
CON | Division 1 | Construction_Site_Channel_Deepening |  | Condemnation | 161600 | 16 | 16 | 0
CON | Division 1 | Construction_Site_Channel_Deepening |  | Inspection | 161700 | 16 | 17 | 0
CON | Division 1 | Construction_Site_Channel_Deepening |  | TitleWork | 161800 | 16 | 18 | 0
CON | Division 1 | Construction_Site_Channel_Deepening |  | Survey | 162200 | 16 | 22 | 0
CON | Division 1 | Construction_Site_Channel_Deepening | Construction_Site_Channel_Deepening_Development | Development | 170000 | 17 | 0 | 0
CON | Division 1 | Construction_Site_Channel_Deepening |  | ConceptualDesign | 171500 | 17 | 15 | 0
CON | Division 1 | Construction_Site_Channel_Deepening |  | PE_DesignSupport | 171600 | 17 | 16 | 0
CON | Division 1 | Construction_Site_Channel_Deepening |  | Survey | 171700 | 17 | 17 | 0
CON | Division 1 | Construction_Site_Channel_Deepening |  | Contract_Drawings | 171800 | 17 | 18 | 0
CON | Division 1 | Construction_Site_Channel_Deepening |  | Environmental | 171900 | 17 | 19 | 0
CON | Division 1 | Construction_Site_Channel_Deepening |  | ActionPlan | 171910 | 17 | 19 | 10
CON | Division 1 | Construction_Site_Channel_Deepening |  | PublicAffairs | 172000 | 17 | 20 | 0
CON | Division 1 | Construction_Site_Channel_Deepening |  | Planning | 172100 | 17 | 21 | 0
CON | Division 1 | Construction_Site_Channel_Deepening |  | Maintenance | 172200 | 17 | 22 | 0
CON | Division 1 | Construction_Site_Channel_Deepening |  | IT | 172300 | 17 | 23 | 0
CON | Division 1 | Construction_Site_Channel_Deepening |  | Construction_InspectionSupport | 172400 | 17 | 24 | 0
CON | Division 1 | Construction_Site_Channel_Deepening | Construction_Site_Channel_Deepening_Construction | Construction | 190000 | 19 | 0 | 0
CON | Division 1 | Construction_Site_Channel_Deepening |  | Contract | 191000 | 19 | 10 | 0
CON | Division 1 | Construction_Site_Channel_Deepening |  | EquipmentContracts | 191100 | 19 | 11 | 0
CON | Division 1 | Construction_Site_Channel_Deepening |  | Management | 191200 | 19 | 12 | 0
CON | Division 1 | Construction_Site_Channel_Deepening |  | Inspection | 191300 | 19 | 13 | 0
CON | Division 1 | Construction_Site_Channel_Deepening |  | Testing | 191400 | 19 | 14 | 0
CON | Division 1 | Construction_Site_Channel_Deepening |  | Survey | 191500 | 19 | 15 | 0
CON | Division 1 | Construction_Site_Channel_Deepening |  | Environmental | 191600 | 19 | 16 | 0
CON | Division 1 | Construction_Site_Channel_Deepening |  | PublicAffairs | 191700 | 19 | 17 | 0
CON | Division 1 | Construction_Site_Channel_Deepening |  | EngineeringSupport | 191800 | 19 | 18 | 0
CON | Division 1 | Construction_Site_Channel_Deepening |  | Maintenance | 191900 | 19 | 19 | 0
CON | Division 1 | Construction_Site_Channel_Deepening |  | IT | 192000 | 19 | 20 | 0
CON | Division 1 | Construction_Site_Channel_Deepening | Construction_Site_Channel_Deepening_Permitting | Permitting | 200000 | 20 | 0 | 0
CON | Division 1 | Construction_Site_Channel_Deepening |  | Corps | 201100 | 20 | 11 | 0
CON | Division 1 | Construction_Site_Channel_Deepening |  | Federal | 201200 | 20 | 12 | 0
CON | Division 1 | Construction_Site_Channel_Deepening |  | State | 201300 | 20 | 13 | 0
CON | Division 1 | Construction_Site_Channel_Deepening |  | City | 201400 | 20 | 14 | 0
CON | Division 1 | Construction_Site_Channel_Deepening | Construction_Site_Channel_Deepening_Legal_Regulatory | Legal_Regulatory | 230000 | 23 | 0 | 0
CON | Division 1 | Construction_Site_Channel_Deepening |  | Design | 231000 | 23 | 10 | 0
CON | Division 1 | Construction_Site_Channel_Deepening |  | Construction | 231100 | 23 | 11 | 0
CON | Division 1 | Construction_Site_Channel_Deepening |  | Development | 231200 | 23 | 12 | 0
CON | Division 1 | Construction_Site_Channel_Deepening |  | LitigationDefense | 231400 | 23 | 14 | 0
CON | Division 1 | Construction_Site_Channel_Deepening | Construction_Site_Channel_Deepening_ProjectCloseOut | ProjectCloseOut | 780000 | 78 | 0 | 0
CON | Division 1 | Construction_Site_Channel_Deepening |  | AsBuilts | 781100 | 78 | 11 | 0
CON | Division 1 | Construction_Site_Channel_Deepening |  | Survey | 781200 | 78 | 12 | 0
CON | Division 1 | Construction_Site_Channel_Deepening |  | TechnicalReferenceCenter | 781300 | 78 | 13 | 0
CON | Division 1 | Construction_Site_Channel_Deepening |  | GeographicInformationSystem | 781400 | 78 | 14 | 0
CON | Division 1 | Construction_Site_Channel_Deepening | Construction_Site_Channel_Deepening_Contingency | Contingency | 790000 | 79 | 0 | 0
BND | Division 1 | Business_Development | Business_Development_ProjectAdminandMgmt | ProjectAdminandMgmt | 100000 | 10 | 0 | 0
BND | Division 1 | Business_Development |  | General | 101000 | 10 | 10 | 0
BND | Division 1 | Business_Development |  | Meetings | 101100 | 10 | 11 | 0
BND | Division 1 | Business_Development |  | ProjectMgmt | 101200 | 10 | 12 | 0
BND | Division 1 | Business_Development |  | Development | 101300 | 10 | 13 | 0
BND | Division 1 | Business_Development |  | Design | 101400 | 10 | 14 | 0
BND | Division 1 | Business_Development |  | Construction | 101500 | 10 | 15 | 0
BND | Division 1 | Business_Development |  | LandAcquisition | 101600 | 10 | 16 | 0
BND | Division 1 | Business_Development |  | FinancialSupport | 101700 | 10 | 17 | 0
BND | Division 1 | Business_Development |  | LegislativeFunding | 101800 | 10 | 18 | 0
BND | Division 1 | Business_Development | Business_Development_Design | Design | 140000 | 14 | 0 | 0
BND | Division 1 | Business_Development |  | General | 141000 | 14 | 10 | 0
BND | Division 1 | Business_Development |  | OutsideDesignServices | 141010 | 14 | 10 | 10
BND | Division 1 | Business_Development |  | RemedialDesign | 141400 | 14 | 14 | 0
BND | Division 1 | Business_Development |  | Restoration | 141500 | 14 | 15 | 0
BND | Division 1 | Business_Development |  | Restore.PlanandDev,Incl.Des. | 141510 | 14 | 15 | 10
BND | Division 1 | Business_Development |  | Environmental | 141600 | 14 | 16 | 0
BND | Division 1 | Business_Development |  | PEDesign | 141700 | 14 | 17 | 0
BND | Division 1 | Business_Development |  | Survey | 141800 | 14 | 18 | 0
BND | Division 1 | Business_Development |  | BidPackage | 142300 | 14 | 23 | 0
BND | Division 1 | Business_Development |  | ITDesignSupport | 142600 | 14 | 26 | 0
BND | Division 1 | Business_Development |  | MaintenanceDesignSupport | 142700 | 14 | 27 | 0
BND | Division 1 | Business_Development | Business_Development_Planning | Planning | 150000 | 15 | 0 | 0
BND | Division 1 | Business_Development |  | General | 151000 | 15 | 10 | 0
BND | Division 1 | Business_Development |  | Assessment_Planning | 151100 | 15 | 11 | 0
BND | Division 1 | Business_Development |  | PreliminaryAssessment | 151110 | 15 | 11 | 10
BND | Division 1 | Business_Development |  | Strategy_Planning | 151120 | 15 | 11 | 20
BND | Division 1 | Business_Development |  | InjuryAssessment | 151130 | 15 | 11 | 30
BND | Division 1 | Business_Development |  | CapacityAnalysis | 151140 | 15 | 11 | 40
BND | Division 1 | Business_Development |  | Environ.Assess_ActionPlan | 151150 | 15 | 11 | 50
BND | Division 1 | Business_Development |  | SiteInvestigation | 151200 | 15 | 12 | 0
BND | Division 1 | Business_Development |  | EE(SiteCharacterization) | 151210 | 15 | 12 | 10
BND | Division 1 | Business_Development |  | EE_CAWorkPlan | 151220 | 15 | 12 | 20
BND | Division 1 | Business_Development |  | EE_CAPreparation | 151230 | 15 | 12 | 30
BND | Division 1 | Business_Development |  | GeneralStormWaterPipes | 151240 | 15 | 12 | 40
BND | Division 1 | Business_Development |  | RemedialInvestigation | 151300 | 15 | 13 | 0
BND | Division 1 | Business_Development |  | CargillOU1 | 151310 | 15 | 13 | 10
BND | Division 1 | Business_Development |  | OU2 | 151320 | 15 | 13 | 20
BND | Division 1 | Business_Development |  | FeasibilityStudy | 151600 | 15 | 16 | 0
BND | Division 1 | Business_Development |  | CulturalResources | 151700 | 15 | 17 | 0
BND | Division 1 | Business_Development |  | TransportationAnalysis | 151800 | 15 | 18 | 0
BND | Division 1 | Business_Development | Business_Development_Acquisition | Acquisition | 160000 | 16 | 0 | 0
BND | Division 1 | Business_Development |  | General | 161000 | 16 | 10 | 0
BND | Division 1 | Business_Development |  | Demolition | 161200 | 16 | 12 | 0
BND | Division 1 | Business_Development |  | RelocationAssistance | 161300 | 16 | 13 | 0
BND | Division 1 | Business_Development |  | Appraisals | 161400 | 16 | 14 | 0
BND | Division 1 | Business_Development |  | EnvironmentalAssessments | 161500 | 16 | 15 | 0
BND | Division 1 | Business_Development |  | Condemnation | 161600 | 16 | 16 | 0
BND | Division 1 | Business_Development |  | Inspection | 161700 | 16 | 17 | 0
BND | Division 1 | Business_Development |  | TitleWork | 161800 | 16 | 18 | 0
BND | Division 1 | Business_Development |  | Survey | 162200 | 16 | 22 | 0
BND | Division 1 | Business_Development | Business_Development_Development | Development | 170000 | 17 | 0 | 0
BND | Division 1 | Business_Development |  | OutsideDesignServices | 171510 | 17 | 15 | 10
BND | Division 1 | Business_Development | Business_Development_Implementation | Implementation | 180000 | 18 | 0 | 0
BND | Division 1 | Business_Development |  | RemedialAction | 181000 | 18 | 10 | 0
BND | Division 1 | Business_Development |  | OandM_Systems | 181100 | 18 | 11 | 0
BND | Division 1 | Business_Development |  | OandM_Monitoring | 181200 | 18 | 12 | 0
BND | Division 1 | Business_Development |  | Restoration | 181300 | 18 | 13 | 0
BND | Division 1 | Business_Development |  | NRDRestoration_Settlement | 181310 | 18 | 13 | 10
BND | Division 1 | Business_Development |  | RestorationImplementation | 181320 | 18 | 13 | 20
BND | Division 1 | Business_Development | Business_Development_Construction | Construction | 190000 | 19 | 0 | 0
BND | Division 1 | Business_Development |  | Contract | 191000 | 19 | 10 | 0
BND | Division 1 | Business_Development |  | EquipmentContracts | 191100 | 19 | 11 | 0
BND | Division 1 | Business_Development |  | Management | 191200 | 19 | 12 | 0
BND | Division 1 | Business_Development |  | Inspection | 191300 | 19 | 13 | 0
BND | Division 1 | Business_Development |  | Testing | 191400 | 19 | 14 | 0
BND | Division 1 | Business_Development |  | Survey | 191500 | 19 | 15 | 0
BND | Division 1 | Business_Development |  | Environmental | 191600 | 19 | 16 | 0
BND | Division 1 | Business_Development |  | OutsideConstructionService | 191810 | 19 | 18 | 10
BND | Division 1 | Business_Development |  | SandSales | 192400 | 19 | 24 | 0
BND | Division 1 | Business_Development | Business_Development_Permitting | Permitting | 200000 | 20 | 0 | 0
BND | Division 1 | Business_Development |  | General | 201000 | 20 | 10 | 0
BND | Division 1 | Business_Development |  | Corps | 201100 | 20 | 11 | 0
BND | Division 1 | Business_Development |  | Federal | 201200 | 20 | 12 | 0
BND | Division 1 | Business_Development |  | State | 201300 | 20 | 13 | 0
BND | Division 1 | Business_Development |  | City | 201400 | 20 | 14 | 0
BND | Division 1 | Business_Development |  | Local | 201500 | 20 | 15 | 0
BND | Division 1 | Business_Development | Business_Development_Maintenance | Maintenance | 220000 | 22 | 0 | 0
BND | Division 1 | Business_Development |  | Environmental | 221000 | 22 | 10 | 0
BND | Division 1 | Business_Development |  | EngineeringSupport | 221100 | 22 | 11 | 0
BND | Division 1 | Business_Development |  | OperatingDeptSupport | 221200 | 22 | 12 | 0
BND | Division 1 | Business_Development |  | BidPackage | 221300 | 22 | 13 | 0
BND | Division 1 | Business_Development |  | Monitoring | 221400 | 22 | 14 | 0
BND | Division 1 | Business_Development | Business_Development_Legal_Regulatory | Legal_Regulatory | 230000 | 23 | 0 | 0
BND | Division 1 | Business_Development |  | Design | 231000 | 23 | 10 | 0
BND | Division 1 | Business_Development |  | Construction | 231100 | 23 | 11 | 0
BND | Division 1 | Business_Development |  | Development | 231200 | 23 | 12 | 0
BND | Division 1 | Business_Development |  | Pre_LitigationPreparation | 231300 | 23 | 13 | 0
BND | Division 1 | Business_Development |  | LitigationDefense | 231400 | 23 | 14 | 0
BND | Division 1 | Business_Development |  | Litigate | 231500 | 23 | 15 | 0
BND | Division 1 | Business_Development |  | ClosureReport_NFA | 231600 | 23 | 16 | 0
BND | Division 1 | Business_Development |  | EnforcementDocuments | 231700 | 23 | 17 | 0
BND | Division 1 | Business_Development |  | FiveYearrevuew | 231800 | 23 | 18 | 0
BND | Division 1 | Business_Development |  | ActionMemo | 231900 | 23 | 19 | 0
BND | Division 1 | Business_Development |  | Compliance | 232000 | 23 | 20 | 0
BND | Division 1 | Business_Development |  | WRDA | 232010 | 23 | 20 | 10
BND | Division 1 | Business_Development |  | Negotiations | 232100 | 23 | 21 | 0
BND | Division 1 | Business_Development |  | AOCNegotiations | 232110 | 23 | 21 | 10
BND | Division 1 | Business_Development |  | CD_AO_UONegotiations | 232120 | 23 | 21 | 20
BND | Division 1 | Business_Development |  | NRDNegotiations | 232130 | 23 | 21 | 30
BND | Division 1 | Business_Development |  | TrusteeNegotiations | 232140 | 23 | 21 | 40
BND | Division 1 | Business_Development |  | Acquisition | 232200 | 23 | 22 | 0
BND | Division 1 | Business_Development | Business_Development_RecordsManagement | RecordsManagement | 270000 | 27 | 0 | 0
BND | Division 1 | Business_Development |  | General | 271000 | 27 | 10 | 0
BND | Division 1 | Business_Development |  | Coding_Scaning | 271100 | 27 | 11 | 0
BND | Division 1 | Business_Development | Business_Development_CostRecovery | CostRecovery | 300000 | 30 | 0 | 0
BND | Division 1 | Business_Development |  | PRPPursuit | 301000 | 30 | 10 | 0
BND | Division 1 | Business_Development |  | InsuranceCostRecovery | 301100 | 30 | 11 | 0
BND | Division 1 | Business_Development | Business_Development_ProjectCloseOut | ProjectCloseOut | 780000 | 78 | 0 | 0
BND | Division 1 | Business_Development |  | General | 781000 | 78 | 10 | 0
BND | Division 1 | Business_Development | Business_Development_Contingency | Contingency | 790000 | 79 | 0 | 0
BND | Division 1 | Business_Development |  | CASS | 909000 | 90 | 90 | 0
BER | Division 1 | Berth_Deepening_Channel_Deepening | Berth_Deepening_Channel_Deepening_ProjectAdminandMgmt | ProjectAdminandMgmt | 100000 | 10 | 0 | 0
BER | Division 1 | Berth_Deepening_Channel_Deepening |  | General | 101000 | 10 | 10 | 0
BER | Division 1 | Berth_Deepening_Channel_Deepening | Berth_Deepening_Channel_Deepening_Design | Design | 140000 | 14 | 0 | 0
BER | Division 1 | Berth_Deepening_Channel_Deepening |  | Environmental | 141600 | 14 | 16 | 0
BER | Division 1 | Berth_Deepening_Channel_Deepening |  | Survey | 141800 | 14 | 18 | 0
BER | Division 1 | Berth_Deepening_Channel_Deepening |  | CAD | 142200 | 14 | 22 | 0
BER | Division 1 | Berth_Deepening_Channel_Deepening |  | BidPackage | 142300 | 14 | 23 | 0
BER | Division 1 | Berth_Deepening_Channel_Deepening | Berth_Deepening_Channel_Deepening_Construction | Construction | 190000 | 19 | 0 | 0
BER | Division 1 | Berth_Deepening_Channel_Deepening |  | Contract | 191000 | 19 | 10 | 0
BER | Division 1 | Berth_Deepening_Channel_Deepening |  | EquipmentContracts | 191100 | 19 | 11 | 0
BER | Division 1 | Berth_Deepening_Channel_Deepening |  | Management | 191200 | 19 | 12 | 0
BER | Division 1 | Berth_Deepening_Channel_Deepening |  | Inspection | 191300 | 19 | 13 | 0
BER | Division 1 | Berth_Deepening_Channel_Deepening |  | Testing | 191400 | 19 | 14 | 0
BER | Division 1 | Berth_Deepening_Channel_Deepening |  | Environmental | 191600 | 19 | 16 | 0
BER | Division 1 | Berth_Deepening_Channel_Deepening |  | EngineeringSupport | 191800 | 19 | 18 | 0
BER | Division 1 | Berth_Deepening_Channel_Deepening |  | NavigationSupport | 192100 | 19 | 21 | 0
BER | Division 1 | Berth_Deepening_Channel_Deepening |  | TenantAccess | 192200 | 19 | 22 | 0
BER | Division 1 | Berth_Deepening_Channel_Deepening |  | OperatingDeptSupport | 192300 | 19 | 23 | 0
BER | Division 1 | Berth_Deepening_Channel_Deepening | Berth_Deepening_Channel_Deepening_Permitting | Permitting | 200000 | 20 | 0 | 0
BER | Division 1 | Berth_Deepening_Channel_Deepening |  | General | 201000 | 20 | 10 | 0
BER | Division 1 | Berth_Deepening_Channel_Deepening | Berth_Deepening_Channel_Deepening_Survey | Survey | 210000 | 21 | 0 | 0
BER | Division 1 | Berth_Deepening_Channel_Deepening |  | Reconnaissance | 211000 | 21 | 10 | 0
BER | Division 1 | Berth_Deepening_Channel_Deepening |  | Design | 211100 | 21 | 11 | 0
BER | Division 1 | Berth_Deepening_Channel_Deepening |  | CAD | 211300 | 21 | 13 | 0
BER | Division 1 | Berth_Deepening_Channel_Deepening |  | BidPackage | 211400 | 21 | 14 | 0
BER | Division 1 | Berth_Deepening_Channel_Deepening |  | EngineeringSupport | 211500 | 21 | 15 | 0
BER | Division 1 | Berth_Deepening_Channel_Deepening |  | OperatingDeptSupport | 211600 | 21 | 16 | 0
BER | Division 1 | Berth_Deepening_Channel_Deepening | Berth_Deepening_Channel_Deepening_Maintenance | Maintenance | 220000 | 22 | 0 | 0
BER | Division 1 | Berth_Deepening_Channel_Deepening |  | Environmental | 221000 | 22 | 10 | 0
BER | Division 1 | Berth_Deepening_Channel_Deepening |  | EngineeringSupport | 221100 | 22 | 11 | 0
BER | Division 1 | Berth_Deepening_Channel_Deepening |  | OperatingDeptSupport | 221200 | 22 | 12 | 0
BER | Division 1 | Berth_Deepening_Channel_Deepening |  | BidPackage | 221300 | 22 | 13 | 0
BER | Division 1 | Berth_Deepening_Channel_Deepening |  | Monitoring | 221400 | 22 | 14 | 0
BER | Division 1 | Berth_Deepening_Channel_Deepening | Berth_Deepening_Channel_Deepening_ProjectCloseOut | ProjectCloseOut | 780000 | 78 | 0 | 0
BER | Division 1 | Berth_Deepening_Channel_Deepening |  | General | 781000 | 78 | 10 | 0
BER | Division 1 | Berth_Deepening_Channel_Deepening | Berth_Deepening_Channel_Deepening_Contingency | Contingency | 790000 | 79 | 0 | 0

## Cost Codes (hidden)
SUBGROUP: GENERAL REQUIREMENTS
Division 01 - General Requirements
13100 | Contractor's Management and Coordination
13300 | Submittal Procedures
13500 | Security Control
13501 | Escort
14100 | Permits
15000 | Mobilization and Demobilization
15001 | Traffic Control
15002 | Sweeping
15123 | Temporary Heating, Cooling and Ventilating
15323 | Temporary Ramps
15400 | Construction Aids
15500 | Vehicular Access and Parking
15600 | Temporary Barriers and Enclosures
15713 | Temporary Erosion, Sediment, and Pollution Control
16600 | Product Storage and Handling Requirements
17329 | Cutting and Patching
17400 | Cleaning and Waste Management
17419 | Construction Waste Recycling
19100 | Commissioning
SUBGROUP: FACILITY CONSTRUCTION
Division 02 - Existing Conditions
20500 | Common Work Results for Existing Conditions
24113 | Site Demolition
24119 | Selective Interior Demolition
25000 | Site Remediation
26100 | Removal and Disposal of Contaminated Soils
26500 | Underground Storage Tank Removal
27100 | Groundwater Treatment
28213 | Asbestos Abatement
28216 | Asbestos Management
28313 | Lead-Based Paint Management
28319 | Lead-Based Paint Abatement
28400 | PCB Remediation
Division 03 - Concrete
30500 | Common Work Results for Concrete
31100 | Concrete Formwork
31500 | Concrete Accessories
32000 | Concrete Reinforcing
33000 | Cast-In-Place Concrete
36000 | Concrete Grouting
Division 04 - Masonry
40500 | Common Work Results for Masonry
40513 | Masonry Mortar and Grout
40523 | Masonry Accessories
42113 | Brick Masonry
42200 | Concrete Unit Masonry
Division 05 - Metals
50500 | Common Work Results for Metals
50513 | Galvanic Coatings
51200 | Structural Steel Framing
51213 | Architecturally Exposed Structural Steel Framing
52100 | Steel Joist Framing
53100 | Steel Decking
54000 | Cold-Formed Metal Framing
55000 | Metal Fabrications
55200 | Metal Railings
57050 | Stainless Steel Fabrications
57300 | Glazed Decorative Metal Railings
57500 | Decorative Formed Metal
Division 06 - Wood, Plastics & Composites
60500 | Common Work Results for Wood, Plastics & Composites
60100 | Maintenance of Wood, Plastics, and Composites
61000 | Rough Carpentry
61100 | Framing and Sheathing
61400 | Treated Wood for Roof Repairs
62000 | Finish Carpentry
64000 | Architectural Woodwork
64100 | Custom Cabinets
64200 | Wood Paneling
64600 | Custom Casework
65113 | Plastic Structural Lumber
66000 | Plastic Fabrications
Division 07 - Thermal and Moisture Protection
70500 | Common Work Results for Thermal and Moisture Protection
70152 | Modified Bituminous Sheet Roofing System Repairs
70153 | Elastomeric Sheet Roofing System Repairs
71000 | Waterproofing
71100 | Damp proofing
71800 | Traffic Coatings
72100 | Thermal Insulation
72600 | Vapor Retarders
72700 | Air Barriers
74100 | Roof Panels
74200 | Wall Panels
75000 | Membrane Roofing
75100 | Built-Up Bituminous Roofing
75200 | Modified Bituminous Sheet Roofing System
75300 | Elastomeric Sheet Roofing System
76100 | Sheet Metal Roofing
76200 | Sheet Metal Flashing and Trim
77123 | Manufactured Gutters and Downspouts
77200 | Roof Accessories
78100 | Applied Fireproofing
78400 | Fire stopping
79200 | Joint Sealants
79500 | Expansion Control
Division 08 - Openings
80500 | Common Work Results for Openings
80600 | Door/Window Schedule
81100 | Metal Doors and Frames
81400 | Wood Doors
83100 | Access Doors and Panels
83300 | Coiling Doors and Grilles
83600 | Panel Doors
84113 | Aluminum Entrances and Storefronts
84126 | All-Glass Entrances and Storefronts
84200 | Entrance Door Systems
84400 | Glazed Curtain Walls
85000 | Windows
85100 | Metal Windows
85600 | Special Function Windows
86000 | Skylights
87000 | Finish Hardware
87100 | Door Hardware
88000 | Glazing
89000 | Louvers and Vents
Division 09 - Finishes
90500 | Common Work Results for Finishes
90600 | Room Material and Finish Schedule
92100 | Plaster and Gypsum Board Assemblies
92200 | Supports for Plaster and Gypsum Board
92216 | Non-Structural Metal Stud Framing
92236 | Lath and Plaster
92600 | Veneer Plaster
92713 | Glass-Fiber-Reinforced Plaster Fabrications
92900 | Gypsum Board
93000 | Tile
93013 | Ceramic Tile
93014 | Ceramic Tile Floor Finish
95100 | Acoustical Ceilings
95400 | Specialty Ceilings (linear metal ceilings, etc.)
96100 | Floor Treatment
96200 | Specialty Flooring
96300 | Masonry Flooring
96340 | Stone Flooring
96400 | Wood Flooring
96500 | Resilient Flooring
96519 | Resilient Tile Flooring
96600 | Terrazzo Flooring
96800 | Carpeting
96900 | Access Flooring
97200 | Wall Coverings
97500 | Stone Facing
97700 | Special Wall Surfaces
98400 | Acoustic Room Components (Acoustic Panels)
99100 | Painting (for interior & exterior architectural painting)
99700 | Special Coatings (for painting concrete, masonry, steel, etc.)
Division 10 - Specialties
100500 | Common Work Results for Specialties
101100 | Visual Display Surfaces
101400 | Identifying Devices (identity & way finding signage)
101453 | Traffic Signage
101463 | Baggage Information Display System
102113 | Toilet Compartments
102226 | Operable Partitions
102500 | Service Walls
102600 | Wall and Door Protection
102800 | Toilet and Bath Accessories
104400 | Fire Protection Specialties
105100 | Lockers
107343 | Bus Stop Shelters
107500 | Flagpoles
Division 11 - Equipment
110500 | Common Work Results for Equipment
111100 | Vehicle Service Equipment
111200 | Parking Control Equipment
111300 | Loading Dock Equipment
114000 | Food Service Equipment
115213 | Projection Screens
118200 | Solid Waste Handling Equipment
Division 12 - Furnishings
120500 | Common Work Results for Furnishings
121000 | Art
122000 | Window Treatments
124000 | Furnishings and Accessories
124619 | Clocks
124843 | Floor Mats
125000 | Furniture
126000 | Multiple Seating
129200 | Interior Plants and Planters
Division 13 - Special Construction
130500 | Common Work Results for Special Construction
133400 | Pre-Engineered Buildings
Division 14 - Conveying Equipment
140500 | Common Work Results for Conveying Equipment
142000 | Elevators
143100 | Escalators
143200 | Moving Walks
144000 | Lifts
Division 21 - Fire Suppression
210500 | Common Work Results for Fire Suppression
210519 | Gauges for Fire Suppression Systems
210520 | Piping Specialties for Water-Based Fire Suppression Piping
210523 | General Duty Valves for Water-Based Fire Suppression Piping
210529 | Hangers & Supports for Fire Suppression Piping and Equipment
210548 | Vibration and Seismic Controls for Fire Suppression Piping and Equipment
210553 | Identification for Fire Suppression Piping & Equipment
210590 | Pressure Testing of Fire Suppression Systems
210719 | Fire Suppression Systems Insulation
211100 | Fire Suppression Piping
211120 | Fire Suppression Pumps
212000 | Fire Suppression Systems
212200 | Fire Detection/Inergen Suppression System
Division 22 - Plumbing
220500 | Common Work Results for Plumbing
220519 | Meters and Gauges for Plumbing Piping
220520 | Piping Specialties for Plumbing Piping
220523 | General Duty Valves for Plumbing Piping
220529 | Hangers & Supports for Plumbing Piping & Equip.
220545 | Seismic Restraints for Plumbing Piping and Equipment
220548 | Vibration & Seismic Controls for Plumbing Piping & Equipment
220553 | Identification for Plumbing Piping and Equipment
220590 | Pressure Testing of Plumbing Systems
220719 | Plumbing Insulation
221100 | Plumbing Piping
221120 | Plumbing Pumps
221319 | Liquid Grease Collection System
223000 | Plumbing Equipment
224000 | Plumbing Fixtures
Division 23 - Heating Ventilating & Air Conditioning
230500 | Common Work Results for HVAC
230518 | Expansion Compensation
230519 | Meters and Gauges for HVAC Piping
230520 | Piping Specialties for HVAC Piping
230523 | General Duty Valves for HVAC Piping
230529 | Hangers & Supports for HVAC Piping and Equipment
230545 | Seismic Restraints for HVAC Piping & Equipment
230548 | Vibration & Seismic Controls for HVAC Piping & Equip
230553 | Identification for HVAC Piping and Equipment
230590 | Pressure Testing of HVAC Systems
230593 | Testing, Adjusting, and Balancing
230719 | HVAC Insulation
230900 | Instrumentation and Controls for HVAC
231216 | Gasoline Dispensing Pumps
232000 | HVAC Piping
232215 | Steam and Condensate Specialties
232220 | HVAC Pumps
232400 | Prefabricated Piping Systems
232500 | HVAC Water Treatment
232923 | Variable-Frequency Drives
233113 | Low Pressure Ductwork
233114 | Medium Pressure Ductwork
233115 | High Pressure Ductwork
233300 | Air Duct Accessories
233319 | Sound Attenuators
233400 | HVAC Fans
233443 | Vehicle Exhaust Extraction System
233600 | Air Terminal Units
233700 | Air Outlets and Inlets
234000 | HVAC Air Cleaning Devices
235100 | Breechings, Chimneys, and Stacks
235200 | Heating Boilers and Accessories
235500 | Fuel-Fired Heaters
235523 | Gas-Fired Radiant Heater
235700 | Heat Exchangers for HVAC
236400 | Packaged Water Chillers
237000 | Central HVAC Equipment
238100 | Decentralized Unitary HVAC Equipment
238116 | Computer Room Air Conditioners
238200 | Convection Heating and Cooling Units
Division 26 - Electrical
260500 | Common Work Results for Electrical
260513 | Medium-Voltage Cables
260519 | Low-Voltage Electrical Power Conductors and Cables
260526 | Grounding and Bonding for Electrical Systems
260529 | Hangers and Supports for Electrical Systems
260533 | Raceway and Boxes for Electrical Systems
260536 | Cable Trays for Electrical Systems
260543 | Underground Ducts and Raceways for Electrical Systems
260553 | Identification for Electrical Systems
260573 | Electrical Systems Analysis
260800 | Acceptance Testing
260913 | Electrical Power Monitoring and Control
260943 | Network Lighting Controls
261100 | Substations
261216 | Cast Coil Substation Transformers
262200 | Low-Voltage Transformers
262300 | Low-Voltage Draw-Out Metal-Enclosed Switchgear
262400 | Switchboards and Panel boards
262500 | Enclosed Bus Assemblies
262726 | Wiring Devices
262816 | Enclosed Switches and Circuit Breakers
262900 | Motor Controllers
263200 | Packaged Generator Assemblies for Emergency Power
263353 | Static Uninterruptible Power Supply
263600 | Transfer Switches
265000 | Lighting
265619 | Roadway Lighting
265623 | Apron Lighting
Division 27 - Communications
270500 | Common Work Results for Communications
270553 | Identification for Telecommunication Systems
271000 | Structured Cabling
272100 | Network Equipment
272133 | Wireless Access Points
272200 | IT Hardware
272219 | Servers
272223 | Desktops
272226 | Laptops
272232 | Monitors (desktop)
272234 | Monitors (large screen)
272236 | Radios, Repeaters and Antennas
272413 | Printers
272500 | Software Acquisition and Licensing
273000 | Phone Communications
274100 | Audio-Video Systems
275116 | Public Address and Mass Notification Systems
275319 | Internal Cellular, Paging and Antenna Systems
Division 28 - Electronic Safety & Security
280500 | Common Work Results for Electronic Safety and Security
280513 | Conductors and Cables for Electronic Safety and Security
281300 | Security Access Control System
282300 | Video Surveillance (CCTV System)
282316 | Licenses for Monitoring interfaces
282319 | Recorders
282329 | Cameras and Sensors
281323 | Remote Card readers
283100 | Fire Detection and Alarm
SUBGROUP: SITE AND INFRASTRUCTURE
Division 31 - Earthwork
310500 | Common Work Results for Earthwork
312000 | Site Clearing and Earthwork
312300 | Trenching, Backfilling, and Compacting
312319 | Dewatering
313200 | Soil Stabilization
313700 | Riprap (land)
316213 | Concrete Piles (land)
316214 | Precast, Prestressed Concrete Piles (land)
316216 | Steel Piles (land)
316217 | Steel Sheet Piles (land)
316300 | Bored Piles (land)
316329 | Light Pole Base Piles
Division 32 - Exterior Improvements
320500 | Common Work Results for Exterior Improvements
320117 | Pavement Repair
320118 | Crack Sealing in Flexible Pavements
320128 | Sealing Cracks & Repairing Surface Imperfections in Rigid Pavements
321123 | Aggregate Base Course
321133 | Cement-Treated Base Course
321200 | Asphalt Concrete Paving
321236 | Bituminous Fog Seal Coat
321238 | Cape Seal
321273 | Asphalt Pavement Joint Sealant
321300 | Portland Cement Concrete Paving
321373 | Compression Joint Sealants for Rigid Pavement
321416 | Brick Unit Paving
321613 | Concrete Curbs and Driveways
321614 | Concrete Mow Strip and Controller Base
321615 | Concrete Sidewalk
321723 | Pavement Markings
323113 | Chain-Link Fences and Gates
323114 | Automatic Gate Operator and Control
328400 | Planting Irrigation
329000 | Landscape Maintenance (for PDX projects)
329113 | Soil Preparation
329119 | Landscape Grading
329200 | Clearing and Seeding
329219 | Seeding
329219 | Seeding (Airfield)
329223 | Sodding
329300 | Trees, Shrubs, and Ground Covers
Division 33 - Utilities
330500 | Common Work Results for Utilities
330516 | Utility Structures
331116 | Site Water Utility Distribution Plumbing
333100 | Sanitary Utility Sewerage Piping
333213 | Sanitary Sewer Pump Station
334100 | Storm Utility Drainage Piping
Division 34 - Transportation
340523 | Common Work Results for Railways
340524 | Rail Turnouts
340526 | Rail Walkways
341113 | Track Rails
341116 | Welded Track Rails
341126 | Track Rail Ballast
341193 | Track Appurtenances and Accessories
344113 | Traffic Signals
344213 | Railway Signals
344300 | Airfield Lighting
344302 | Aircraft Guidance Signage
347113 | Guard Posts
347600 | Railway Equipment
347613 | Roadway Crossing Control Equipment
347713 | Passenger Loading Bridges
347716 | Baggage Conveyors
Division 35 - Waterway & Marine
350500 | Common Work Results for Waterway & Marine Construction
353200 | Woody Debris Structures
354000 | Waterway Construction
354237 | Riprap Bank Protection (marine)
355912 | Heavy Timber Pier Construction
355913 | Timber Fender Piles
355914 | Marine Fenders
356213 | Concrete Piles (marine)
356214 | Precast, Prestressed Concrete Piles (marine)
356216 | Steel Pipe Piles (marine)
356217 | Steel Sheet Piles (marine)
352023 | Dredging
SUBGROUP: PROCESS EQUIPMENT
Division 41 - Material Proc. & Handling Equip.
412213 | Cranes
412214 | Crane Rail
SUBGROUP: FAA CONSTRUCTION
Division 51 - Earthwork
510101 | Surface Preparation (P-101)
510151 | Clearing and Grubbing (P-151)
510152 | Excavation and Embankment (P-152)
510153 | Controlled Low-Strength Material (P-153)
510154 | Sub base Course (P-154)
510155 | Lime-Treated Sub grade (P-155)
510156 | Temporary Air & Water Pollution, Soil Erosion, & Siltation Control (P-156)
510158 | Fly Ash Treated Sub grade (P-158)
510161 | Geotextile (P-161)
Division 52 - Flexible Base Courses
520208 | Aggregate Base Course (P-208)
520209 | Crushed Aggregate Base Course (P-209)
520210 | Caliche Base Course (P-210)
520211 | Lime Rock Base Course (P-211)
520212 | Shell Base Course (P-212)
520213 | Sand-Clay Base Course (P-213)
520217 | Aggregate-Turf Pavement (P-217)
Division 53 - Rigid Base Courses
530301 | Soil Cement Base Course (P-301)
530304 | Cement Treated Base Course (P-304)
530306 | Econocrete Sub base Course (P-306)
Division 54 - Flexible Surface Courses
540401 | (Superpave™) Plant Mix Bituminous Pavements (P-401sp)
540402 | Porous Friction Course (P-402)
540403 | (Superpave™) Plant Mix Bituminous Bases (P-403sp)
Division 55 - Rigid Pavement
550501 | Portland Cement Concrete Pavement (P-501)
Division 56 - Miscellaneous
560602 | Bituminous Prime Coat (P-602)
560603 | Bituminous Tack Coat (P-603)
560604 | Compression Joint Seals for Concrete Pavements (Regional) (P-604)
560605 | Joint Sealing Filler (P-605)
560606 | Adhesive Compounds (P-606)
560609 | [ Polymerized ] Bituminous Fog Seal Coat (P-609)
560610 | Structural Portland Cement Concrete (P-610)
560620 | Runway and Taxiway Painting (P-620)
560621 | Saw-Cut Grooves (P-621)
560625 | Coal-Tar Pitch Emulsion Sealcoat (P-625)
560626 | Emulsified Asphalt Slurry Seal Surface Treatment (P-626)
560631 | Refined Coal Tar Emulsion s/Additives, Slurry Seal Surface Treatment (P-631)
Division 57 - Fencing
570160 | Wire Fence with Wood Posts (F-160)
570161 | Wire Fence with Steel Posts (F-161)
570162 | Chain Link Fences (F-162)
570163 | Wild-Life Deterrent Fence (F-163)
Division 58 - Drainage
580701 | Pipe for Storm Drains and Culverts (D-701)
580702 | Slotted Drains (D-702)
580705 | Pipe Under drains for Airports (D-705)
580751 | Manholes, Catch Basins, Inlets, and Inspection Holes (D-751)
580752 | Concrete Culverts, Headwalls, & Misc. Drainage Structures (D-752)
580754 | Concrete Paved Gutters, Ditches, and Flumes (D-754)
Division 59 - Turfing
590901 | Seeding (T-901)
590903 | Sprigging (T-903)
590904 | Sodding (T-904)
590905 | Topsoiling (T-905)
590907 | Tilling (T-907)
590908 | Mulching (T-908)
Division 60 - Lighting Installation
600101 | Airport Rotating Beacon (L-101)
600102 | Airport Hazard Beacon (L-102)
600103 | Airport Beacon Towers (L-103)
600107 | Airport Wind Cones (L-107)
600108 | Airport Underground Cable (L-108)
600109 | Airport Transformer Vault and Equipment (L-109)
600110 | Airport Underground Electrical Duct (L-110)
600115 | Electrical Manholes and Junction Structures (L-115)
600119 | Airport Obstruction Lights (L-119)

## UoM (hidden)
Hard Cost
UoM | % | 1 | Standard View
UoM | Acre | 2 | Engineering Planning View
UoM | CY | 4
UoM | Day | 5
UoM | Ea | 6
UoM | Gal | 7
UoM | Hr | 8
UoM | Lb | 9
UoM | LF | 10
UoM | LS
UoM | SF
UoM | SY
UoM | Ton
UoM | Week
Job

## SoftCostUom (hidden)
Soft Cost
UoM | % | 1
UoM | Week | 2
UoM | Day | 4
UoM | Hr | 5
UoM | Ea | 6
UoM | LS | 7
Job

## Scope and Risk (hidden)
|  |  | Risk Breakdown Structure | Code
|  |  | People | P
Scope Accuracy: | Level 1: Project scope well understood and well defined | People | PEOPLE: Unavailable resources - Engineering (P1) | P1
Scope Accuracy: | Level 2: Project scope conceptual | People | PEOPLE: Unavailable resources - IT (P2) | P2
Scope Accuracy: | Level 3: Project scope is a "vision" with limited detail | People | PEOPLE: Unavailable resources - Project (P3) | P3
|  | People | PEOPLE: Unavailable resources - Business (P4) | P4
|  | People | PEOPLE: Unavailable resources - Sponsor (P5) | P5
Engineering Effort: | Level A: Preliminary engineering performed | People | PEOPLE: Difficulty staffing resources (P6) | P6
Engineering Effort: | Level B: Conceptual engineering performed | People | PEOPLE: Loss of key people - Engineering (P7) | P7
Engineering Effort: | Level C: No engineering performed | People | PEOPLE: Loss of key people - IT (P8) | P8
|  | People | PEOPLE: Loss of key people - Business (P9) | P9
|  | People | PEOPLE: Conflicts interfere with progress (P10) | P10
|  | People | PEOPLE: Resources lack required skills, experience, fit - Engineering (P11) | P11
| Project Charter | People | PEOPLE: Resources lack required skills, experience, fit - IT (P12) | P12
| Business Case - Gate 1 | People | PEOPLE: Resources lack required skills, experience, fit - Business (P13) | P13
| Preliminary Design - Gate 2 | People | PEOPLE: Insufficient onboarding of new project staff (P14) | P14
| 100% Design/ Pre-Bid - Gate 3 | People | PEOPLE: Human error (P15) | P15
| Bid Acceptance - Gate 4 | People | PEOPLE: Project teams lacked sufficient understanding of new technology (P16) | P16
| Project Closeout - Gate 5 | People | PEOPLE: Inability to scale specialty skills (P17) | P17
|  | Requirements | Requirements | R
|  | Requirements | REQUIREMENTS: Project outcomes or scope unclear (R1) | R1
|  | Requirements | REQUIREMENTS: Stakeholders not well understood (R2) | R2
| Stage Gate 1 - Project Charter: +/-50% | Requirements | REQUIREMENTS: Error or omissions in requirements (R3) | R3
| Stage Gate 2 - Business Case: +/-30% | Requirements | REQUIREMENTS: Significant learning, new ground (R4) | R4
| Stage Gate 3 - Preliminary Planning: +/-25% | Requirements | REQUIREMENTS: Shifting business timelines, priorities (R5) | R5
| Stage Gate 4a - 30% Design: -15% to +20% | Requirements | REQUIREMENTS: Inability to accurately translate business requirements into infrastructure scope (R6) | R6
| Stage Gate 4a - 60% Design: -10% to +15% | Requirements | REQUIREMENTS: Unforeseen complexity or understanding of infrastructure (R7) | R7
| Stage Gate 4a - 90% Design: +/-10% | Requirements | REQUIREMENTS: Mismatch of expectations between customers, sponsors, vendors (R8) | R8
| Stage Gate 4b - CD Design: +/-5% |  | Process | PRC
|  | Process | PROCESS: Poor work breakdown or estimating (PRC1) | PRC1
| Percentage Based | Process | PROCESS: Operational processes not well understood (PRC2) | PRC2
| Hourly Estimate | Process | PROCESS: Insufficient understanding of environmental complexity, dependencies (PRC3) | PRC3
|  | Process | PROCESS: Delays in reviews, approvals, decision-making problems (PRC4) | PRC4
|  | Process | PROCESS: Management or escalation problems (PRC5) | PRC5
|  | Process | PROCESS: Sliced work or unclear hand-offs (PRC6) | PRC6
|  | Process | PROCESS: Delivery methodology not well applied (PRC7) | PRC7
|  | Process | PROCESS: Unclear roles and responsibilities (PRC8) | PRC8
|  | Process | PROCESS: Gatekeepers or assessors lack skill, knowledge to make gate assessments/decisions (PRC9) | PRC9
|  | Process | PROCESS: Skill or accountability gap on complex end-to-end architecture/engineering solutions versus product solution (PRC10) | PRC10
|  | Process | PROCESS: Insufficient engagement to prepare estimates (PRC11) | PRC11
|  | Process | PROCESS: Project staff lacked sufficient understanding of Port processes (PRC12) | PRC12
|  | Process | PROCESS: Stakeholders responsibilities not well understood (PRC13) | PRC13
|  | Process | PROCESS: Changing process (PRC14) | PRC14
|  | Process | PROCESS: Insufficient of unclear process (PRC15) | PRC15
|  | Process | PROCESS: Insufficient technology piloting (PRC16) | PRC16
|  | Process | PROCESS: Permitting delays (PRC17) | PRC17
|  | Data | Data | D
|  | Data | DATA: Development quality or production inconsistencies (D1) | D1
|  | Data | DATA: Data quality problems (D2) | D2
|  | Data | DATA: Date management problems (D3) | D3
|  | Data | DATA: Limited access to data (D4) | D4
|  |  | Vendor | V
|  | Vendor | VENDOR: Resources lack sufficient depth of skills, experience, fit - Services vendor (V1) | V1
|  | Vendor | VENDOR: Unavailable resources - Services vendor (V2) | V2
|  | Vendor | VENDOR: Quality of goods not sufficient - Product vendor (V3) | V3
|  | Vendor | VENDOR: Procurement or contract problems (V4) | V4
|  |  | Quality | Q
|  | Quality | QUALITY: Quality metrics not well understood (Q1) | Q1
|  | Quality | QUALITY: Inappropriate test plans (Q2) | Q2
|  | Quality | QUALITY: Insufficient testing (Q3) | Q3
|  | Quality | QUALITY: New, complex problems discovered (Q4) | Q4
|  | Quality | QUALITY: insufficient quality management expertise (Q5) | Q5
|  | Quality | QUALITY: Inconsistent use of quality tools (Q6) | Q6
|  | Quality | QUALITY: Inadequate design (Q7) | Q7
|  |  | Technical | TEC
|  | Technical | TECHNICAL: Infrastructure not available (TEC1) | TEC1
|  | Technical | TECHNICAL: Complex physical infrastructure (TEC2) | TEC2
|  | Technical | TECHNICAL: Complex software infrastructure (TEC3) | TEC3
|  | Technical | TECHNICAL: Nonstandard Port tools, components, frameworks (TEC4) | TEC4
|  | Technical | TECHNICAL: Poor infrastructure performance (TEC5) | TEC5
|  | Technical | TECHNICAL: Complex interfaces with other systems (TEC6) | TEC6
|  |  | Turnover | TO
|  | Turnover | TURNOVER: Client acceptance process is not clear or not approved (TO1) | TO1
|  | Turnover | TURNOVER: Required skill in people not ready (TO2) | TO2
|  | Turnover | TURNOVER: More support required than expected (TO3) | TO3
|  | Turnover | TURNOVER: Business turnover problems (TO4) | TO4
|  | Turnover | TURNOVER: IT support turnover problems (TO5) | TO5
|  |  | Product | PRO
|  | Product | PRODUCT: Complex large design/development (PRO1) | PRO1
|  | Product | PRODUCT: Product quality problems (PRO2) | PRO2
|  |  | Uncategorized | U
|  | Uncategorized | UNCATEGORIZED: Uncategorized risk - description required (U1) | U1
Construction
|  | Construction | CONSTRUCTION: Potential survey error e.g. incorrect grades, locational error etc (C1) | C1
|  | Construction | CONSTRUCTION: Potential delay resulting from the Private Utilities being tardy in relocating utilities (C2) | C2
|  | Construction | CONSTRUCTION: Unforeseen site conditions (utilities, environmental etc) during construction (C3) | C3
|  | Construction | CONSTRUCTION: Differential settlement to properties due to work; impacts to design and construction (C4) | C4
|  | Construction | CONSTRUCTION: Cost escalation (of materials/equipment) during construction period (C5) | C5
|  | Construction | CONSTRUCTION: Risk that price of steel may increase prior to order by contractor (C6) | C6
|  | Construction | CONSTRUCTION: Additional streetscape or stormwater requirements (C7) | C7
C8
C9
C10
C11

## Work Plan
Look at project titles for which of the 3 work areas are
being considered with this cost estimate
2023-06-01
Area of 3" mill & inaly pulled from 8-25-22 estimate "2026 Taxiway K West Rehabilitation" prepared by Eric Hein.
345800 | SF
7/25-28/2023
Area of 3" mill & inlay now to extend from Rwy 3-21 / Taxiway E intersection to Exit K1 holdline.
Jennifer Rabby provided area of reduction as 209,000 SF. Revised M&I area = 345,800-209,000 = |  |  |  |  | 136800 | SF.
This reduces AC surface course by 6,900 Tons - 2,730 Tons = |  |  | 4170 | Tons
Previous OPC - AC Surface = 10,110 Tons - 4,170 Tons = |  | 5940 | Tons for reduced project
1
2
3